Chapter- 2.2c

Hydro Capacity Addition during the Year 2014-15

| Sl. No. | Particular | Unit Nos. | Capacity (MW) |  |  |  |  | Commissioning as per program |  | Actual (A)/ Anticipated |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Target |  |  | Actual |  |  |  |  |  |  |
| A. Central Sector |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Parbati-III NHPC, HP 4x130= 520 MW | Unit # 4 |  | 130 |  | 130 |  | Aug- 14 |  | 22.05.2014 (A) |  |  |
| 2 | Rampur SJVN Limited, HP. 6x68.67 = 412 MW | Unit # 3 Unit # 4 Unit # 6 |  | 68.67 68.67 68.67 |  | 68.67 68.67 68.67 |  | Jun 14 May 14 Apr 14 |  | 31.07.2014(A) 12.06.2014(A) 04.12.2014(A) |  |  |
| Out side the Programme |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Koldam NTPC, H.P. 4x200 = 800 MW | Unit # 1 Unit # 2 |  |  |  | 200 200 |  | Mar-15 Mar-15 |  | 31.03.2015 (A) 30.03.2015 (A) |  |  |
|  | Sub- total (A): |  |  | 336 |  | 736 |  |  |  |  |  |  |
| B. State Sector |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Lower Jurala TSGENCO, Telangana 6x40= 240 MW | Unit # 1 Unit # 2 Unit # 3 Unit # 4 |  | 40 40 40 40 | 0 0 0 0 |  | Jul.-14 Jul.-14 Oct.-14 Mar.-15 |  | 2015-16 2015-16 2015-16 2015-16 |  | Slipped due to flooding of Power House on 30.07.2014 during synchronization process for Unit # 1 to Unit# 3. |  |
| 5 | Nagarjuna Sagar APGENCO, A.P. 2x25= 50 MW | Unit # 1 Unit # 2 |  | 25 25 | 0 0 |  | Sep-14 Dec-14 |  | 2015-16 2015-16 |  | Commissioning delayed due to non-availability of water. |  |
|  | Sub- total (B): |  |  | 210 | 0 |  |  |  |  |  |  |  |
| C. Private Sector |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Jorethang Loop DANS Pvt. Ltd., Sikkim 2x48= 96 MW | Unit # 1 Unit # 2 |  | 48 48 | 0 0 |  | Feb-15 Mar-15 |  | 2015-16 |  | Slipped due to non-completion of HRT. |  |
| 7 | Teesta-III Teesta Urja, Sikkim 6x200= 1200 MW | Unit # 6 |  | 200 | 0 |  |  |  | 2016-17 |  | Slipped due to Financial crunch with the Developer. |  |
|  | Sub- total (C): |  |  | 296 | 0 |  |  |  |  |  |  |  |
|  | Total (A+B+C) |  |  | 842 | 736 |  |  |  |  |  |  |  |

Out side RFD achievements:

Unit #1 & # 2 (400 MW) of Kol Dam HEP commissioned during March, 2015.