# EXECUTIVE SUMMARY

Trend of Hydro-Thermal Mix as on 30.09.2015

| Hydro: | 42,283.42 MW | (17.45%) |
| --- | --- | --- |
| Thermal: | 1,94,199.56 MW | (80.16%) |
| Nuclear: | 5,780.00 MW | (02.39%) |

Hydro Capacity Under Execution (As on 30.09.2015): A hydro capacity of 13,852 MW   is under execution to give benefits during remaining period of 12th Plan & beyond. Sector wise details are given as under:-

| Sector | Capacity (MW) |
| --- | --- |
| Central | 7275 |
| State | 2022 |
| Private | 4555 |
| Total: | 13,852 MW |

12th Plan Hydro Capacity Addition as Plan Progress:-

Hydro Capacity Addition for the Year 2012-13: Hydro Capacity Addition Monitorable Targets for the Year 2012-13  was 802 MW (645 MW in Central Sector, 87 MW in State Sector, and 70 MW in Private Sector.).  A Capacity of 501 MW  (374 MW in Central Sector, 57 MW in State Sector and 70 MW in Private Sector) has been achieved during 2012-13. Project-wise details are given in Chapter 2.2a.

Hydro Capacity Addition for the Year 2013-14: Hydro Capacity Addition Monitorable Targets for the Year 2013-14  is 1198 MW (914 MW in Central Sector, 85 MW in State Sector and 199 MW in Private Sector.).  A Capacity of 1058 MW  (914 MW in Central Sector, 45 MW in State Sector and 99 MW in Private Sector) has been achieved during the year 2013-14. Project-wise details are given in Chapter 2.2b.

Hydro Capacity Addition for the Year 2014-15: Hydro Capacity Addition Monitorable Targets for the Year 2014-15 is 842 MW (336 MW in Central Sector, 210 MW in State Sector and 296 MW in Private Sector.).  A Capacity of 736 MW in Central Sector has been achieved during the year 2014-15. Project-wise details are given in Chapter 2.2c.

Hydro Capacity Addition for the Year 2015-16: Hydro Capacity Addition Monitorable Targets for the Year 2015-16 is 1691 MW (590 MW in Central Sector, 575 MW in State Sector and 526 MW in Private Sector) A Capacity of 1166 MW (400 MW in Central Sector 340 MW in State Sector and 426 MW in Private Sector) has been achieved during the year 2015-16 up to 30.09.2015. Project-wise details are given as under:-

Hydro Projects Monitorable Target for 2015-16

| Sl. No. | Particular |  | Unit Nos. | Cap. (MW) |  | Commissioning as programmed |  | Actual(A)/ Anticipated |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A. | Central Sector |  |  |  |  |  |  |  |  |  |
| 1 | Koldam NTPC, HP 4x200= 800 MW | Unit # 3 Unit # 4 |  | 200 200 | 4/15 5/15 |  | 10.04.2015(A) 12.06.2015(A) |  |  |  |
| 2 | Teesta Low Dam IV NHPC, West Bengal 4x40 = 160 MW | Unit # 1 Unit # 2 |  | 40 40 | 2/16 3/16 |  | Feb 16 Mar 16 |  |  |  |
| 3 | Pare NEEPCO, Arunachal Pradesh 2x55=110 MW | Unit # 1 Unit # 2 |  | 55 55 | 3/16 3/16 |  | 2016-17 2016-17 |  | Coffer dam over toppled in June, 15. Work on Dam started w.e.f. Oct’15 after dewatering the area. |  |
|  | Sub- total (A): |  |  | 590 |  |  |  |  |  |  |
| B. | State Sector |  |  |  |  |  |  |  |  |  |
| 4 | Baglihar - II JKPDC, J&K 3x150= 450 MW | Unit # 1 Unit # 2 |  | 150 150 | 9/15 9/15 |  | 05.09.2015(A) 29.09.2015(A) |  |  |  |
| 5 | Kashang – I HPPCL, H.P. 1x65=65 MW | Unit # 1 |  | 65 | 3/16 |  | 3/16 |  |  |  |
| 6 | Lower Jurala TSGENCO, Telangana 6x40= 240 MW | Unit # 1 Unit # 2 Unit # 3 Unit # 4 |  | 40 40 40 40 | 7/15 8/15 9/15 10/15 |  | 10/15 30.09.2015(A) 10/15 |  | Unit 1 could not be commissioned due to non- availability of water. Now likely to be commissioned in Oct.2015. |  |
| 7 | Nagarjuna Sagar TR APGENCO, AP 2x25=50 MW | Unit # 1 Unit # 2 |  | 25 25 | 7/15 7/15 |  | 10/15 10/15 |  | Unit 1 & 2 could not be commissioned due to non- availability of water. |  |
|  | Sub- total (B): |  |  | 575 |  |  |  |  |  |  |
| C. | Private Sector |  |  |  |  |  |  |  |  |  |
| 8 | Sorang HSPCL, H.P. 2x50 = 100 MW | Unit # 1 Unit # 2 |  | 50 50 | 6/15 6/15 |  | 11/15 11/15 |  | Lilo of Sorang Trans. line with Karcham Wangtoo – Abdullahpur line to be done. |  |
| 9 | Srinagar AHPCL, Uttarakhand 4x82.5=330 | Unit # 1 Unit # 2 Unit # 3 Unit # 4 |  | 82.5 82.5 82.5 82.5 | 4/15 4/15 5/15 6/15 |  | 10.04.2015(A) 08.06.2015(A) 20.04.2015(A) 03.06.2015(A) |  |  |  |
| 10 | Jorethang Loop DANS Pvt. Ltd., Sikkim 2x48= 96 MW | Unit # 1 Unit # 2 |  | 48 48 | 9/15 10/15 |  | 22.09.2015(A) 23.09.2015(A) |  |  |  |
|  | Sub- total (C): |  |  | 526 |  |  |  |  |  |  |
|  | Total (A+B+C) |  |  | 1691 |  |  |  |  |  |  |
|  | Note: 1166 MW out of 1691MW is Commissioned. |  |  |  |  |  |  |  |  |  |