- CHAPTER- 11

- DETAILS OF UNDER CONSTRUCTION HYDRO ELECTRIC PROJECTS (ABOVE 25 MW)

- HAVING TIME/COST OVERRUN

| Sl. No | Project Name/(I.C.)/ Executing Agency | State |  | Unit No. | Cap. (MW) | Org. Comm. Sched. | Latest Comm. Sched. | Time over run (months) | Org. Cost (Rs. in Crores) | Latest Cost (Rs. in Crores) | Cost over run (Rs. in Crores) | Reasons for time and cost over run |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| CENTRAL SECTOR |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Tapovan Vishnughad (4x130 = 520 MW) NTPC | Uttara khand | 1 2 3 4 |  | 130 130 130 130 | 2012-13 2012-13 2012-13 2012-13 | 2018-19 2018-19 2018-19 2018-19 | 72 | 2978.48 (11/06) | 3846.30 (01/14) Latest approved | 867.82 | - Delay in procurement/deployment of Tunnel Boring Machine by Civil Contractor. - Slow progress in Power house due to poor rock strata. - Heavy water ingress due to bad geology in HRT and rock fall on TBM. - Flash flood in June, 2013. - Termination of civil contracts for Barrage and HRT. |
| 2 | Lata Tapovan (3x57 = 171 MW) NTPC | Uttara khand | 1 2 3 |  | 57 57 57 | 2017-18 2017-18 2017-18 | 2021-22 2021-22 2021-22 | 48 | 1527.00 | 1527.00 | Nil | - Flash flood during June, 2013 in Uttarakhand. - Local issues / non-start of works in Barrage area - Hon’ble Supreme court ban on construction works since May-14.. |
| 3 | Pare (2x55 = 110 MW) NEEPCO | Arunachal Pradesh | 1 2 |  | 55 55 | 2012-13 | 2016-17 2016-17 | 48 | 573.99 (06/07) | 1487.49 (12/14) | 913.50 | - Law & Order problem. - Poor geology. - Poor approach roads. - Flash flood during May-Aug, 2014 - Flash flood during Jun-Sep, 2015. Dam area inundated with water, Concreting of Dam effected for 04 months. |
| 4 | Tuirial (2x30 = 60 MW) NEEPCO | Mizoram | 1 2 |  | 30 30 | 2013-14 2013-14 | 2016-17 2016-17 | 36 | 368.72 | 1381.71 | 1012.99 | - Susension of Project activities due to local agitation for about 7 yrs. (June-2004 to May-2011) - Poor approach roads. - Slope failure in Power House. |
| 5 | Kameng (4x150 = 600 MW) NEEPCO | Arunachal Pradesh | 1 2 3 4 |  | 150 150 150 150 | 2009-10 2009-10 2009-10 2009-10 | 2016-17 2016-17 2016-17 2016-17 | 84 | 2496.90 (03/04) | 6476.34 (12/14) | 3979.44 | - Change in dam parameters. - Slow progress in dam & HRT due to Bad geology, heavy seepage, inadequate machinery. - Flash flood in Oct. 2008 and Sept. 2012. - Ingress of water in HRT. - Poor approach roads. - Contractual issues. - Shortage of aggregate. - Clearance for quarry from State Govt. |
| 6 | Tehri PSS (4x250 = 1000 MW) THDC | Uttara khand | 1 2 3 4 |  | 250 250 250 250 | 2010-11 2010-11 2010-11 2010-11 | 2018-19 2018-19 2018-19 2018-19 | 96 | 1657.60 | 2978.86 | 1321.26 | - Approval of RCE as L-1 price bid was more than cost estimate. RCE approved in Nov-2011. - Litigation by bidders. - Poor geology. - Local agitation at Asena Quarry. - Agitation at muck disposal area. - Poor preparedness of contractor. - Revision of Lay out of machine hall due to poor geology. |
| 7 | Teesta Low Dam– IV (4x40 = 160 MW) NHPC | West Bengal | 1 2 3 4 |  | 40 40 40 40 | 2009-10 2009-10 2009-10 2009-10 | 2015-16 2015-16 2016-17 2016-17 | 72 84 | 1061.38 (03/05) | 2162.46 | 1101.08 | - Delay in forest clearance. - Flash flood in July, 2007, May, 2009 & July, 2010. - Gorkha Jan Mukti agitations/bandhs. - Cash crunch of Civil contractor (M/s HCC), the civil works were at halt from March, 2013 to November, 2014. |
| 8 | Parbati - II (4x200 = 800 MW) NHPC | Himachal Pradesh | 1 2 3 4 |  | 200 200 200 200 | 2009-10 2009-10 2009-10 2009-10 | 2018-19 2018-19 2018-19 2018-19 | 108 | 3919.59 (12/01) | 7818.68 (03/15) | 3899.09 | - Hon’ble High Court of Himachal Pradesh ban on stone crusher operation. - Delay in revised forest clearance. - TBM suffered extensive damage due to heavy ingress of water and slush in TBM face in Nov, 2006. - Slide in Power House area in Apr-04, Jun-06 and Feb-07. - Flash flood in 2004,2005,2010 and 2011. - Jiwa Nallah works affected due to cavity treatment. - Contractual issues. |
| 9 | Subansiri Lower (8x250 = 2000 MW) NHPC | Arunachal Pradesh/ Assam | 1 2 3 4 5 6 7 8 |  | 250 250 250 250 250 250 250 250 | 2009-11 2009-11 2009-11 2009-11 2009-11 2009-11 2009-11 2009-11 | 2019-21 (subject to re-start of works) | 120 | 6285.33 (12/02) | 16865 (04/15) | 10599.67 | - Disruption of works by locals in Ar. Pradesh side. - Slope failure in Power House in Jan, 2008. - Damage to bridge on Ranganadi river. - Change in design of surge shafts to surge tunnels. - Stoppage of works due to agitation launched by Anti Dam activists in Assam against construction of Project. Work stopped since 16.12.2011. - Issue of D/s impact studies. |
| 10 | Kishanganga (3x110 = 330 MW) NHPC | Jammu & Kashmir | 1 2 3 |  | 110 110 110 | 2015-16 2015-16 2015-16 | 2016-17 2016-17 2016-17 | 12 | 3642.04 (09/07) | 5497.72 | 1855.68 | - Heavy Rainfall in March, 2011. - Cavity in HRT – TBM portion. - Poor geology in Access tunnel. - Dam works affected due to arbitration proceedings at International Court of Arbitration. - Local people demanding Employment in NHPC. - R&R Issues. |
| 11 | Vishnugad Pipalkoti (4x111 = 444 MW) THDC | Uttara khand | 1 2 3 4 |  | 111 111 111 111 | 2013-14 2013-14 2013-14 2013-14 | 2019-20 2019-20 2019-20 2019-20 | 72 | 2491.58 (03/08) | 3745.08 (10/11) | 1253.50 | - CCEA approval in Aug-2008 but works could not be awarded due to Forest clearance/diversion of forest land. Forest land was acquired in January-14 and subsequently works awarded in January-2014. - Disruption of works by local people. |
|  | STATE SECTOR |  |  |  |  |  |  |  |  |  |  |  |
| 12 | Kashang-I (1x65 = 65 MW) HPPCL | Himachal Pradesh | 1 |  | 65 | 2013-14 | 2015-16 | 24 | 478.02 (03/08) | 478.02 (03/08) | Nil | - Slow progress of civil and E&M works. - Flash flood in June, 2013. - Approach roads washed off during heavy rains in Monsoon 2013. |
| 13 | Kashang-II & III (1x65 + 1x65 MW) =130 MW HPPCL | Himachal Pradesh | 1 2 |  | 65 65 | 2013-14 2013-14 | 2018-19 2018-19 | 60 | 601.78 (03/08) | 601.78 (03/08) | Nil | - Local issues. Works could not be started due to continuous agitation by Lipa villagers. Matter is sub-judice. - Flash flood in June, 2013. - Works stopped by contractor. |
| 14 | Uhl-III (3x33.33 = 100 MW) BVPCL (HPSEB) | Himachal Pradesh | 1 2 3 |  | 33.33 33.33 33.33 | 2006-07 2006-07 2006-07 | 2017-18 2017-18 2017-18 | 132 | 431.56 (09/02) | 940.84 (03/08) | 509.28 | - Delay in award of works. - Contract for construction of HRT rescinded twice i.e. during May, 2008 & July, 2010 due to slow progress and non-performance by the contractor. - Poor geology in HRT. |
| 15 | Sawra Kuddu (3x37 =111MW) HPPCL, | Himachal Pradesh | 1 2 3 |  | 37 37 37 | 2010-11 2010-11 2010-11 | 2018-19 2018-19 2018-19 | 96 | 558.53 (03/03) | 1181.90 (03/12) | 623.37 | - Delay in MOEF clearance. - Delay in award of Civil & E&M works. - Poor geology in HRT. - Slow progress of HRT Lining. - Contractual issues - Contract for HRT package terminated on 9.1.14. Re-awarded in Nov,2014 to M/s. HCC. |
| 16 | Sainj (2x50 = 100 MW) HPPCL | Himachal Pradesh | 1 2 |  | 50 50 | 2014-15 2014-15 | 2016-17 2016-17 | 24 | 784.56 | 784.56 | Nil | - Slow progress of HRT and Barrage works - Local issues |
| 17 | Shongtom Karcham (3x150 = 450 MW) HPPCL 16.08.2012 | Himachal Pradesh | 1 2 3 |  | 150 150 150 | 2017-18 2017-18 2017-18 | 2018-19 2018-19 2018-19 | 12 | 2807.83 | 3316.35 | 508.52 | - Shifting of Army Ammunition Depot. |
| 18 | Lower Jurala (6x40 = 240 MW) TGENCO | Telangana | 1 2 3 4 5 6 |  | 40 40 40 40 40 40 | 2011-13 2011-13 2011-13 2011-13 2011-13 2011-13 | 2015-16 2015-16 2015-16 2015-16 2016-17 2016-17 | 36 Comm. 36 48 | 908.34 (05/07) | 1969.14 | 566.49 | - Delay in award of E&M works. - Slow progress in civil works. Land acquisition problem. - Unprecedented flood in 2009, 2010, 2012 & 2013. - Frequent bandh by TJAC for Telangana State. - Agitation by local villagers. - Right flank Dam concreting was stopped by the villagers from 23.04.2011 to 30.11.2012. - Slow progress of HM works. - Unit-1 & 2 could not be commissioned in 2013-14 due to less availability of water. - Submergence of Power House on 30.07.2014 due to release of flood water from Priyadarshni Jurala. |
| 19 | Pulichintala (4x30 = 120 MW) TGENCO | Telengana | 1 2 3 4 |  | 30 30 30 30 | 2009-11 2009-11 2009-11 2009-11 | 2016-17 2016-17 2016-17 2016-17 | 72 | 380.00 (2006-07) | 563.49 | 183.49 | - Delay in award of E&M works. - Unprecedented floods in Oct.2009 & Sept.2011. - Contractual issues. - Slow progress of Power House works. |
| 20 | Nagarjuna Sagar Tail Pool Dam (2x25 = 50 MW) APGENCO | Andhra Pradesh | 1 2 |  | 25 25 | 2008-09 2008-09 | 2015-16 2015-16 | 84 | 464.63 (2002-03) | 958.67 | 494.04 | - Slow progress of dam due to frequent flooding during 2009, 2011& 2013. - Delay in award of HM works. - Contractual issues in Dam works. - Non-availability of water. |
| 21 | Pallivasal 2x30 = 60 MW KSEB | Kerala | 1 2 |  | 30 30 | 2010-11 2010-11 | 2018-19 2018-19 | 96 | 222.00 (2004) | 284.69 (2007) | 62.69 | - Slow progress of civil works. - Delay in land acquisition. - Change in alignment of Adit to HRT. - Poor geology strata in HRT. - Heavy Monsoon |
| 22 | Thottiyar (1x30+1x10)= 40MW KSEB | Kerala | 1 2 |  | 30 10 | 2012-13 2012-13 | 2018-19 2018-19 | 72 | 136.79 (2007) | 150.02 | 13.23 | - Land acquisition issue. - The works of weir and approach channel stopped from 2010 to 2012 by local people. - The work stopped by Court from 12.12.2012 to April-2013. |
| 23 | New Umtru (2x20 =40 MW) MePGCL | Meghalaya | 1 2 |  | 20 20 | 2011-12 2011-12 | 2016-17 2016-17 | 60 | 226.40 | 461.27 | 234.87 | - Delay in award of works. - Slow progress of civil works. |
| 24 | ## Shahpurkandi 3x33+3x33+1x8 =206 MW, Irrigation Deptt. &PSPCL | Punjab | 1 2 3 4 5 6 7 |  | 33 33 33 33 33 33 8 | 2017-18 | 2018-19 | 12 | 2285.81 | 2285.81 | Nil | - Works of Dam stopped since 29.08.2014 due to inter-state dispute between states of J&K & Punjab. |
| 25 | Koyna Left Bank PSS 2x40 = 80 MW WRD, Mah. | Maharashtra | 1 2 |  | 40 40 | 2017-18 2017-18 | 2018-19 2018-19 | 12 | 226.40 | 379.78 | 153.38 | - Slow progress of works. - Fund constraints due to increase in project cost. RCE under approval. |
|  | PRIVATE SECTOR |  |  |  |  |  |  |  |  |  |  |  |
| 26 | Tidong-I 2x50 =100 MW NSL Tidong | Himachal Pradesh |  | 1 2 | 50 50 | 2013-14 2013-14 | 2017-18 2017-18 | 48 | 543.15 (08/05) | 543.15 (08/05) | Nil | - Delay in NOC by Projects affected Panchayats, suspension of works by Govt.for one year. |
| 27 | Tangnu Romai-I (2x22 = 44 MW) TRPGPL | Himachal Pradesh |  | 1 2 | 22 22 | 2014-15 2014-15 | 2018-19 2018-19 | 48 | 255.00 (2006) | 255..0 (2006) | Nil | - Slow progress of civil works. - Poor geology. - Difficult area. - Weather conditions & accessibility. |
| 28 | Sorang (2x50 = 100 MW), HSPPL | Himachal Pradesh |  | 1 2 | 50 50 | 2012-13 2012-13 | 2015-16 2015-16 | 36 | 586.00 (2006) | 586.00 (2006) | Nil | - Poor geology. - Difficult area. - Weather conditions & accessibility. - Penstock cracks / leakage during filling of Water conductor System. |
| 29 | Singoli Bhatwari (3x33 = 99 MW) L&T | Uttarakhand |  | 1 2 3 | 33 33 33 | 2014-15 2014-15 2014-15 | 2019-20 2019-20 2019-20 | 60 | 666.47 (2008) | 666.47 (2008) | Nil | - Poor geology in HRT. - Agitation by local people. - Flash flood in June,2013. |
| 30 | Phata Byung (2x38 = 76 MW), LANCO | Uttara khand |  | 1 2 | 38 38 | 2013-14 2013-14 | 2017-18 2017-18 | 48 | 520.00 | 520.00 | Nil | - Flash flood in June,2013. - Poor geology in HRT. |
| 31 | Maheshwar (10x40 = 400 MW) SMHPCL | Madhya Pradesh |  | 1 2 3 4 5 6 7 8 9 10 | 40 40 40 40 40 40 40 40 40 40 | 2001-02 2001-02 2001-02 2001-02 2001-02 2001-02 2001-02 2001-02 2001-02 2001-02 | 2017-18 | 192 | 1569.27 (96-97) | 4635.00 | 1190.73 | - R&R issues - Cash flow problem with developer |
| 32 | Teesta Stage III (6x200 = 1200 MW) Teesta Urja Limited | Sikkim |  | 1 2 3 4 5 6 | 200 200 200 200 200 200 | 2011-12 2011-12 2011-12 2011-12 2011-12 2011-12 | 2016-17 2016-17 2016-17 2016-17 2016-17 2016-17 | 60 | 5705.55 | 11382.00 | 5676.45 | - Delay in forest clearance. - Works suffered due to earthquake in Sept.2011. - Financial constraints with developer - Delay in Pressure shaft works. - Delay in Power Evacuation arrangement. |
| 33 | Teesta Stage VI (4x125 = 500 MW) Lanco Energy Private Limited | Sikkim |  | 1 2 3 4 | 125 125 125 125 | 2012-13 2012-13 2012-13 2012-13 | 2021-22 2021-22 2021-22 2021-22 | 108 | 3283.08 | 5400.00 | 2116.92 | - Poor geology. - Land acquisition. - Contractual issues - Funds constraints with developer |
| 34 | Rangit-IV HE Project (3X40 = 120 MW) JPCL | Sikkim |  | 1 2 3 | 40 40 40 | 2012-13 2012-13 2012-13 | 2018-19 2018-19 2018-19 | 72 | 726.16 | 726.16 | Nil | - Slow progress of HRT & Surge Shaft works due to poor geology. - Works hampered due to earthquake in September, 2011. - Financial constraints with developer |
| 35 | Bhasmey (2x25.5 =51 MW) Gati Infrastructure | Sikkim |  | 1 2 | 25.5 25.5 | 2012-13 2012-13 | 2019-20 2019-20 | 84 | 408.50 | 408.50 | Nil | - Forest clearance - Financial constraints with developer |
| 36 | Rongnichu (2x48 =96 MW) Madhya Bharat Pvt. Co.Ltd. | Sikkim |  | 1 2 | 48 48 | 2015-16 2015-16 | 2019-20 2019-20 | 48 | 491.32 | 491.32 | Nil | - Land Acquisition - Poor geology. |
| 37 | Ratle (4x205+1x30) = 850 MW Ratle HEP Pvt .Ltd. | J&K |  | 1 2 3 4 5 | 205 205 205 205 30 | 2017-18 2017-18 2017-18 2017-18 2017-18 | 2021-22 2021-22 2021-22 2021-22 2021-22 | 48 | 5517.02 | 5517.02 | Nil | - Slow progress of works. |
| 38 | Gongri 2x72= 144 MW Dirang Energy (P)Ltd | Ar. Pradesh |  | 1 2 | 72 72 | 2017-18 2017-18 | 2021-22 2021-22 | 48 | 1436.27 | 1436.27 | Nil | - Works awarded on 22.11.2011. However, consent to establish from State Pollution Control Board was issued on 19-5-14. |
| 39 | Bajoli Holi 3x60= 180 MW M/s GMR Bajoli Holi | H.P. |  | 60 60 60 | 180 | 2017-18 | 2019-20 | 24 | 1696.93 | 1696.93 | Nil | - Slow progress of works. |
| 40 | Dikchu 3x32= 96 MW Sneha Kinetic Power Projects Pvt. Ltd. | Sikkim |  | 32 32 32 | 96 | 2017-18 | 2019-20 | 24 | 639.57 | 639.57 | Nil | - Slow progress of works. |
| 41 | Rangit-II 2x33= 66 MW Sikkim Hydro Power Ltd. | Sikkim |  | 33 33 | 66 | 2017-18 | 2019-20 | 24 | 498.00 | 498.00 | Nil | - Slow progress of works. |
| 42 | Panan 4x75= 300 MW Himagiri Hydro Energy Pvt. Ltd. | Sikkim |  | 75 75 75 75 | 300 | 2018-19 | 2020-21 | 24 | 1 833.05 | 1833.05 | Nil | - Clearance from NWLB |