## Ch 5
CHAPTER- 5
Sanctioned Hydro Projects for 12th Plan & Beyond
(Excluding projects under Ministry of New & Renewable Energy)
Sl. | Name of Scheme | State | I.C. | Benefits | Date of | Likely
No. |  |  | (No. x MW) | (MW) | Approval | Commng.
A. | Hydro Capacity as per Programme of 12th Plan
i) | Commissioned during 12th Plan
Commissioned during 2012-13
Central Sector
1 | Chamera-III (NHPC) | H.P. | 3x77 | 231 | 01.09.05
2 | Chutak (NHPC) | J&K | 4x11 | 44 | 24.08.06
3a | Teesta Low Dam-III (NHPC) | W.B. | 4x33 | 99 | 30.10.03
| Sub- total (Central Sector) : |  |  | 374
State Sector
4a | Bhawani Barrage III | T.N. | 2x15 | 15 | 27.03.02
5 | Myntdu | Meghalaya | 2x42+ 1x42 | 42 | 09.06.03
| Sub- total (State Sector) : |  |  | 57
Private Sector
6 | Budhil | H.P. | 2x35 | 70 | 02.06.05
| Sub- total (Private Sector) : |  |  | 70
| Total Commissioned 2012-13 |  |  | 501
Commissioned during 2013-14
Central Sector
3b | Teesta Low Dam-III (NHPC) | W.B. | 4x33 | 33 | 30.10.03
7 | Uri-II (NHPC) | J&K | 4x60 | 240 | 01.09.05
8 | Nimoo Bazgo (NHPC) | J&K | 3x15 | 45 | 24.08.06
9a | Parabati-III (NHPC) | H.P. | 4x130 | 390 | 09.11.05
10a | Rampur (SJVNL) | H.P. | 6x68.67 | 206 | 25.01.07
| Sub- total (Central Sector) : |  |  | 914
State Sector
11 | Bhawani Barrage II | T.N. | 2x15 | 30 | 11.06.99
4b | Bhawani Barrage III | T.N. | 2x15 | 15 | 27.03.02
| Sub- total (State Sector) : |  |  | 45
Private Sector
12 | Chujachen | Sikkim | 2x49.5 | 99 | 30.11.04
| Sub- total (Private Sector) : |  |  | 99
| Total Commissioned 2013-14 |  |  | 1058
Commissioned during 2014-15
Central Sector
9b | Parabati-III (NHPC) | H.P. | 4x130 | 130 | 09.11.05
10b | Rampur (SJVNL) | H.P. | 6x68.67 | 206 | 25.01.07
13a | Kol Dam (NTPC) | H.P. | 4x200 | 400 | 28.10.02
| Sub- total (Central Sector) : |  |  | 736
| Total Commissioned 2014-15 |  |  | 736
Commissioned during 2015-16
Central Sector
13b | Kol Dam (NTPC) | H.P. | 4x200 | 400 | 28.10.02
| Sub- total (Central Sector) : |  |  | 400
State Sector
14a | Baglihar- II | J&K | 3x150 | 300 | 19.03.12
15a | Lower Jurala | Telangana | 6x40 | 40 | July, 2007
| Sub- total (State Sector) : |  |  | 340
Private Sector
16 | Shrinagar | Uttarakhand | 4x82.5 | 330 | 14.06.2000
17 | Jerethang Loop | Sikkim | 2x48 | 96 | 26.08.06
| Sub- total (Private Sector) : |  |  | 426
| Total Commissioned 2015-16 (up to Sep-2015) |  |  | 1166
| Total (i) 12th Plan-Commissioned (up to Sep-2015) |  |  | 3461
ii) | Under Execution
Central Sector
1 | Kishanganga (NHPC) | J&K | 3x110 | 330 | 20.07.07 | 2016-17
2 | Parbati St. II (NHPC) | H.P. | 4x200 | 800 | 11.09.02 | 2018-19
3 | Tapovan Vishnugad (NTPC) | Uttarakhand | 4x130 | 520 | 11/2006 | 2018-19
4 | Teesta Low Dam-IV (NHPC) | W.B. | 4x40 | 160 | 30.09.05 | 2015-17
5a | Subansiri Lower (NHPC) | Ar. Pr. | 8x250 | 1000 | 09.09.03 | 2019-21
6 | Kameng (NEEPCO) | Ar. Pr. | 4x150 | 600 | 02.12.04 | 2016-17
7 | Pare (NEEPCO) | Ar. Pr. | 2x55 | 110 | 04.12.08 | 2016-17
8 | Tuirial (NEEPCO) | Mizoram | 2x30 | 60 | 14.01.11 | 2016-17
| Sub- total (Central Sector) : |  |  | 3580
- 16 -
State Sector
9 | Baglihar- II | J&K | 3x150 | 150 | 19.03.12 | 2015-16
10 | Uhl-III | H.P. | 3x33.33 | 100 | 19.09.02 | 2017-18
11 | Kashang -I | H.P. | 1x65 | 65 | Nov, 01 | 2015-16
12 | Kashang -II & III | H.P. | 2x65 | 130 | - | 2018-19
13 | Sainj | H.P. | 100 | 100 | 29.12.10 | 2016-17
14 | Swara Kuddu | H.P. | 3x37 | 111 | 10.11.04 | 2018-19
15 | Nagarujana Sagar TR | A.P. | 2x25 | 50 | 17.01.05 | 2015-16
16 | Lower Jurala | Telangana | 6x40 | 200 | July, 2007 | 2015-17
17 | Pulichintala | Telangana | 4x30 | 120 | 25.04.07 | 2016-17
18 | Pallivasal | Kerala | 2x30 | 60 | Jan., 07 | 2018-19
19 | Thottiyar | Kerala | 1x30+1x10 | 40 | 05.06.08 | 2018-19
20 | New Umtru | Meghalaya | 2x20 | 40 | Dec., 07 | 2016-17
| Sub- total (State Sector) : |  |  | 1166
Private Sector
21 | Sorang | H.P. | 2x50 | 100 | 09.06.06 | 2015-16
22 | Tidong-I | H.P. | 2x50 | 100 | 28.07.06 | 2017-18
23 | Tangu Romai- I | H.P. | 2x22 | 44 | 30.11.07 | 2018-19
24 | Phata Byung | Uttarakhand | 2x38 | 76 | 06.10.08 | 2017-18
25 | Singoli Bhatwari | Uttarakhand | 3x33 | 99 | 11.07.08 | 2019-20
26 | Maheshwar | M.P. | 10x40 | 400 | 30.12.96 | 2017-18
27 | Teesta St. III | Sikkim | 6x200 | 1200 | 12.05.06 | 2016-17
28 | Teesta St. VI | Sikkim | 4x125 | 500 | 27.12.06 | 2021-22
29 | Rangit-IV | Sikkim | 3x40 | 120 | 06.07.07 | 2018-19
30 | Bhasmey | Sikkim | 3x17 | 51 | Dec-08 | 2019-20
| Sub- total (Private Sector) : |  |  | 2690
| Total ii: 12th Plan-Under execution |  |  | 7436
| Total'A': 12th Plan (Comm. + Under Execution) |  |  | 10897
SUMMARY- 12th Plan
|  | Central | State | Private | Total
| Commissioned | 2424 | 442 | 595 | 3461
| Under Construction | 3580 | 1166 | 2690 | 7436
| Total: (12th Plan) | 6004 | 1608 | 3285 | 10897
B. | Hydro Capacity for benefits beyond 12th Plan- Under Execution
Central Sector
31 | Tehri PSS (THDC) | Uttarakhand | 4x250 | 1000 | 18.07.06 | 2018-19
32 | Lata Tapovan (NTPC) | Uttarakhand | 3x57 | 171 | 17.07.12 | 2021-22
33 | Vishnugad Pipalkoti (THDC) | Uttarakhand | 4x111 | 444 | 21.08.08 | 2019-20
5b | Subansiri Lower (NHPC) | Ar. Pr. | 8x250 | 1000 | 09.09.03 | 2019-21
34 | Ramam-III (NTPC) | West Bengal | 3x40 | 120 | 10.09.14 | 2019-20
35 | Polavaram (PPA) | Andhra Pradesh | 12x80 | 960 |  | 13th Plan
| Sub- total (Central Sector) : |  |  | 3695
State Sector
36 | Shahpurkandi | Punjab | 3x33+3x33+1x8 | 206 | 04.05.11 | 2018-19
37 | Shongtom Karcham | H.P. | 3x150 | 450 | 16.08.12 | 2018-19
38 | Koyna Left Bank | Maharashtra | 2x40 | 80 | 20.02.04 | 2018-19
39 | Vyasi | Uttarakhand | 2x60 | 120 | 25.10.2011 | 2018-19
| Sub- total (State Sector) : |  |  | 856
Private Sector
40 | Ratle | J&K | 4x205+1x30 | 850 | 19.12.12 | 2021-22
41 | Bajoli Holi | H.P. | 3x60 | 180 | 30.12.11 | 2019-20
42 | Chanju-I | H.P. | 3x12 | 36 | 24.04.10 | 2017-18
43 | Tashiding | Sikkim | 2x48.5 | 97 | 06.04.09 | 2017-18
44 | Dikchu | Sikkim | 3x32 | 96 | 21.10.11 | 2019-20
45 | Rangit-II | Sikkim | 2x33 | 66 | 10.02.10 | 2019-20
46 | Rongnichu | Sikkim | 2x48 | 96 | 01.10.08 | 2019-20
47 | Panan | Sikkim | 4x75 | 300 | 07.03.11 | 2020-21
48 | Gongri | Ar. Pradesh | 2x72 | 144 | 04.02.13 | 2020-21
| Sub- total (Private Sector) : |  |  | 1865
| Total 'B': Beyond 12th Plan-Under execution |  |  | 6416
| Total: Under Execution |  |  | 13852
- 17 -

## Ch7
CHAPTER 7
Financial Status of H.E. Projects 12th Plan and Beyond | [13 empty] | Rs. Lakhs
Sl. | Name of project | Capacity | Benefits | Sancd. | Latest/ | Total | Total | Total | Total | Total | Total | Total | Total | Expend. | cumm exp upto for curr year 09-15
No. | (State) | (MW) | (MW) | Cost | Ant. | Expend. | Expend. | Expend. | Expend. | Expend. | Expend. | Expend. | Expend. | During
|  |  |  | (PL) | Cost | upto | upto | upto | upto | upto | upto | upto | upto | 2015-16
[5 empty] | (PL) | Mar,08 | Mar,09 | Mar,10 | Mar,11 | Mar,12 | Mar,13 | Mar,14 | Mar,15 | (Upto)
i) Commissioned during 11th Plan
Central Sector
1 | Sewa -II (NHPC) | 3x40 | 120 | 66546 | 106312 | 63126 | 79014 | 94696 | 99947 | 106488 | 106823
| J&K |  |  | (9/02) |  | Mar,13: (Jun-12)
2 | Koteshwar (THDC) | 4x100 | 400 | 130156 | 2386.41 | 75836 | 121944 | 177149 | 230802 | 262071 | 271684 | 273502 | 667
| (Uttarakhand) |  |  | (10/99) | (03/12) | Mar,15: (Dec-14)
3 | Omkareshwar (NHDC) | 8x65 | 520 | 222473 | - | Mar,08: 219052; Mar,09: 222879
| M.P. |  |  | (11/2002) |  | Mar,09: (11/2008)
4 | Teesta V (NHPC) | 3x170 | 510 | 219804 | 252622 | Mar,08: 245989
| (Sikkim) |  |  | (04/99) | (04/08)
Sub-total:Central Sector |  |  | 1550
State Sector
5 | Baglihar-I (J&K) | 3x150 | 450 | 349500 | 520000 | Mar,08: 402215; Mar,09: 457172; Mar,10: 474786; Mar,15: -
|  |  |  | (1997) | (2008) | Mar,10: (May-09)
6 | Maneri Bhali-II | 4x76 | 304 | 111139 | 171441 | Mar,08: 184611; Mar,15: NA
| (Uttarakhand) |  |  | (02/99) | (2005)
7 | Ghatghar PSS | 2x125 | 250 | 62078 | 156401 | Mar,08: 139308; Mar,15: -
| Maharashtra |  |  |  | (Under Rev.)
8 | Varahi Extn. | 2x115 | 230 | 28055 | 29100 | Mar,08: 12301; Mar,09: 28300
| Ktk. |  |  | (2002) | (2004)
9 | Priyadarshni Jurala, | 6x39 | 234 | 54700 | 70000 | 35755 | 47498 | 62500 | 65701 | 68913 | 68950
| A.P. |  |  | (2002) |  | Mar,13: (Sep-12)
10 | Kuttiyadi Addl. Extn. | 2x50 | 100 | 22050 * | 16828** | Mar,08: 10573; Mar,09: 13389; Mar,10: 14158
| Kerala |  |  | (1998) | (2003) | Mar,10: (Sep-09)
11 | Balimela Extn. | 2x75 | 150 | 20009 | 21240 | Mar,08: 19413; Mar,09: 20577; Mar,10: 20640; Mar,15: -
| Orissa |  |  | (10/98) | (04/2000) | Mar,10: (May-09)
12 | Purulia PSS | 4x225 | 900 | 145656 | 295260 | Mar,08: 210073
| W.B. |  |  | (09/91) | (1994)
13 | Myntdu, Meghalaya | 2x42 | 84 | 36308 | 117313 | 42374 | 65937 | 82827 | 96485 | 96879
|  |  |  | (1999) | (2010) | Mar,12: (Jul-11)
Sub-total: State Sector |  |  | 2702
Private Sector
14 | Allain Duhangan | 2x96 | 192 | 92235 | - | Mar,08: 87100; Mar,09: 129600; Mar,10: 150600; Mar,15: -
| H.P. |  |  |  |  | Mar,10: (Jun-09)
15 | Karcham Wangtoo | 4x250 | 1000 | 590959 | - | Mar,08: 129971; Mar,09: 265813; Mar,10: 421767; Mar,11: 618785
H.P.
16 | Malana-II | 2x50 | 100 | 59800 | 63347 | Mar,08: 28001; Mar,09: 51100; Mar,10: 63939; Mar,11: 78646
H.P.
Sub-total: Private Sector |  |  | 1292
Total (Commnd- 11th Plan): |  |  | 5544
ii) Commissioned during12th Plan
Central Sector
1 | Uri-II (NHPC) | 4x60 | 240 | 172479 | 230565 | 33125 | 72257 | 108233 | 139923 | 169359 | 192807 | 209681
| J&K |  |  | (02/2005) |  | Mar,14: (Dec-13)
2 | Chamera-III (NHPC) | 3x77 | 231 | 140563 | 208401 | 40870 | 74655 | 114462 | 155270 | 179593 | 184224
| H.P. |  |  | (02/2005) |  | Mar,13: (Jun-12)
3 | Chutak | 4x11 | 44 | 62126 | 91325 | 13991 | 23837 | 41398 | 62195 | 73193 | 77532
| J&K |  |  | (12/05) |  | Mar,13: (Jan-13)
4 | Teesta Low Dam - III | 4x33 | 132 | 76892 | 162800 | 63717 | 87929 | 109542 | 125807 | 146753 | 168698 | 170639
| (NHPC) W.B. |  |  | (12/02) |  | Mar,14: (Apr-13)
5 | Nimoo Bazgo | 3x15 | 45 | 61101 | 93610 | 14319 | 26448 | 44469 | 62209 | 72494 | 84091 | 88385
| J&K |  |  | (12/05) | (03/2011) | Mar,14: (Oct-13)
6 | Parbati -III(NHPC) | 4x130 | 520 | 230456 | 271600 | 40710 | 69805 | 98878 | 140631 | 176029 | 207796 | 234946
| H.P. |  |  | (05/2005)
7 | Ram Pur (SJVNL) | 6x68.67 | 412 | 204703 | 328828 | 25277 | 53496 | 78730 | 112752 | 165973 | 238013 | 312329 | 333791
| H.P. |  |  |  |  | Mar,15: (Dec-14)
8 | Kol Dam (NTPC) | 4x200 | 800 | 452715 | 722000 | 215927 | 269162 | 317400 | 364000 | 427000 | 493700 | 587800 | 654400
| H.P. |  |  | (12/2001)
Sub-total:Central Sector |  |  | 2424
State Sector
9 | Bhawani Kattlai Barrage - II | 2x15 | 30 | 9915 | 49746 | 6272 | 11169 | 25393 | 45370 | 46583 | 47706 | 49340
| T.N. |  |  | (1995) |  | Mar,14: (Sep-13)
10 | Bhawani Kattlai Barrage - III | 2x15 | 30 | 9975 | 49320 | 5705 | 9660 | 15186 | 35379 | 36852 | 37987 | 41364
| T.N. |  |  | (1999) |  | Mar,14: (Sep-13)
11 | Myntdu, | 2x42+1x42 | 42 | 36308 | 117313 | 42374 | 65937 | 82827 | 96485 | 96800
| Meghalaya |  |  | (1999) | (2010) | Mar,12: (Jun-11)
Sub-total:State Sector |  |  | 102
Private Sector
12 | Budhil | 2x35 | 70 | 41880 | - | Mar,08: 16062; Mar,09: 24510; Mar,10: 30839; Mar,11: 36400
| H.P. |  |  |  |  | Mar,11: (04/2010)
13 | Chujachen | 2x49.5 | 99 | 44876 | 104450 | 25431 | 42534 | 65310 | 80080 | 96620 | 119126
| Sikkim |  |  |  |  | Mar,13: (02/2013)
14 | Shrinagar | 4x82.5 | 330 | 169912 | 206900 | 27100 | 75927 | 149060 | 227398 | 332801 |  |  | 508800
| Uttarakhand |  |  | (08/07) |  | Mar,08: (12/07); Mar,15: (Jan-15)
Sub-total: Private Sector |  |  | 499
Total: Commnd. 12th Plan (upto June-15) |  |  | 3025
iii) Under Execution for benefits during 12th Plan and beyond
Central Sector
1 | Kishanganga (NHPC) | 3x110 | 330 | 364204 | 549772 | 4922 | 17577 | 28932 | 69214 | 140313 | 218417 | 327946 | 391295 | 24566 | 415861
| J&K |  |  | (09/07) | (09/07) | [8 empty] | (Sep-15) | (09/15)
2 | Parbati -II(NHPC) | 4x200 | 800 | 391959 | 536570 | 201325 | 234394 | 270070 | 308303 | 336307 | 385420 | 438357 | 495004 | 27346 | 522350
| H.P. |  |  | (12/2001) | (08/2011) | [8 empty] | (Sep-15) | (09/15)
3 | Tehri PSS (THDC), | 4x250 | 1000 | 297886 | 297886 | 21016 | 23744 | 24435 | 25215 | 32076 | 46642 | 69234 | 118902 | 24059 | 142961
| Uttarakhand |  |  | (12/05) | (04/10) | [8 empty] | (Sep-15) | (09/15)
4 | Tapovan Vishnugad (NTPC) | 4x130 | 520 | 297848 | 384630 | 24053 | 55400 | 84600 | 107800 | 145700 | 181300 | 207800 | 241700 | 11700 | 253400
| Uttarakhand |  |  | (03/2004) | (03/2004) | [8 empty] | (Aug-15) | (08/15)
5 | Lata Tapovan(NTPC) | 3x57 | 171 | 152700 | 152700 | - | - | - | - | 3600 | 9700 | 13800 | 13900 | 200 | 14100
| Uttarakhand |  |  | (07/2012) | (07/2012) | [8 empty] | (Aug-15)
6 | Vishnugad Pipalkoti (THDC) | 4x111 | 444 | 249158 | 374508 | 3001 | 5893 | 10250 | 14650 | 29892 | 34298 | 47931 | 59239 | 14066 | 73311
| Uttarakhand |  |  | (3/08) | (10/11) | [8 empty] | (Sep-15)
7 | Teesta Low Dam-IV(NHPC) | 4x40 | 160 | 106138 | 150200 | 23115 | 46109 | 69559 | 92744 | 110500 | 131417 | 148050 | 172470 | 14403 | 186873
| W.B. |  |  | (3/05) | [9 empty] | (Sep-15) | (09/15)
8 | Subansiri Lower (NHPC) | 8x250 | 2000 | 628533 | 1530000 | 197522 | 298696 | 395827 | 485106 | 560594 | 620348 | 678258 | 757863 | 22178 | 780041
| Ar. Pradesh/Assam |  |  | (12/2002) | [9 empty] | (Sep-15) | (09/15)
9 | Kameng (NEEPCO) | 4x150 | 600 | 249690 | 465395 | 70239 | 87006 | 110586 | 141013 | 180028 | 221594 | 284668 | 376255 | 42062 | 418317
| Ar. Pradesh |  |  | (03/04) | (12/2011) | [8 empty] | (Sep-15)
10 | Pare (NEEPCO) | 2x55 | 110 | 57399 | 112838 |  | 4560 | 9750 | 18247 | 31059 | 51754 | 81178 | 99440 | 12706 | 108638
| Ar. Pr. |  |  | (06/07) | (01/13) | [8 empty] | (Sep-15)
11 | Tuirial (NEEPCO) | 2x30 | 60 | 36872 | 91363 |  |  | 21409 | 22609 | 30115 | 40134 | 57322 | 80074 | 88896 | 87246
| Mizoram |  |  | (06/97) | (03/10) | [8 empty] | (Sep-15)
12 | Ramam-III (NTPC) | 3x40 | 120 | 138184 |  | Mar,15: 10800 | 1100 | 12000
| West Bengal | [12 empty] | (Aug-15)
13 | Polavaram (PPA) | 12x80 | 960 | 1601045 |  | Mar,15: 506738 | 736406
| Andhra Pradesh |  |  | (02/09) | [9 empty] | (Sep-15)
| Sub Total: Central Sector |  | 7275
State Sector
14 | Baglihar-II | 3x150 | 150 | 3113.19 | 3113.19 | Mar,12: 19172
J&K
15 | Shahpurkandi | 3x33+3x33+1x8 | 206 | 228581 | 228581 | Mar,13: 29934; Mar,14: 32773; Mar,15: 51350
| Punjab |  |  |  |  | Mar,14: (Aug-13); Mar,15: (Apr-15)
16 | Uhl-III | 3x33.33 | 100 | 43156 | 94084 | 25916 | 34812 | 49962 | 62465 | 75474 | 88149 | 100470 | 112830 | 931
| H.P. |  |  | (09/02) | (03/08) | [8 empty] | (Jun-15)
17 | Sawara Kuddu | 3x37 | 111 | 55853 | 118190 | 9292 | 12100 | 33125 | 43126 | 66018 | 81355 | 95909 | 102255 | 1468
| H.P. |  |  | (03/03) | [9 empty] | (Jul-15)
18 | Kashang -I | 1x65 | 65 | 47802 | 47802 | 14332 | 17523 | 17718 | 31546 | 45964 | 60874 | 73655 | 84344 | 3558
| H.P. |  |  | (03/08) | (03/08) | [8 empty] | (Jul-15)
19 | Kashang -II & III | 2x65 | 130 | 60178 | 60178
H.P.
20 | Sainj | 2x50 | 100 | 78456 | 78456 |  |  |  | 13990 | 27279 | 45048 | 65619 | 83946 | 4351
| H.P. | [12 empty] | (Jul-15)
21 | Shontong Karcham | 3x150 | 450 | 280783 | 331635 | Mar,13: 17889; Mar,14: 22904; Mar,15: 27093 | 3029
| H.P. | [12 empty] | (Jul-15)
22 | Koyna Left bank PSS | 2x40 | 80 | 37978 | 37978 | Mar,12: 8480; Mar,13: 11667; Mar,14: 12893; Mar,15: 13160
Maharashtra
23 | Nagarjuna Sagar T Pool | 2x25 | 50 | 46463 | 95867 | 7275 | 13220 | 23568 | 38808 | 46362 | 53462 | 58995 | 7257 | 3950
| A.P. |  |  | (2002) | [9 empty] | (Aug-15)
24 | Lower Jurala | 6x40 | 200 | 90834 | 196914 | 213 | 14565 | 31608 | 61672 | 88600 | 110952 | 133289 | 157282 | 8599
| Telangana |  |  | (05/07) | [9 empty] | (Aug-15)
25 | Pulichintala | 4x30 | 120 | 38000 | 56349 | 222 | 1585 | 9701 | 15882 | 17446 | 21791 | 24094 | 37426 | 1401
| Telangana |  |  | (2006-07) | [9 empty] | (Aug-15)
26 | Pallivasal | 2x30 | 60 | 22200 | 28469 | 3580 | 4592 | 5884 | 11697 | 14640.53 | 15854 | 17368 | 17877 | 75
| Kerala |  |  | (2004) | (2007) | [8 empty] | (May-15)
27 | Thottiyar | 1x30 + 1x10 | 40 | 13679 | 15002 | - | - | 91 | 118 | 291 | 1624 | 3205 | 4618 | 452
| Kerala |  |  | (2007) | [9 empty] | (Sep-15)
28 | New Umtru | 2x20 | 40 | 22640 | 46127 | - | 5928 |  |  | 11287 | 16723 | 19667 | 25591 | 28522
| Meghalaya+B87 |  |  |  |  | Mar,09: (08/2008) | (Sep-15)
29 | Vyasi | 2x60 | 120 | 93623 | 93623 | Mar,08: -; Mar,15: 8764 | 10741
| Uttarakhand |  |  | (2010-02) | [9 empty] | (Sep-15)
| Sub-total: State Sector |  | 2022
-40-
Private Sector
30 | Ratle | 4x205 + 1x30 | 850 | 551702 | 551702 | Mar,12: 12412; Mar,13: 37380
J&K
31 | Sorang | 2x50 | 100 | 58600 | 58600 | Mar,08: 9959; Mar,09: 17105; Mar,10: 21305
| H.P. |  |  | (2006) | (2006)
32 | Tidong-I | 2x50 | 100 | 54315 | 54315 | - | 2340 | 3460 | 11800 | 22600 | 25089 | 27989
| H.P. |  |  | (08/05) | (08/05) | Mar,14: (May-13)
33 | Tangu Romai- I | 2x22 | 44 | 25500 | 25500 | Mar,11: 3526; Mar,12: 4137; Mar,13: 17900
| H.P. |  |  | (2006) | (2006)
34 | Bajoli Holi | 3x60 | 180 | 169693 | 169693 | Mar,13: 11200; Mar,15: 38830
| H.P. |  |  |  |  | Mar,15: (Dec-14)
35 | Chanju-I | 3x12 | 36 | 29509 | 29509 |  |  |  | 805 | 4594 | 15239 | 19466 | 32328 | 6457
| H.P. | [12 empty] | (Sep-15)
36 | Phata Byung | 2x38 | 76 | 52000 | 52000 | - | - | 19112 | 27698 | 36498 | 48696 | 51824
| Uttarakhand |  |  | (2007) | (2007) | Mar,10: (03/2010); Mar,14: (Jun-13)
37 | Singoli Bhatwari | 3x33 | 99 | 66647 | 66647 | - | - | 14507 | 20362 | 35100 | 48578 | 63513 | 73742 | 6595
| Uttarakhand |  |  | (2008) | (2008) | [8 empty] | (Sep-15)
38 | Maheshwar | 10x40 | 400 | 156927 | 463500 | 125513 | 170557 | 238200 | 291185 | 291770 |  |  | 313500
| M.P. |  |  | (96-97)
39 | Teesta St. III | 6x200 | 1200 | 570555 | 1138200 | 94800 | 167300 | 308340 | 442504 | 547543 | 685478 | 821968 | 916170 | 78600
| Sikkim |  |  |  |  | Mar,13: (01/2013) | (Aug-15)
40 | Teesta St. VI | 4x125 | 500 | 328308 | 328308 | 53419 | 72467 | 76673 | 150396 | 208625 | 239950 |  | 270376 | 9178
| Sikkim |  |  |  |  | Mar,10: (09/2009) | (Jun-15)
41 | Rangit-IV | 3x40 | 120 | 72616 | 72616 | 561 | 9809 | 13829 | 24717 | 37636 | 41653 | 56320
| Sikkim |  |  |  |  | Mar,14: (Sep-13)
42 | Bhasmey | 3x17 | 51 | 40850 | 40850 | Mar,12: 16090; Mar,13: 16240
| Sikkim |  |  |  |  | Mar,13: (Apr-12)
43 | Tashiding | 2x48.5 | 97 | 46595 | 46595 | Mar,11: 2975
Sikkim
44 | Dikchu | 3x32 | 96 | 63957 | 63957 | 175 | 1123 | 2961 | 5243 | 9938
| Sikkim |  |  |  |  | Mar,12: (Nov-11)
45 | Rangit- II | 2x33 | 66 | 49800 | 49800
Sikkim
46 | Rongnichu | 2x48 | 96 | 49132 | 49132
Sikkim
47 | Panan | 4x75 | 300 | 183305 | 183305 | 1578 | 2808 | 5367 | 9167 | 10462 | 11731 | 12740 | 14450
| Sikkim |  |  |  |  | Mar,15: (Apr-15)
48 | Gongri | 2x72 | 144 | 143627 | 143627 | Mar,13: 29021; Mar,14: 42687; Mar,15: 46886 | 5400
Ar. Pradesh
Sub-total: Private Sector |  |  | 4555
| Total (iii): (Under Execution): |  | 13852
-41-

## Ch8
CHAPTER 8
Status of Environmental and Forest Clearance of H.E. Projects for
benefits in 12th Plan & beyond
Sl. | Name of | State | I.C. | Benefits | Date of | Date of | Date of | Date of
No. | Project |  | (No.xMW) | (MW) | Clearance | Env. | Forest | Approval
[6 empty] | Clearance | Clearance
A. | Commissioned during 12th Plan
Central Sector
1 | Uri-II (NHPC) | J&K | 4x60 | 240 | 11.02.04 | 13.08.04 | Not Reqd. | 01.09.05
2 | Chamera-III (NHPC) | H.P. | 3x77 | 231 | 10.10.03 | 10.03.05 | 08.06.04 | 01.09.05
3 | Chutak (NHPC) | J&K | 4x11 | 44 | 23.04.04 | 17.11.05 | Not Reqd. | 24.08.06
4 | Teesta Low Dam-III (NHPC) | W.B. | 4x33 | 132 | 25.06.02 | 16.07.03 | 07.04.04 | 30.10.03
5 | Nimoo Bazgo (NHPC) | J&K | 3x15 | 45 | 16.03.04 | 30.05.05 | Not Reqd. | 24.08.06
6 | Parabati-III (NHPC) | H.P. | 4x130 | 520 | 12.11.03 | 16.04.05 | 13.06.05 | 09.11.05
7 | Ram Pur (SJVNL) | H.P. | 6x68.67 | 412 | 16.12.05 | 31.03.06 | 07.04.06 | 25.01.07
8 | Kol Dam (NTPC) | H.P. | 4x200 | 800 | 30.06.02 | 10.05.2000 | 23.11.2000 | 28.10.02
State Sector
9 | Bhawani Kattlai Barrage-II | T.N. | 2x15 | 30 | - | 02.01.86 | 02.01.86 | 11.06.99
10 | Bhawani Kattlai Barrage- III | T.N. | 2x15 | 30 | - | 02.01.86 | 02.01.86 | 27.03.02
11 | Myntdu | Meghalaya | 2x42 | 42 | 20.09.99 | 26.09.01 | 19.06.01 | 09.06.03
12a | Baglihar-II | J&K | 3x150 | 300 | 29.12.10 | - | Not Reqd. | 29.12.10
13a | Lower Jurala | Telangana | 6x40 | 40 | 24.07.07 | 04.05.07 | Not Reqd. | 24.07.07
Private Sector
14 | Budhil | H.P. | 2x35 | 70 | - | 28.02.06 | 19.04.06 | 02.06.05
15 | Chujachen | Sikkim | 2x49.5 | 99 | - | 09.09.05 | 09.01.06 | 30.11.04
16 | Srinagar | Utt. | 4x82.5 | 330 | - | 27.07.99 | 17.04.06 | 20.07.05
17 | Jorethang Loop | Sikkim | 2x48 | 96 | - | 26.07.07 | 12.05.08 | 26.08.06
| Total : Commissioned 12th Plan (upto Sep-15) |  |  | 3461
B. | Under Execution
Central Sector
1 | Kishanganga (NHPC) | J&K | 3x110 | 330 | 31.08.05 | 09.03.06 | 27.05.08 | 14.01.09
2 | Parbati-II (NHPC) | H.P. | 2x400 | 800 | 03.01.01 | 04.06.01 | 11.08.99 | 11.09.02
3 | Tehri PSS | Utt. | 4x250 | 1000 | 10.10.88 | 19.07.90 | 04.06.87 | 18.07.06
4 | Tapovan Vishnugad (NTPC) | Utt. | 4x130 | 520 | 11.08.04 | 08.02.05 | 22.04.06 | 11/2006
5 | Lata Tapovan (NTPC) | Utt. | 3x57 | 171 | 08.02.06 | 21.02.07 | 30.04.07 | 2012-08-01
6 | Vishnugad ipalkoti (THDC) | Utt. | 4x111 | 444 | 09/2006 | 22.08.07 | 28.05.13 | 21.08.08
7 | Teesta Low Dam-IV (NHPC) | W.B. | 4x40 | 160 | 23.12.03 | 31.03.05 | 12.01.05 | 30.09.05
8 | Subansiri Lower (NHPC) | Ar. Pr./ Ass | 8x250 | 2000 | 13.01.03 | 16.07.03 | 12.10.04 | 09.09.03
9 | Kameng (NEEPCO) | Ar. Pr. | 4x150 | 600 | 30.04.91 | 29.03.01 | 03.08.2000 | 02.12.04
10 | Pare (NEEPCO) | Ar. Pr. | 2x55 | 110 | 24.09.07 | 13.09.06 | 14.03.08 | 04.12.08
11 | Tuirial (NEEPCO) | Mizoram | 2x30 | 60
12 | Ramam-III (NTPC) | West Bengal | 3x40 | 120 | 12.09.06 | 17.08.07 | 18.10.08 | 10.09.14
13 | Polavaram (PPA) | Andhra Pr. | 12x80 | 960 | 21.07.2010 | 28.07.10 | 21.07.10
| Sub-total (Central Sector): |  |  | 7275
State Sector
14 | Baglihar-II | J&K | 3x150 | 150 | 29.12.10 | - | Not Reqd. | 29.12.10
15 | Shahpurkandi | Punjab | 3x33+3x33+1x8 | 206 | 08/2009 | 18.11.81 | Not Reqd. | 04.05.11
16 | Uhl-III | H.P. | 3x33.33 | 100 | 19.09.02 | 15.11.02 | 20.12.02 | 26.09.03
17 | Sawara Kuddu | H.P. | 3x37 | 111 | June, 07 | May, 07 | June, 06 | June, 07
18 | Kashang-I | H.P. | 2x32.5 | 65 | - | 15.11.02 | 23.06.04 | 31.07.08
19 | Kashang -II & III | H.P. | 2x65 | 130 | - | 16.04.10 | 14.01.13 | 2009
20 | Sainj | H.P. |  | 100 | - | 04.05.09 | 26.10.09 | 29.12.10
21 | Shongtong Karcham | H.P. | 3x150 | 450 | 16.8.12 | 19.05.11 | 22.03.11 | -
22 | Koyna Left Bank PSS | Mah. | 2x40 | 80 | - | 16.05.07 | Not Reqd. | 20.02.04
23 | Nagarjuna Sagar T Pool | A.P. | 2x25 | 50 | 30.11.07 | 14.06.01 | 11.04.01 | 17.01.05
24 | Pulichintala | Telangana | 4x30 | 120 | - | 09.06.2005 | 20.10.2006 | 25.04.07
25 | Lower Jurala | Telangana | 6x40 | 200 | 24.07.07 | 04.05.07 | Not Reqd. | 24.07.07
26 | Pallivasal Extn. | Kerala | 2x30 | 60 | 31.01.07 | Not Reqd. | 11.07.07 | 31.01.07
27 | Thottiyar | Kerala | 1x30 + 1x10 | 40 | 05.06.08 | Not Reqd. | 11.07.07 | 05.06.08
28 | New Umtru | Meghalaya | 2x20 | 40 | - | 13.03.06 | 27.09.05 | 2006-12-01
29 | Vyasi | Uttarakhand | 2x60 | 120 | - | 22.04.10 | 14.10.13 | 25.10.2011
| Sub-total (State Sector): |  |  | 2022
Private Sector
30 | Ratle | J&K | 4x205=1x30 | 850 | - | 12.12.12 | 27.04.12 | 19.12.12
31 | Sorang | H.P. | 2x50 | 100 | - | 07.09.06 | Nov, 06 | June, 06
32 | Tidong-I | H.P. | 100 | 100 | - | 18.06.08 | 18.06.08 | 23.07.07
33 | Tangu Romai- I | H.P. | 2x22 | 44 | - | 01.05.09 | 19.01.10 | 30.11.07
34 | Bajoli Holi | H.P. | 3x60 | 180 | - | 24.01.11 | 08.07.11 | 30.12.11
35 | Chanju | H.P. | 3x12 | 36 | - | 20.04.11 | 17.02.11 | 24.04.10
36 | Phata Byung | Uttarakhand | 2x38 | 76 | - | 01.05.09 | - | 30.11.07
37 | Singoli Bhatwari | Uttarakhand | 3x33 | 99 | - | 24.08.07 | 16.01.09 | 11.07.08
38 | Maheshwar | M.P. | 10x40 | 400 | - | 07.01.94 | Not Reqd. | 29.09.06
39 | Teesta St. III | Sikkim | 6x200 | 1200 | - | 04.08.06 | 02.11.07 | 12.05.06
40 | Teesta St. VI | Sikkim | 4x125 | 500 | - | 21.09.06 | 25.04.08 | 27.12.06
41 | Rangit-IV | Sikkim | 3x40 | 120 | - | 16.05.07 | 26.12.07 | 06.07.07
42 | Bhasmey | Sikkim | 3x17 | 51 | - | 15.05.07 | 13.09.10 | -
43 | Tashiding | Sikkim | 2x48.5 | 97 | - | 29.07.10 | 06.04.10 | 06.04.09
44 | Dikchu | Sikkim | 3x32 | 96 | - | 01.04.08 | 22.01.10 | 21.10.11
45 | Rangit- II | Sikkim | 2x33 | 66 | - | 16.04.10 | 22.10.10 | 10.2.10
46 | Rongnichu | Sikkim | 2x48 | 96 | - | 04.04.07 | 18.05.09 | 01.10.08
47 | Panan | Sikkim | 4x75 | 300 | - | 02.01.07 | 21.09.10 | 07.03.11
48 | Gongri | Ar. Pradesh | 2x72 | 144 | - | 07.09.12 | 19.03.13 | 04.02.13
| Sub-total (Private Sector): |  |  | 4555
| Total : Under Execution |  |  | 13852
-42-

## Ch9
Chapter 9
Status of Civil Package Award (First Package) of H.E. Projects
for 12th Plan & beyond
Sl. | Name of Project | State | Capacity | Benefits | Date of CCEA/ | Date of letter
No. |  |  | (MW) |  | Investment | of award
|  |  |  | (MW) | Decision | (First Package)
A. | Commissioned during 12th Plan
Central Sector
1 | Uri-II (NHPC) | J&K | 4x60 | 240 | 01.09.05 | 21.09.05
2 | Chamera-III (NHPC) | H.P. | 3x77 | 231 | 01.09.05 | 21.09.05
3 | Chutak (NHPC) | J&K | 4x11 | 44 | 24.08.06 | 23.09.06
4 | Teesta Low Dam-III(NHPC) | W.B. | 4x33 | 132 | 30.10.03 | 28.10.03
5 | Nimoo Bazgo (NHPC) | J&K | 3x15 | 45 | 24.08.06 | 23.09.06
6 | Parbati-III (NHPC) | H.P. | 4x130 | 520 | 09.11.05 | 15.12.05
7 | Ram Pur (SJVNL) | H.P. | 412 | 412 | 25.01.07 | 01.02.07
8 | Kol Dam (NTPC) | H.P. | 4x200 | 800 | 28.10.02 | 12/2003
State Sector
9 | Bhawani Kattlai Barrage-II | T.N. | 2x15 | 30 | 11.06.99 | 03.02.06
10 | Bhawani Kattlai Barrage-III | T.N. | 2x15 | 30 | 27.03.02 | 03.02.06
11 | Myntdu | Meghalaya | 2x42 | 42 | 09.06.03 | 03/04
12 | Baglihar-II | J&K | 3x150 | 300 | 29.12.10 | 31.03.12
13 | Lower Jurala | Telangana | 6x40 | 40 | 07/07 | 10.02.08
Private Sector
14 | Budhil | H.P. | 2x35 | 70 | 02.06.05 | 26.12.05
15 | Chujachen | Sikkim | 2x49.5 | 99 | 30.11.04 | 12.08.06
16 | Srinagar | Uttaranchal | 4x82.5 | 330 | 20.07.05 | 06/2007
17 | Jorethang Loop | Sikkim | 2x48 | 96 | 26.08.06 | 09.03.09
| Total : Commissioned (upto Sep-15) |  |  | 3461
B. | Under Execution
Central Sector
1 | Kishanganga (NHPC) | J&K | 3x110 | 330 | 20.07.07 | 22.01.09
2 | Parbati-II (NHPC) | H.P. | 4x200 | 800 | 11.09.02 | 09/02
3 | Tehri PSP | Uttarakhand | 4x250 | 1000 | 18.07.06 | 23.06.11
4 | Tapovan Vishnugad (NTPC) | Uttarakhand | 4x130 | 520 | 11/06 | 11/06
5 | Lata Tapovan (NTPC) | Uttarakhand | 3x57 | 171 | 08/2012 | 17.08.12
6 | Vishnugad Pipalkoti (THDC) | Uttarakhand | 4x111 | 444 | 21.08.08 | 17.01.14
7 | Teesta Low Dam-IV(NHPC) | W.B. | 4x40 | 160 | 30.09.05 | 10.05.06
8 | Subansiri Lower (NHPC) | Ar.Pr./ Assam | 8x250 | 2000 | 09.09.03 | 19.12.03
9 | Kameng (NEEPCO) | Ar. Pr. | 4x150 | 600 | 02.12.04 | 08.12.04
10 | Pare (NEEPCO) | Ar. Pr. | 2x55 | 110 | 04.12.08 | 31.08.09
11 | Tuirial (NEEPCO) | Mizoram | 2x30 | 60 | 07.07.98 14.01.11(RCE) | 30.08.02
12 | Ramam-III | West Bengal | 3x40 | 120 |  | 10.09.14
13 | Polavaram (PPA) | Andhra Pr. | 12x80 | 960
| Sub-total (Central Sector): |  |  | 7275
State Sector
14 | Baglihar-II | J&K | 3x150 | 150 | 29.12.10 | 31.03.12
15 | Uhl-III | H.P. | 3x33.33 | 100 | 19.09.02 | 02.04.03
16 | Sawara Kuddu | H.P. | 3x37 | 111 | 06/07 | 17.07.07
17 | Kashang-I | H.P. | 2x32.5 | 65 | 11/01 | 09.04.09
18 | Kashang -II & III | H.P. | 2x65 | 130 | 11/2001 | 11.11.10
19 | Sainj | H.P. | 2x50 | 100 | 29.12.10 | 02.08.10
20 | Shongton Karcham | H.P. | 3x150 | 450 | 16.08.12 | 04.08.12
21 | Shahpurkandi | Punjab | 3x33+3x33+1x8 | 206 | 04.05.11 | 11.02.13
22 | Koyna Left Bank PSS | Mah. | 2x40 | 80 | 20.02.04 | 20.06.07
23 | Nagarjuna Sagar T Pool | A.P. | 2x25 | 50 | 17.01.05 | 19.05.05
24 | Pulichintala | Telangana | 4x30 | 120 | 25.04.07 | 01.08.07
25 | Lower Jurala | Telangana | 6x40 | 200 | 07/07 | 10.02.08
26 | Pallivasal | Kerala | 2x30 | 60 | 31.01.07 | 31.01.07
27 | Thottiyar | Kerala | 1x30 + 1x10 | 40 | 05.06.08 | 22.12.08
28 | New Umtru | Meghalaya | 2x20 | 40 | Dec-07 | 20.12.07
29 | Vyasi | Uttarakhand | 2x60 | 120
| Sub-total (State Sector): |  |  | 2022
Private Sector
30 | Ratle | J&K | 4x205+1x30 | 850 | 19.12.12 | 04.07.13
31 | Sorang | H.P. | 2x50 | 100 | 06/06 | 06/2007
32 | Tidong-I | H.P. | 100 | 100 | 23.07.07 | 07.11.08
33 | Bajoli Holi | H.P. | 3x60 | 180 | 30.12.11 | 29.05.13
34 | Tangu Romai- I | H.P. | 2x22 | 44 | 2014-15 | 14.06.10
35 | Chanju-I | H.P. | 3x12 | 36 | 2017-18 | 23.07.11
36 | Phata Byung | Uttarakhand | 2x38 | 76 | 06.10.08 | 12.04.08
37 | Singoli Bhatwari | Uttarakhand | 3x33 | 99 | 11.07.08 | 20.06.08
38 | Maheshwar | M.P. | 10x40 | 400 | 30.12.96 | 22.02.97
39 | Teesta St. III | Sikkim | 6x200 | 1200 | 12.05.06 | 18.04.07
40 | Teesta St. VI | Sikkim | 4x125 | 500 | 27.12.06 | 03/2007
41 | Rangit-IV | Sikkim | 3x40 | 120 | 06.07.07 | 22.11.07
42 | Bhasmey | Sikkim | 3x17 | 51 | Dec-08 | 12.04.10
43 | Tashiding | Sikkim | 2x48.5 | 97 | 06.04.09 | 28.03.11
44 | Dikchu | Sikkim | 3x32 | 96 | 21.10.11 | 22.03.11
45 | Rangit-II | Sikkim | 2x33 | 66 | 10.02.10 | 24.10.11
46 | Rongnichu | Sikkim | 2x48 | 96 | 01.10.08 | 07.04.10
47 | Panan | Sikkim | 4x75 | 300 | 07.03.11 | 22.02.14
48 | Gongri | Ar. Pradesh | 2x72 | 144 | 04.02.13 | 22.12.11
| Sub-total (Private Sector): |  |  | 4555
| Total -Under Execution: |  |  | 13852
Additional
1 | Demwe Lower | Ar. Pradesh | 5x342+1x40 | 1750 | 20.11.09 | 12/2010
(Works on the project yet to start for want of Financial Closure.
- 43-

## Ch9.1
CHAPTER 9.1
Ordering Status of TG sets for H. E. Projects for 12th Plan & Beyond
Summary- 12th Plan
Sector | BHEL | China | Others | Total
Central Sector
Commissioned | 1821 | 0 | 603 | 2424
Under Execution | 2470 | 0 | 1110 | 3580
Sub-total (Central) | 4291 | 0 | 1713 | 6004
State Sector
Commissioned | 0 | 0 | 442 | 442
Under Execution | 270 | 100 | 796 | 1166
Sub-total (State) | 270 | 100 | 1238 | 1608
Private Sector
Commissioned | 330 | 70 | 195 | 595
Under Execution | 400 | 0 | 2290 | 2690
Sub-total (Private) | 730 | 70 | 2485 | 3285
Total: Commissioned | 2151 | 70 | 1240 | 3461
Total: Under Execution | 3140 | 100 | 4196 | 7436
Total- 12th Plan | 5291 | 170 | 5436 | 10897
Summary- Under Execution- 12th Plan & Beyond
Sector | Benefits | Capacity Ordered |  |  | Not yet ordered
| (MW) | BHEL | Others | Total
Central Sector | 7275 | 3205 | 3110 | 6315 | 960
State Sector | 2022 | 596 | 1426 | 2022 | 0
Private Sector | 4555 | 400 | 3675 | 4075 | 480
Total: Under Execution | 13852 | 4201 | 8211 | 12412 | 1440
- 44 -

## Ch9.2
CHAPTER 9.2
Ordering Status of TG sets of H.E. Projects
for 12th Plan & beyond.
Sl. | Name of the | Capacity | Benefits | Make/Supplier | Date of
No. | Project/State | (No.x MW) | (MW) | of TG set | Order
A. | Commissioned during 12th Plan
Central Sector
BHEL Units
1 | Chutak (NHPC) J&K | 4x11 | 44 | BHEL | 16.08.07
2 | Nimoo Bazgo (NHPC) J&K | 3x15 | 45 | BHEL | 12.06.07
3 | Parabati-III (NHPC) HP | 4x130 | 520 | BHEL | 29.12.06
4 | Ram Pur (SJVNL), H.P. | 6x68.67 | 412 | BHEL | 16.09.08
5 | Kol Dam (NTPC), H.P. | 4x200 | 800 | BHEL, Toshiba & Marubeni | 07/2004
| Sub-total- BHEL |  | 1821
Other Units
6 | Uri-II (NHPC), J&K | 4x60 | 240 | Alstom, India & France | 29.12.06
7 | Chamera-III (NHPC) HP | 3x77 | 231 | M/s Alstom, India & France | 23.01.07
8 | Teesta Low Dam-III (NHPC), W.B. | 4x33 | 132 | VA Tech, India | 30.07.04
| Sub-total- Other units |  | 603
| Sub-total (Central Sector): |  | 2424
State Sector
Other Units
9 | Bhawani Barrage II ,T.N. | 2x15 | 30 | Litostroj Slovania Koncar, Croatia | 27.12.06
10 | Bhawani Barrage III, T.N. | 2x15 | 30 | Litostroj Slovania | 15.11.06
Koncar, Croatia
11 | Myntdu, (Meghalaya) | 2x42 | 42 | V.A. Tech, India | 30.11.05
12 | Baglihar-II, J&K | 3x150 | 300 | Voith-Andritz consortium, Germany & India | 31.03.12
13 | Lower Jurala, Telangana | 6x40 | 40 | Alstom, India | 09.06.08
| Sub-total- Other units |  | 442
| Sub-total (State Sector): |  | 442
Private Sector
BHEL Units
14 | Srinagar (Uttarakhand) | 4x82.5 | 330 | BHEL | 04/2007
| Sub-total- BHEL |  | 330
Chineese
15 | Budhil (H.P.) | 2x35 | 70 | Dongfang Elec.Corporation, China | 12.07.06
| Sub-total- Chineese |  | 70
Other Units
16 | Chujachen (Sikkim) | 2x49.5 | 99 | Alstom, India | 20.12.06
17 | Jorethang Loop, Sikkim | 2x48 | 96 | Alstom, India | 1.12.09
| Sub-total- Other units |  | 195
| Sub-total (Private Sector): |  | 595
Total : Commnd. 12th Plan (upto Sep-15) |  |  | 3461
B. | Under Execution for benefits during 12th Plan & beyond
Units ordered
Central Sector
BHEL Units
1 | Parbati-II (NHPC),(H.P. | 4x200 | 800 | BHEL | 24.12.02
2 | Kishanganga (NHPC), J&K | 3x110 | 330 | BHEL | 22.01.09
3 | Tapovan Vishnugad (NTPC), Utt. | 4x130 | 520 | BHEL | 01/2008
4 | Lata Tapovan, Uttarakhand | 3x57 | 171 | BHEL | 12/2012
5 | Teesta Low Dam-IV (NHPC), W.B. | 4x40 | 160 | BHEL | 10.05.07
6 | Kameng (NEEPCO), Ar. Pr. | 4x150 | 600 | BHEL | 03.12.04
7 | Tuirial (NEEPCO), Mizoram | 2x30 | 60 | BHEL | 25.10.03 & 01.08.11(Rev)
8 | Vishnugad Pipalkoti (THDC) | 4x111 | 444 | BHEL | 18.11.14
9 | Ramam-III (NTPC) | 3x40 | 120 | BHEL | 10.09.14
| Sub-total- BHEL |  | 3205
Other Units
10 | Tehri PSP (THDC) | 4x250 | 1000 | Alstom, France | 23.06.11
11 | Subansiri Lower (NHPC), Ar. Pradesh | 8x250 | 2000 | Alstom, France & India | 11.02.05
12 | Pare (NEEPCO), Ar. Pr. | 2x55 | 110 | Andritz Hydro, India | 01.10.10
| Sub-total- Others |  | 3110
| Sub-total (Central Sector): |  | 6315
- 45 -
State Sector
BHEL Units
13 | Uhl-III (H.P.) | 3x33.33 | 100 | BHEL | 15.02.07
14 | Nagarjuna Sagar Tail, AP | 2x25 | 50 | BHEL | 03.05.06
15 | Pulichintala, Telangana | 4x30 | 120 | BHEL | 25.05.07
16 | Shahpurkandi, Punjab | 3x33+3x33+1x8 | 206 | BHEL | 28.02.14
17 | Vyasi , Uttarakhand | 2x60 | 120 | BHEL
| Sub-total- BHEL |  | 596
Chineese
18 | Pallivasal, Kerala | 2x30 | 60 | Dongfang Elec.Corp., China | 31.01.07
19 | Thottiyar, Kerala | 1x30 + 1x10 | 40 | Chongqing, China | 22.12.08
| Sub-total- Chineese |  | 100
OTHER UNITS
20 | Baglihar-II, J&K | 3x150 | 150 | Voith-Andritz consortium, Germany & India | 31.03.12
21 | Kashang-I (H.P.) | 2x32.5 | 65 | Andritz Hydro, India | 01.12.10
22 | Kashang -II & III , H.P. | 2x65 | 130 | Andritz Hydro, India | 01.12.10
23 | Sawara Kuddu, H.P. | 3x37 | 111 | Andritz Hydro, India | 05.02.09
24 | Sainj, H.P. |  | 100 | Voith Hydro, India | 17.08.11
25 | Koyna Left Bank PSS, Maharashtra | 2x40 | 80 | Litostroj Slovania Koncar, Croatia | 16.12.10
26 | Lower Jurala, Telangana | 6x40 | 200 | Alstom, India | 09.06.08
27 | New Umtru, Meghalaya | 2x20 | 40 | V.A. Tech, India | 25.02.09
28 | Shontong Karcham, H.P. | 3x150 | 450 | Andritz Hydro, India | 04.03.15
| Sub-total- Others |  | 1326
| Sub-total (State Sector): |  | 2022
Private Sector
BHEL Units
29 | Maheshwar (M.P.) | 4x100 | 400 | BHEL | 25.06.07
| Sub-total- BHEL |  | 400
OTHER UNITS
30 | Ratle (J&K) | 4x205+1x30 | 850 | Alstom, India | 31.12.12
31 | Sorang (H.P.) | 2x50 | 100 | Voith Siemens, India | 06/2007
32 | Tidong-I, H.P. | 100 | 100 | Alstom, India | 28.02.11
33 | Tangu Romai- I, H.P. | 2x22 | 44 | Andritz Hydro, India | 17.04.13
34 | Chanju-I, H.P. | 3x12 | 36 | B Fouress, India | 21.09.11
35 | Phata Byung, (Uttarakhand) | 76 | 76 | Alstom, India | 12.04.08
36 | Singoli Bhatwari, Uttarakhand | 3x33 | 99 | Voith Hydro, India | 15.06.11
37 | Teesta St. III, (Sikkim) | 6x200 | 1200 | Andritz Hydro, India | 18.10.07
38 | Rangit-IV, Sikkim | 3x40 | 120 | Andritz Hydro, India | 28.08.09
39 | Bhasmey, Sikkim | 3x17 | 51 | Voith Hydro, India | 14.04.10
40 | Teesta St. VI, Sikkim | 4x125 | 500 | Alstom, India | 04/2009
41 | Tashiding, Sikkim | 2x48.5 | 97 | Alstom, India | 21.05.10
42 | Rongnichu, Sikkim | 2x48 | 96 | Voith Hydro, India | 28.09.11
43 | Dikchu, Sikkim | 3x32 | 96 | Alstom, India | 07/2011
44 | Gongri, Ar. Pradesh | 2x72 | 144 | Andritz Hydro, India | 13.12.13
45 | Rangit-II, Sikkim | 2x33 | 66 | Gammon India Ltd. | 24.03.12
| Sub-total- Others |  | 3675
| Sub-total (Private Sector): |  | 4075
| Total (Units Ordered): |  | 12412
Units not yet ordered
Central Sector
46 | Polavaram (PPA) Andhra Pr. | 12x80 | 960
| Sub-total (Central Sector): |  | 960
State Sector
| Sub-total (State Sector): |  | 0
Private Sector
47 | Bajoli Holi, H.P. | 3x60 | 180
48 | Panan, Sikkim | 4x75 | 300
| Sub-total (Private Sector): |  | 480
Total: (Units not yet ordered) |  |  | 1440
| Total: Under execution |  | 13852
- 46-

## summ ch 5
SUMMARY- 12th Plan
|  | Central | State | Private | Total
| Commissioned | 2424 | 442 | 595 | 3461
| 12th plan Under Construction | 3580 | 1166 | 2690 | 7436
| U/Cons. Beyond 12th Plan | 3695 | 856 | 1865 | 6416
| Total: (12th Plan) | 6004 | 1608 | 3285 | 10897
| Total: (12th Plan+13th Plan) | 7275 | 2022 | 4555 | 13852