Chapter- 2.2a

Hydro Capacity Addition during the Year 2012-13

| Sl. No. | Particular | Unit Nos. | Target (MW) | Commissioning as programmed | Actual (MW) | Actual (A)/ Anticipated | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | A. Central Sector |  |  |  |  |  |  |
| 1 | Chamera-III NHPC, H.P. 3x77= 231 MW | 1 2 3 | 77 77 77 | Jun-12 Aug-12 Oct -12 | 77 77 77 | 28.06.2012(A) 12.06.2012(A) 07.06.2012(A) |  |
| 2 | Uri-II NHPC, J&K 4x60= 240 MW | 1 2 3 4 | 60 60 60 60 | Aug -12 Sept -12 Nov-12 Dec-12 | - - - - | Slipped Slipped Slipped Slipped | - Local agitation from mid March, 12 to June, 12 end. - TRT was flooded on 17.09.12 due to flash flood. - Filling of U/s Water conductor system delayed due to agitation by local people demanding employment in NHPC. - Commissioned in 2013-14. |
| 3 | Chutak NHPC, J&K 4x11 =44 MW | 1 2 3 4 | 11 11 11 11 | Sept-12 Sept-12 Nov -12 Dec-12 | 11 11 11 11 | 22.11.2012(A) 08.11.2012(A) 11.11.2012(A) 28.01.2013(A) |  |
| 4 | Parbati-III NHPC, HP 4x130= 520 MW | 1 | 130 | Mar-13 | - | Slipped | - Non-availability of Transmission system. - Completion of Surge shaft gates. -Commissioned in 2013-14 |
|  | Sub- total (A): |  | 645 |  | 275 |  |  |
|  | B. State Sector |  |  |  |  |  |  |
| 5 | Bhawani Kattalai -II TANGEDCO, T.N Tamil Nadu, 2x15 = 30 MW | 1 2 | 15 15 | June-12 July-12 | - - | Slipped | - Unit #1&2 synchronised at part load in July,11 & Sept,11 - Reservoir filling delayed on account of less release from Mettur dam. - Commissioned in 2013-14 |
| 6 | Bhawani Kattalai -III TANGEDCO, T.N 2x15 = 30 MW | 1 | 15 | Oct-12 | 15 | 08.12.12(A) |  |
| 7 | Myntdu, MeECL, Meghalaya 3x42 = 126 MW | 3 | 42 | Mar-13 | 42 | 07.03.2013(A) |  |
|  | Sub- total (B): |  | 87 |  | 57 |  |  |
|  | C. Private Sector |  |  |  |  |  |  |
| 8 | Budhil Lanco H P 2x35=70 MW | 1 2 | 35 35 | May-12 July-12 | 35 35 | 30.05.2012(A) 26.05.2012(A) |  |
|  | Sub- total (C): |  | 70 |  | 70 |  |  |
|  | Total (A+B+C) |  | 802 |  | 402 |  |  |
| Out side the programme of 2012-13. |  |  |  |  |  |  |  |
| 1. | Teesta Low Dam –III NHPC, WB 4x33=132 MW | 1 2 3 | - - - | 2013-14 2013-14 2013.14 | 33 33 33 | 30.01.2013(A) 20.01.2013(A) 24.02.2013(A) |  |
|  | Sub- total : Outside |  | - |  | 99 |  |  |
|  | Total: 2012-13 |  | 802 |  | 501 |  |  |