# EXECUTIVE SUMMARY

Trend of Hydro-Thermal Mix as on 31.03.2016

| Hydro: | 42,783.42 MW | (16.50%) |
| --- | --- | --- |
| Thermal: | 2,10,675.04 MW | (81.27%) |
| Nuclear: | 5,780.00 MW | (02.23%) |

Hydro Capacity Under Execution (As on 31.03.2016): A hydro capacity of 13,502 MW   is under execution to give benefits during remaining period of 12th Plan & beyond. Sector wise summary is given as under:-

| Sector | Capacity (MW) |
| --- | --- |
| Central | 6235 |
| State | 2712 |
| Private | 4555 |
| Total: | 13,502 MW |

12th Plan Hydro Capacity Addition as Plan Progress:-

Hydro Capacity Addition for the Year 2012-13: Hydro Capacity Addition Monitorable Targets for the Year 2012-13  was 802 MW (645 MW in Central Sector, 87 MW in State Sector, and 70 MW in Private Sector.).  A Capacity of 501 MW  (374 MW in Central Sector, 57 MW in State Sector and 70 MW in Private Sector) has been achieved during 2012-13. Project-wise details are given in Chapter 2.2a.

Hydro Capacity Addition for the Year 2013-14: Hydro Capacity Addition Monitorable Targets for the Year 2013-14 was 1198 MW (914 MW in Central Sector, 85 MW in State Sector and 199 MW in Private Sector.).  A Capacity of 1058 MW  (914 MW in Central Sector, 45 MW in State Sector and 99 MW in Private Sector) has been achieved during the year 2013-14. Project-wise details are given in Chapter 2.2b.

Hydro Capacity Addition for the Year 2014-15: Hydro Capacity Addition Monitorable Targets for the Year 2014-15 was 842 MW (336 MW in Central Sector, 210 MW in State Sector and 296 MW in Private Sector.).  A Capacity of 736 MW in Central Sector has been achieved during the year 2014-15. Project-wise details are given in Chapter 2.2c.

Hydro Capacity Addition for the Year 2015-16: Hydro Capacity Addition Monitorable Targets for the Year 2015-16 was 1691 MW (590 MW in Central Sector, 575 MW in State Sector and 526 MW in Private Sector) A Capacity of 1516 MW (480 MW in Central Sector 610 MW in State Sector and 426 MW in Private Sector) has been achieved during the year 2015-16 up to 31.03.2016. Project-wise details are given in Chapter 2.2d.

Hydro Capacity Addition for the Year  2016-17: Hydro Capacity Addition Monitorable Targets for the Year 2016-17 is 1714 MW (490 MW in Central Sector, 995 MW in State Sector and 229 MW in Private Sector). Project-wise details are given as under:-

Hydro Projects Monitorable Target for 2016-17

| Sl. No. | Particular | Unit Nos. | Cap. (MW) |  | Commissioning as programmed |  | Actual(A)/ Anticipated | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A. | Central Sector |  |  |  |  |  |  |  |
| 1 | Teesta Low Dam IV NHPC, West Bengal 4x40 = 160 MW | Unit # 3 Unit # 4 |  | 40 40 | 6/16 9/16 |  |  |  |
| 2 | Kameng NEEPCO Arunachal Pradesh 4x150= 600 MW | Unit # 1 Unit # 2 |  | 150 150 | 2/17 3/17 |  |  |  |
| 3 | Pare NEEPCO, Arunachal Pradesh 2x55=110 MW | Unit # 1 Unit # 2 |  | 55 55 | 12/16 1/17 |  |  |  |
|  | Sub- total (C.S.): |  |  | 490 |  |  |  |  |
| B. | State Sector |  |  |  |  |  |  |  |
| 4 | Nagarjuna Sagar TR APGENCO, AP 2x25=50 MW | Unit # 1 Unit # 2 |  | 25 25 | 8/16 8/16 |  |  |  |
| 5 | Kashang – I HPPCL, H.P. 1x65=65 MW | Unit # 1 |  | 65 | 5/16 |  |  |  |
| 6 | Sainj HPPCL, H.P. 2X50=100 MW | Unit # 1 Unit # 2 |  | 50 50 | 12/16 1/17 |  |  |  |
| 7 | Lower Jurala TSGENCO, Telangana 6x40= 240 MW | Unit # 5 Unit # 6 |  | 40 40 | 9/16 11/16 |  |  |  |
| 8 | Pulichintala TSGENCO,Telengana 4x30= 120 MW | Unit # 1 Unit # 2 |  | 30 30 | 8/16 12/16 |  |  |  |
| 9 | New Umtru MePGCL; Meghalaya 2x20= 40 MW | Unit # 1 Unit # 2 |  | 20 20 | 11/16 12/16 |  |  |  |
| 10 | Teesta- III (*) Teesta Urja Ltd.; Sikkim 6x200= 1200 MW | Unit # 1 Unit # 2 Unit # 3 |  | 200 200 200 | 12/16 1/17 2/17 |  |  |  |
|  | Sub- total (S.S.): |  |  | 995 |  |  |  |  |
| C. | Private Sector |  |  |  |  |  |  |  |
| 11 | Chanju-I (#) IA Energy ; H.P. 3x12= 36 MW | Unit # 1 Unit # 2 Unit # 3 |  | 12 12 12 | 7/16 9/16 12/16 |  |  |  |
| 12 | Dikchu (#) Sneha Kinetic Power Projects (P).Ltd., Sikkim 3x32= 96 MW | Unit # 1 Unit # 2 Unit # 3 |  | 32 32 32 | 7/16 8/16 9/16 |  |  |  |
| 13 | Tashiding (#) Shiga Energy Pvt. Ltd. Sikkim 2x48.5= 97 MW | Unit # 1 Unit # 2 |  | 48.5 48.5 | 1/17 2/17 |  |  |  |
|  | Sub- total (P.S.): |  |  | 229 |  |  |  |  |
|  | Total C.S.+S.S.+P.S.) |  |  | 1714 |  |  |  |  |
|  | # Projects outside 12th plan but likely to be commissioned in 2016-17; (*) w.e.f. 6-8-15, Teesta Urja Ltd. is a Govt. of Sikkim Enterprise, hence in State Sector. |  |  |  |  |  |  |  |