- I  N  D  E  X

| Chapter | Contents | Page No. |
| --- | --- | --- |
|  | Preface | 1-2 |
|  | Executive Summary | 3-4 |
| 1. | Milestones achieved during the quarter Jan - Mar, 2016 | 5 |
| 2. | Plan wise hydro capacity targets/ achievements from 4th plan onwards. | 6 |
| 2.1 | Year/Plan wise hydro capacity in the country. | 7-8 |
| 2.2 | Hydro capacity addition during 12th Plan- As Plan progress | 9 |
| 2.2a | Hydro Capacity addition during 2012-13 | 10 |
| 2.2b | Hydro Capacity addition during 2013-14 | 11 |
| 2.2c | Hydro Capacity addition during 2014-15 | 12 |
| 2.2d | Hydro Capacity addition during 2015-16 | 13 |
| 3. | Growth of installed capacity. | 14 |
| 3.1 | Growth of hydro capacity. | 15 |
| 4. | Trend of hydro capacity addition. (hydro and thermal mix ) | 16 |
| 5. | A List of sanctioned H.E.Projects for benefits during 12th Plan & beyond. | 17-18 |
| 6. | Status of sanctioned H.E.Projects for benefits during 12th Plan & beyond. | 19-40 |
| 7. | Financial status of sanctioned H.E.Projects for 12th Plan & beyond. | 41-42 |
| 8. | Status of environment & forest clearance of sanctioned H.E.Projects for 12th Plan & beyond. | 43 |
| 9. | Status of Award of civil package for under execution H.E.Projects for 12th Plan & beyond. | 44 |
| 9.1 | Summary of ordering status of TG sets of under execution H.E. Projects for 12th Plan & beyond. | 45 |
| 9.2 | Status of ordering status of TG sets of under execution H.E.Projects for 12th Plan & beyond. | 46-47 |
| 9.3 | 12th Plan & beyond Projects- Ordering status of various packages | 48-60 |
| 10. | Status of financial closure of Private Sector projects. | 61-62 |
| 11. | Details of Under Construction Projects having Time/Cost over-run | 63-68 |