Chapter- 2.2d

Hydro Capacity Addition during the Year 2015-16

| Sl. No. | Particular | Unit Nos. | Target | Actual | Commissioning as programmed | Actual(A)/ Anticipated | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Capacity (MW) |  |  |  |  |
| A. | Central Sector |  |  |  |  |  |  |
| 1 | Koldam NTPC, HP 4x200= 800 MW | Unit # 3 Unit # 4 | 200 200 | 200 200 | 4/15 5/15 | 10.04.2015(A) 12.06.2015(A) | Commissioned |
| 2 | Teesta Low Dam –IV, NHPC, W.B 4x40 = 160 MW | Unit # 1 Unit # 2 | 40 40 | 40 40 | 2/16 3/16 | 14.02.2016 16.03.2016 | Commissioned |
| 3 | Pare NEEPCO, Arunachal Pradesh 2x55=110 MW | Unit # 1 Unit # 2 | 55 55 |  | 3/16 3/16 |  | Slipped to 2016-17 due to inundation of dam area with flood water after overtopping of Coffer Dam in June’15 and many times thereafter. |
|  | Sub- total (A): |  | 590 | 480 |  |  | Achieved:-480 MW |
| B. | State Sector |  |  |  |  |  |  |
| 4 | Baglihar - II JKPDC, J&K 3x150= 450 MW | Unit # 1 Unit # 2 Unit # 3 | 150 150 150 | 150 150 150 | 9/15 9/15 2016-17 | 05.09.2015(A) 29.09.2015(A) 26.10.2015(A) | Commissioned |
| 5 | Kashang – I HPPCL, H.P. 1x65=65 MW | Unit # 1 | 65 |  | 3/16 | 3/16 | Slipped to 2016-17 due to non-completion of E&M works. |
| 6 | Lower Jurala TSGENCO, Telangana 6x40= 240 MW | Unit # 1 Unit # 2 Unit # 3 Unit # 4 | 40 40 40 40 | 40 40 40 40 | 7/15 8/15 9/15 10/15 | 14.10.2015(A) 30.09.2015(A) 04.01.2016(A) 05.03.2016(A) | Commissioned |
| 7 | Nagarjuna Sagar TR APGENCO, AP 2x25=50 MW | Unit # 1 Unit # 2 | 25 25 |  | 7/15 7/15 | Likely to slip to 2016-17 | Unit 1 & 2 could not be commissioned due to non- availability of rated discharge. |
|  | Sub- total (B): |  | 575 | 610 |  |  | Achieved:-610 MW |
| C. | Private Sector |  |  |  |  |  |  |
| 8 | Sorang HSPCL, H.P. 2x50 = 100 MW | Unit # 1 Unit # 2 | 50 50 |  | 6/15 6/15 | 2016-17 2016-17 | Unit # 1 synchronized, but could not be commissioned due to non-availability of rated discharge. Penstock ruptured on 18.11.2015. Likely to slip to 2017-18. |
| 9 | Srinagar AHPCL, Uttarakhand 4x82.5=330 | Unit # 1 Unit # 2 Unit # 3 Unit # 4 | 82.5 82.5 82.5 82.5 | 82.5 82.5 82.5 82.5 | 4/15 4/15 5/15 6/15 | 10.04.2015(A) 08.06.2015(A) 20.04.2015(A) 03.06.2015(A) | Commissioned |
| 10 | Jorethang Loop DANS Pvt. Ltd., Sikkim 2x48= 96 MW | Unit # 1 Unit # 2 | 48 48 | 48 48 | 9/15 10/15 | 22.09.2015(A) 23.09.2015(A) | Commissioned |
|  | Sub- total (C): |  | 526 | 426 |  |  | Achieved:-426 MW |
|  | Total (A+B+C) |  | 1691 | 1516 |  |  | Achieved:-1516 MW |
|  |  | Note: 1516 MW out of 1691MW is Commissioned. |  |  |  |  |  |

Out side RFD achievements:

Unit #3 (400 MW) of Baglihar-II HEP commissioned ahead of Programme during Oct-2015.