# EXECUTIVE SUMMARY

Trend of Hydro-Thermal Mix as on 31.12.2016

| Hydro: | 43,139.43 MW | (16.34%) |
| --- | --- | --- |
| Thermal: | 2,15,168.90 MW | (81.48%) |
| Nuclear: | 5,780.00 MW | (02.19%) |
| Total: (excluding RES) | 2,64,088.33 MW |  |

Hydro Capacity Under Execution (As on 31.12.2016): A hydro capacity of 13,267.50 MW   is under execution to give benefits during remaining period of 12th Plan & beyond. Sector wise summary is given as under:-

| Sector | 12th Plan(2012-17) (As per Programme) | Beyond 12th Plan | Total Capacity (MW) |
| --- | --- | --- | --- |
| Central | 3420.00 | 2735.00 | 6155.00 |
| State | 1856.00 | 1901.50 | 3757.50 |
| Private | 1490.00 | 1865.00 | 3355.00 |
| Total: | 6766.00 | 6501.50 | 13,267.50 MW |

12th Plan Hydro Capacity Addition as Plan Progress:-

Hydro Capacity Addition for the Year 2012-13: Hydro Capacity Addition Monitorable Targets for the Year 2012-13  was 802 MW (645 MW in Central Sector, 87 MW in State Sector, and 70 MW in Private Sector.).  A Capacity of 510 MW  (374 MW in Central Sector, 66 MW  in State Sector and 70 MW in Private Sector) has been achieved during 2012-13. Project-wise details are given in Chapter 2.2a.

Hydro Capacity Addition for the Year 2013-14: Hydro Capacity Addition Monitorable Targets for the Year 2013-14 was 1198 MW (914 MW in Central Sector, 85 MW in State Sector and 199 MW in Private Sector.).  A Capacity of 1058 MW  (914 MW in Central Sector, 45 MW in State Sector and 99 MW in Private Sector) has been achieved during the year 2013-14. Project-wise details are given in Chapter 2.2b.

Hydro Capacity Addition for the Year 2014-15: Hydro Capacity Addition Monitorable Targets for the Year 2014-15 was 842 MW (336 MW in Central Sector, 210 MW in State Sector and 296 MW in Private Sector.).  A Capacity of 736 MW in Central Sector has been achieved during the year 2014-15. Project-wise details are given in Chapter 2.2c.

Hydro Capacity Addition for the Year 2015-16: Hydro Capacity Addition Monitorable Targets for the Year 2015-16 was 1691 MW (590 MW in Central Sector, 575 MW in State Sector and 526 MW in Private Sector) A Capacity of 1516 MW (480 MW in Central Sector 610 MW in State Sector and 426 MW in Private Sector) has been achieved during the year 2015-16. Project-wise details are given in Chapter 2.2d.

Hydro Capacity Addition for the Year 2016-17: Hydro Capacity Addition Monitorable Targets for the Year 2016-17 is 1714 MW (490 MW in Central Sector, 995 MW in State Sector and 229 MW in Private Sector).

A Capacity of  320 MW (80 MW in Central Sector, 240 MW  in State Sector) has been achieved during the year 2016-17 up to 31.12.2016. Project-wise details are given as under:-

Hydro Projects Monitorable Target for 2016-17

| Sl. No. |  | Particular | Unit Nos. | Cap. (MW) | Commissioning as programmed | Actual(A)/ Anticipated | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A. |  | Central Sector |  |  |  |  |  |
| 1 |  | Teesta Low Dam IV NHPC, West Bengal 4x40 = 160 MW | Unit # 3 Unit # 4 | 40 40 | Jun.16 Sep.16 | 03.07.2016(A) 11.08.2016(A) | Commissioned Commissioned |
| 2 |  | Pare NEEPCO, Ar. Pradesh 2x55=110 MW | Unit # 1 Unit # 2 | 55 55 | Dec. 16 Jan.17 | 2017-18 2017-18 | Slipped Slipped |
| 3 |  | Kameng NEEPCO Arunachal Pradesh 4x150= 600 MW | Unit # 1 Unit # 2 | 150 150 | Feb.17 Mar.17 | 2017-18 2017-18 | Slipped Slipped |
|  |  | Sub- total (C.S.): |  | 490 |  | 80MW |  |
| B. |  | State Sector |  |  |  |  |  |
| 1 |  | Sainj HPPCL, H.P. 2x50= 100 MW | Unit # 1 Unit # 2 | 50 50 | Dec.16 Jan.17 | Mar’17 Mar’17 |  |
| 2 | Kashang – I HPPCL, H.P. 1x65=65 MW |  | Unit # 1 | 65 | May 16 | 26.06.2016(A) | Commissioned |
| 3 | Lower Jurala TSGENCO, Telangana 6x40= 240 MW |  | Unit # 5 Unit # 6 | 40 40 | Sept.16 Nov.16 | 20.08.2016(A) 29.09.2016(A) | Commissioned Commissioned |
| 4 | Pulichintala TSGENCO,Telangana 4x30=120 MW |  | Unit # 1 Unit # 2 | 30 30 | Aug.16 Dec16 | 25.09.2016(A) Dec16 | Commissioned |
| 5 | New Umtru MePGCL, Meghalaya 2x20=40MW |  | Unit # 1 Unit # 2 | 20 20 | Nov.16 Dec.16 | Mar’17 2017-18 | Critical |
| 6 | Teesta-III Teesta Urja Ltd. 6x200=1200 MW |  | Unit #1 Unit # 2 Unit # 3 | 200 200 200 | Dec.16 Jan.17 Feb.17 | Jan’17 Jan’17 Jan’17 |  |
| 7 | Nagarjuna Sagar TR APGENCO, Telangana 2x25= 50 MW |  | Unit #1 Unit #2 | 25 25 | Aug.16 Aug.16 | Jan’17 Jan’17 | Depends on availability of water |
|  | Sub- total (B): |  |  | 995 |  | 175 MW |  |
| C. |  | Private Sector |  |  |  |  |  |
| 1 |  | Chanju-I IA Energy ; H.P. 3x12= 36 MW | Unit # 1 Unit # 2 Unit # 3 | 12 12 12 | July 16 Sept.16 Dec.16 | Jan’17 Feb’17 Feb’17 |  |
| 2 |  | Dikchu Sneha Kinetic Power Projects (P).Ltd., Sikkim 2x48= 96 MW | Unit # 1 Unit # 2 | 48 48 | July.16 Sept.16 | Feb’17 Feb’17 |  |
| 3 |  | Tashiding Shiga Energy Pvt. Ltd. Sikkim 2x48.5= 97 MW | Unit # 1 Unit # 2 | 48.5 48.5 | Jan.17 Feb.17 | Mar’17 Mar’17 |  |
|  |  | Sub- total (P.S.): |  | 229 |  |  |  |
|  |  | Total C.S.+S.S.+P.S.) |  | 1714 |  | 255 MW |  |
|  | Out Side Programme |  |  |  |  |  |  |
| 1 | Kashang-II & III HPPCL , HP |  | Unit # 1 | 65 | NA | 28.08.2016(A) | Commissioned |
|  | Grand Total (31.12.2016) |  |  |  |  | 320 MW |  |