Chapter 9.3

Status of ordering of various packages of 12th Plan & beyond Hydro Projects under construction

| Sl. No. | Project name/ Exec. Agency CEA clearance/ Approval Capacity (MW) | State Region | Contract | Scope of works & brief details | Contracting Agency (Name & Location) | Contract value ( Rs. Crs.) | # Date of Contract (commencement)/ Completion |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # Commissioned During 12th Plan |  |  |  |  |  |  |  |
| # Central Sector |  |  |  |  |  |  |  |
| 1 | ## Uri-II NHPC 11.2.2004/ 01.9.2005 4x60 = 240 MW | J&K NR | Civil works | Construction of Diversion Tunnel and its gate, Concrete Gravity Dam, Head Race Tunnel, Surge Shaft, Pressure Shaft, Under ground Power House, Tail Race tunnel | M/s HCC Ltd. | 574.99 | 21.09.2005 9/2009 |
|  |  |  | E&M works | Design, Manufacture, Supply, Erection , Testing & commissioning | M/s Alstom Projects India Ltd & M/s Alstom Power Hydraulique, France | 407.98 | 29.12.2006 03/2010 |
|  |  |  | H&M works | M/s Om Metals-SPML (JV) |  | 54.44 crs + € 0.75 million | 09.05.2007 31.08.2009 |
| 2 | ## Chamera-III NHPC 10.10.2003/ 01.09.2005 3x77= 231 MW | # H.P. NR | Civil works | Construction of Diversion Tunnel and its gate, Concrete Gravity Dam, Head Race Tunnel, Surge Shaft, Pressure Shaft, Under ground Power House, Tail Race tunnel | M/s HCC Ltd. | 504.87 | 21.09.2005 31.1. 2010 |
|  |  |  | # E&M works | # Design, Manufacture, Supply, Erection , Testing & commng. | # M/s Alstom Projects India Ltd & M/s Alstom Power Hydraulique France | # 251.90 | 23.012007 10/2010 |
|  |  |  | # H&M works | # Hydro-Mechanical Packages | # M/s Om Metals-SPML (JV) | # 74.69 | 26.07.07 15.8.10 |
| 3 | ## Chutak NHPC 23.04.2004/ 24.08.2006 4x11 = 44 MW | J&K NR | # Civil works | # Diversion channel, Barrage, Intake, HRT, Power House, TR | M/s HCC Ltd, Mumbai | 410.54 | 23.09.2006 11/2010 |
|  |  |  | # E&M works | # Generating units, and # Auxl. | M/s BHEL | 198.06 | 16.08.2007 02/2010 |
|  |  |  | H&M works | # Hydro-mechanical # works | M/s PES Engineers Private Ltd. | € 0.32m+ 25.9 crs | 06.08.2008 30.09.2010 |
| 4 | Teesta Low Dam-III NHPC 25.06.2002/ 30.10.2003 4x33 = 132 MW | # W.B.. ER | # Civil works | Construction of Barrage, WCS, Power House and Tail Race works, Diversion works, Switchyard etc. | M/s Patel Engg. Ltd, Mumbai | 239.11 | 28.10.2003 07/ 2007 |
|  |  |  | # E&M works | Generating Units, Main step up Transformers, Switch Yard, EOT Crane | M/s VA Tech Hydro India Pvt. Ltd. ,Bhopal, | 222.78 | 30.07.2004 10/2007 |
|  |  |  | # H&M works | Various Gates Packages | M/s Texmaco & M/s Alstom Ltd. Kolkata - Consortium | 41.53 Cr. + €2.95 (Ist Contract) + 8.85 crs (IInd contract) | 11.02.2005 12/2007 |
| 5 | ## Nimoo Bazgo NHPC 16,03.2006/24.08.2006 3x15 = 45 MW | # J&K NR | # Civil works | # Diversion channel, Dam, Intake, Power House, Swyd | M/s HCC Ltd, Mumbai | 383.90 | 23.09.2006 06/2010 |
| 6 | ## Parbati-III NHPC 12.11.2003/09.11.2005 ## 4x130 = 520 MW | # H.P. NR | # Civil works | Construction of Rockfill Dam, Intake Structure and part Head Race Tunnel (5.9 km.) etc. Construction of part Head Race Tunnel (1.97km), SurgeShaft, Pressure Shaft, Power House and Tail Race Tunnel etc. | M/s Patel – L&T Consortium M/s Jager – Gammon JV | 439.08 324.20 | 15.12.2005 08/2010 15.12.2005 08/2010 |
| 7 | Ram Pur (SJVNL) SJVNL 16.12.2005/25.01.07 6x68.67= 412 MW | # H.P. NR | Civil & H&M works | Construction of civil works for HRT (from 51m to 12900m), river diversion works | M/s Patel – Gammon JV, Mumbai | 382.44 + USD 9.09 million | 01.02.2007 08/2011 |
|  |  |  |  | Construction of civil works for HRT (from 12900m to 15088), surge shaft, pressure shaft, Power House & Hydro Mechanical works | M/s Patel – Gammon JV, Mumbai | 364.25 + JY 359.13 million | 02/2007 04/2011 |
|  |  |  | E&M works | Turbine generating units and associated auxiliaries | M/s BHEL | 476.43 crs + € 15.15m | 16.9.2008 15.3.2012 |
| 8 | Kol Dam NTPC 30.6.2002/Oct.2002 # 4x200 = 800 MW | # H.P. NR | Civil works | Package for Main Dam, Spillway & power intake | M/s Italian Thai Development Public Co. Ltd., Bankok, Thailand | 664.56 | 12/2003 11/2008 |
|  |  |  |  | De-silting arrangement | M/s Afcons & RN Shetty & Co. JV Mumbai | 158.37 | 01/2005 11/2008 |
|  |  |  |  | Power House, Penstock Tunnels & Tail Race Channel | M/s Gammon India Ltd., Mumbai | 189.22 | 05/2004 11/2008 |
|  |  |  |  | Diversion Tunnel | M/s. Continental Cons Ltd., New Delhi | 166.65 | 06/2002 08/2004 |
|  |  |  | E&M works | Electro-Mech. Package | M/s BHEL, Toshiba & Marubeni JV | 261.35 | 07/2004 04/2009 |
|  |  |  |  | Generator Transformer | M/s BHEL | 35.26 | 03/2005 04/2009 |
|  |  |  |  | Switch Yard including civil works | M/s L&T hennai | 54.74 | 10/2005 04/2009 |
|  |  |  | H&M works | Hydro-Mechanical Packages | M/s. OM Metals & Minerals Ltd., Delhi | 37.60 + Euro 1.88 M | 08/2003 11/2008 |
|  |  |  | E&M works | Turbine generating units and associated auxiliaries | M/s BHEL | 476.43 crs + € 15.15m | 16.9.2008 15.3.2012 |
| 9 | Teesta Low Dam-IV NHPC 23.12.2003/30.09.2005 4x40 = 160 MW | # W.B.. ER | # Civil works | Construction of Diversion Arrangmt, Concrete Gravity Dam , PH, TRT | M/s HCC Ltd. , Mumbai | 395.90 + US $ 10.2 Million | 10.05.2006 09/2009 |
|  |  |  | # E&M works | Supply, erection, testing & commissng of TG unit | M/s BHEL | 247.57 | 10.05.2007 05/2010 |
|  |  |  | # H&M works | Supply, erection, testing & commissng of gates | M/s Om Metals -SPML JV | 88.80 | 09.05.2007 08/2009 |
| # State Sector |  |  |  |  |  |  |  |
| 10 | Bhawani Kattalai Barrage-II TANGEDCO/ 11.6.99 2x15 = 30 MW | Tamil Nadu SR | # Civil works & H&M works | # Construction of Power House, including TR | # K. Rajagopalan & Co. Mettur and M/s Shri Saravana Enterprises, Madurai Consortium | # 40.22 | # 24.02.2006 23.08.2008 |
|  |  |  |  | # Construction of Barrage & Gates | # K. Rajagopalan & Co. Mettur and M/s Shri Saravana Enterprises, Madurai Consortium | # 44.75 | # 27.04.2007 26.10.2009 |
|  |  |  | # E&M works | # Turbine Generating units and auxiliaries | M/s Litostroj, Slovania & M/s Koncar Croatia | # Euro 15.24 M # + 23.685 Cr | # 27.12.2006 27.05.2009 |
| 11 | Bhawani Kattalai Barrage-III TANGEDCO/ 27.03.2002 2x15 = 30 MW | Tamil Nadu SR | # Civil works & # H&M works | # Construction of Power House, including TR | # M/s East Coast Construction & Industries, M/s General Mechanical works, Chennai | # 39.99 | # 03.02.2006 # 21.08.2008 |
|  |  |  |  | # Construction of Barrage & Gates | M/s East Coast Construction & Industries, M/s General Mechanical works, Chennai | # 28.23 | # 11.10.2006 01.05.2009 |
|  |  |  | # E&M works | # Turbine Generating units and auxiliaries | # M/s Litostroj, Slovania & M/s Koncar Croatia | # Euro 15.24 Million + # 23.685 Cr | # 15.11.2006 # (27.12.2006) 27.05.2009 |
| 12 | Myntdu, MeECL 20.09.99/ 2x42 = 84 MW | Megha laya NER | Civil works | Main Dam Civil Works | M/s SEW Construction Ltd., Hyderabad | 87.80 | 03/2004 03/2007 |
|  |  |  |  | HRT, Surge Shaft, Intake, pressure tunnel, PH,TRT | M/s Skanska Cementation (I) Ltd., Kolkata | 52.84 | 02/2005 04/2007 |
|  |  |  |  |  | M/s SEW Construction Ltd., Hyderabad | 28.62 | 02/2006 05/2008 |
|  |  |  | E&M works | Generating unit & equipment | VA TECH Hydro India (Pvt) Ltd. & Vatech Escher Wyss Flovel Ltd. | 66.00 | 30.11.2005 05/2008 |
|  |  |  | H&M works | # Gates, erection, # commissioning | # M/s Precision, Ahmedabad | # 25.62 | # 12/2005 06/2007 |
| 13 | Baglihar-II JKPDC 3x150= 450 MW | J&K N.R. | Civil works & HM works |  | Jai Prakash Associates, New Delhi | 503.50 | 31.03.2012 03.01.2016 |
|  |  |  | # E&M works |  | Voith-Andritz Germany/ Voith –Andritz India consortium | Euro 78.698 million + 447.37 Crs. | 31.03.2012 15.08.2015 |
| 14 | Lower Jurala TSGENCO, TEC in July 2007 6x40=240 MW | Telan gana SR | Civil works | .Excavation of approach channel, powerhouse pit, tail race channel | M/s M. Ramakrishna Reddy, Hyderbad | 95.99 | # 10.02.2008 09.02.2010 |
|  |  |  |  | # Weir woks | # M/s Patel-VARKS-JV, Hyderbad | # 79.10 | # 05.09.2008 04.03.2011 |
|  |  |  | # E&M works | # Design, manufacture, testing & commng of TG unit and auxiliaries | # M/s Alstom Projects, India | # 13.7m+238 cr # (for supply) # 0.007.7m + # 43.45crs- erection | # 09.06.2008 # 08.01.2013 |
| 15 | ## Kashang-I H.P. Power Corpn. Ltd. 11.01 / 09.04.2009 1x65= 65 MW | # H.P. NR | Civil and H&M works | # River Diversion of Kerang Khand, Trench Weir, Connveyance Tunnel, De-sanding Basins, Connecting Tunnel, Kerang- Kashang Link Tunnel, Drop Structure, Underground Balancing Reservoir, HM works St.-II & St.-III | # M/s Patel Engg. Ltd. | # 252.39 | # 12.11.2010 11.11.2014 |
|  |  |  | # E&M works | # Included with Kashang Stage-I |  |  |  |
| 16 | ## Kashang-II & III H.P. Power Corpn. Ltd. 11.01 / 09.04.2009 1x65 + 1x65= 130 MW | # H.P. NR | Civil and H&M works | # River Diversion of Kerang Khand, Trench Weir, Connveyance Tunnel, De-sanding Basins, Connecting Tunnel, Kerang- Kashang Link Tunnel, Drop Structure, Underground Balancing Reservoir, HM works St.-II & St.-III | # M/s Patel Engg. Ltd. | # 252.39 | # 12.11.2010 11.11.2014 |
|  |  |  | # E&M works | # Included with Kashang Stage-I |  |  |  |
| 17 | Pulichintala (TSGENCO) 4x30=120 MW Partially commissioned Unit #1 = 30MW | Telangana SR | Civil & H&M Works | Construction of Power House, Tail Race, , gates etc. | M/s SCL-CR18G JV | 56.59 | # 01.08.2007 01.02.2011 |
|  |  |  | E&M # works | # Design, manuf., testing & supply of TG unit and auxiliaries | # M/s BHEL | # 155 | # 25.05.2007 24.01.2010 |
|  |  |  |  | # Erection of E&M equipment | # M/s Hypower Associates, Jabalpur Re-awarded to M/s Yantra Epcom Solutions Pvt. Ltd., Hyderabad | # 3.63 Crores. | # 28.08.2009 27.05.2011 (Contract terminated in August 2013) re-awarded 17.02.2014 |
| # Commissioned Outside from 12th Plan Programme |  |  |  |  |  |  |  |
| # | Jaldhaka (WBSEDCL) 4x9=36 MW | W.B. |  |  |  |  |  |
| # Private Sector |  |  |  |  |  |  |  |
| 18 | Budhil Lanco Green Power Pvt Ltd TEC on 2.06.2005 by HPSEB/ March 07 (FC) 2x35=70 MW | H.P. NR | Civil works | Dam, HRT Power house etc | Lanco Infratech Limited | 198.0 | 26.12.05 30.04.08 |
|  |  |  | E&M works | Supply of TG sets | Dongfang electric Corporation limited, China | 40.0 | 12.07.06 31.03.08 |
|  |  |  |  | Supply of other E&M equipment and Erection & commissioning of E&M equipment | Lanco Infratech Limited | 56.0 | 17.07.06 30.04.08 |
|  |  |  | H&M works | Complete civil works and HM works | Lanco Infratech Limited | 198.0 | 26.12.05 30.04.08 |
|  |  |  | E&M works | # Entire EM works including TG sets | M/s Abir Construc. Pvt. Ltd. TG Set- M/s Dongfang Electric Corporation, Ltd. | 40.0 | 18.10.06 04/08 |
| 19 | Chujachen Gati Infrastructure Ltd, Secunderabad 30.11.2004 (State Govt.)/ 2x49.5= 99 MW | Sikkim ER | Civil works | # Dam, Tunnel, Power House, Surge-Shaft, Intake | # M/s SEW –Prasad JV, Hyderabad | # 200 | # 12.8.2006 03/2009 |
|  |  |  | # E&M works | # Generating units and auxiliaries | M/s Alstom Project India Ltd | 158 | # 20.12.2006 06/2009 |
|  |  |  | # H&M works | # Design Engineering Fabrication & Erection of Gates | M/s SEW Ltd. |  | 08/2006 |
| 20 | ## Srinagar GVK Industries Ltd. 20.07.05/ 3.8.2007 (FC) 4x82.5=330 MW | Uttara khand NR | Civil works | # Awarded |  |  | 06/2007 |
|  |  |  | E&M works | # Manufacturing., Supply, erection & commng. of TG units | M/s BHEL | 442.13 | 04/2007 |
| 21 | Jorethang Loop M/s DANS Energy 2x48 = 96 MW | Sikkim NER | Civil works and H&M works | # Barrage , Tunnel , Power House, Surge-Shaft, Intake, # Design Engg., # Fabrication & # Erection of Gates | EPC Contract M/s SEW Infrastructure Limited | 463.3 | # 01.12.2009 01.09.2012 |
|  |  |  | # E&M works | # Supply, erection, testing of Generating units and auxiliaries | M/s Alstom Projects India Limited | 107.59 + Euro 0.2534 | # 07.08.2009 07.05.2012 |
| # Under Execution |  |  |  |  |  |  |  |
| # Central Sector |  |  |  |  |  |  |  |
| 1 | Kishanganga NHPC 06.08.2003/ 14.01.2009 # 3x110 MW = 330 MW | J&K NR | Turn key Contract | Dam, Head Race Tunnel, Surge Shaft, Pressure Shaft, Power House, Tail Race tunnel | # Turn-key execution by consortium of M/s HCC Ltd., M/s DSD Noell Gmbll, Germanyand # M/s BHEL with M/s HCC as lead partner. | 1925.84 | 22.01.2009 |
|  |  |  |  | Supply of H&M Plant & Machinery |  | Euro 2.70 crs + 15.24 crs |  |
|  |  |  |  | Erection, Testing & Commissioning |  | Euro 0.10 + 25.17 crs |  |
|  |  |  |  | Supply of E&M Plant & Machinery |  | Euro 0.55 crs + 398.95 crs |  |
|  |  |  |  | Erection, Testing & Commissioning |  | Euro 0.12 crs + 50.06 crs |  |
| 2 | Parbati-II NHPC 12.10.1999/ 11.09.2002 # 4x200 = 800 MW | # H.P. NR | # Civil works | Lot-1: Civil & HM works for Dam and Part HRT (0-3500m) | M/s Patel-SEW JV, | 322.9 | 11.09.2002 10.09.2007 |
|  |  |  |  | # Lot-2: Civil & HM works of HRT (3500-24733m) | M/s Himachal JV | 419.89 | 11.09.2002 10.09.2007 |
|  |  |  |  | Contract terminated in March-12 and Fresh awarded as under. |  |  |  |
|  |  |  |  | # Lot-2A: Balance civil works of HRT by TBM | # M/s Gammon-CMS JV, Mumbai | # 455.63 | 13.08.2013 12.08.2017 |
|  |  |  |  | # Lot-2B: Balance civil works of HRT by DBM and associated HM works | # M/s Valecha Engg. Ltd, Mumbai | # 176.29 | 21.11.2013 20.11.2017 |
|  |  |  |  | # Lot-3: Civil & HM works of Power House, Pressure Shaft, Surge Shaft & Part HRT (24733-31525) | # M/s Gammon India Ltd. | # 603.69 | 13.09.2002 13.03.2007 |
|  |  |  |  | # Lot-4: Jiwa Nallah Works | # M/s BJ_Techno-HAS (JV) | # 56.47 | 11.09.2002 10.09.2007 |
|  |  |  |  | Contract terminated and Fresh awarded as under: |  |  |  |
|  |  |  |  | Lot-4A: Balance Civil & HM works of Jiwa Nallah and associated works | # M/s Coastal Projects, Noida | 78.34 | # 22.06.2011 21.04.2014 |
|  |  |  | E&M works | Generating Units, EOT Crane # Main step up Transformers, Switch Yard and | # M/s BHEL | 354.44 | 24.12.2002 23.04.2007 |
|  |  |  |  | # Electrical & Mechanical Auxiliaries | # M/s BHEL | # 34.2 | 24.12.2002 23.04.2007 |
|  |  |  | # E&M works | # Design, Manufacture, Supply, Erection , Testing & commg. | # M/s BHEL | # 391.11 | 29.12.2006 02/2011 |
|  |  |  | # H&M works | # Hydro-Mechanical Packages | # M/s Om Metals-SPML (JV) | # 96.08 | 26.07.07 15.8.10 |
| 3 | Tehri PSS, THDC, 18.7.06 Nov-11 (Revised CCEA) 4x250=1000 MW | # Uttara. khand NR | EPC/ Turnkey Contract | - Planning, Design and Engg. ii. Civil works - Supply of EM & HM (off shore) iv. Supply of E&M and HM (on shore) E&M and HM services | # Consortium of M/S Alstom Hydro France and Hindustan Construction Company with M/s Alstom Hydro, France as lead partner | Total in 1843.49 E&M equip:- Euro 62.92 million + # 474.43 Cr. | 23.06.2011 27.07.11 26.01.2016 (Commencement Date) |
|  |  |  |  |  |  |  | U-1: 48 Mth. U-2: 50 Mth. U-3: 52 Mth. U-4: 54 mth. (from commenc.) |
| 4 | ## Tapovan Vishnugad NTPC 11.08.2004/Nov, 2006 4x130 = 520 MW | # Uttara. khand NR | Civil works | Construction of Barrage and De-silting chambers | M/s SSJV Projects Pvt. Ltd. and M/s ZVS, Russia | 276..91 | 01/2007 07/2012 Contract terminated in Nov-10. |
|  |  |  |  | Contract terminated in November-10 and fresh award made in July-12 |  |  |  |
|  |  |  |  | Construction of Barrage and De-silting chambers (Balance Works) | M/s Rithwik Projects Pvt. Ltd., Hyderabad. | 457.57 | 07/2012 03/2015 |
|  |  |  |  | # Works have been re-awarded. # Details to be provided. | M/s L&T Ltd. and M/s Alpine Mayreder Bau GmbH | 455.921 | 11/2006 08/2012 |
|  |  |  |  | # Power House & Penstock package | M/s Patel Engg. Pvt. Ltd. | 221.28 Cr. + Euro 37.58m | 05/2007 08/2012 |
|  |  |  | E&M works | # Turbine generating units and associated auxiliaries | M/s BHEL | 328.28 crs. | 1/.2008 12/12 |
|  |  |  | H&M works | # Manufacturing, erection & Commissioning of various gates. | M/s Om Metal Infra project Ltd. | 64.19 Cr. + €1.26m | 10./07 09/12 |
| 5 | Lata Tapovan, NTPC Aug-2012 3x57= 171 MW | # Uttara khand NR | Civil & HM works | # EPC Contract | M/s L&T | 780.54 | 17.08.2012 16.08.2017 |
|  |  |  | E&M Package |  | BHEL | 2611.04 | Dec, 12 June, 17 |
| 6 | Vishnugad Pipalkoti, THDC 21.08.2008 4x111= 444 MW | # Uttara khand NR | Civil & HM works | # EPC Contract | M/s HCC Ltd | 1597.30 | 17.01.2014 16.07.2018 |
|  |  |  | E&M Package | # EPC Contract | BHEL | 360.36 | 18.11.2014 17.11.2018 |
| 7 | ## Subansiri Lower ## NHPC ## 07.06.2001/09.09.03 8x250= 2000 MW | ## Ar.Pr/ Assam NER | Civil works | # Dam/Barrage, Water # conductor system | M/s BGS – SGS - Soma JV, Hyderabad | 1098.32 | 19.12.2003 12/2009 |
|  |  |  |  | Power House & Tail Race civil works | M/s L & T LTD, Chennai | 921.59 | 19.12.2003 12/2009 |
|  |  |  |  | Supply of CIF/CIP: Supply of all off shore equipments and material including general and specified spares. | Consortium of M/s Alstom Power Hydraulique, France And M/s Alstom Project India Ltd. | Euro 76.80 million + US$ 6,779,760. | 11.02.2005 08/2010 |
|  |  |  | E&M works | Ex-works supply of all equipment and material including general and specified spares of Indian origin. | Consortium of M/s Alstom Power Hydraulique, France and M/s Alstom Project India Ltd. | € 23.21 million + US$ 14,56 million + 727.97 crs | 11.02.2005 08/2010 |
|  |  |  |  | Local transportation including port clearance and port charges and inland insurance and installation services. | M/s Alstom Project India Ltd. | 1,23,74,37,486. 00 | 11.02.2005 08/2010 |
|  |  |  | # H&M works | Supply, erection & commng. of gates | # M/s Texmaco Ltd. | 283.48 Cr. + Euro 2.22 M | 19.06.2006 04/2010 |
| 8 | Kameng NEEPCO 12 2004/ 4x150 = 600 | Ar. Pr. NER | Civil and H&M works | Package-I Bichom Dam & part of Bichom & Tenga tunne | M/s Patel – Unity JV, Mumbai | 143.81 | 08.12.2004 08.02.2009 |
|  |  |  |  | Package-II Tenga Dam & part of Bichom & Tenga Tunnel & part of Tenga kimi tunnel |  | 116.40 | 08.12.2004 08.02.2009 |
|  |  |  |  | Package.-III P.H. civil works & part of Tenga kimi tunnel |  | 131.65 | 08.12.2004 08.02.2009 |
|  |  |  |  | Package-IV Hydro-mechanical works & penstock lining. | M/s OMML & JSC-JV, New Delhi | 236.14 | 17.12.2004 51 months |
|  |  |  |  | Diversion Tunnel (Re-awarded) | M/s SEW Coastel-JV Hyderabad | 39.44 | 07.01.2010 07/2010 |
|  |  |  | E&M works | Package-V Generating Units | M/s. BHEL, New Delhi. | 241.11 | 03.12.2004 12/2009 |
| 9 | Pare NEEPCO 24.9.2007/4.12.2008 2x55 = 110 MW | Ar. Pr. NER | # Package-I Civil works | Package-I : Dam, Water Conductor system, Power House | M/s HCC Ltd. Mumbai | 276.44 | 31.08.2009 30.08.2012 |
|  |  |  | # Package-II : # H&M works | # Package-II : Gates, # Trash Rack, Penstocks # and Steel liners | M/s Precision Infratech Ltd. Ahmedabad | 47.50 | 03.12.2010 12/2012 |
|  |  |  | # Package-III # E&M works | # Contract-1 : Design # & Engineering, manufacture, # Supply of Turbine Generator sets, Control Panels along # with Aux. # Contract-2 : Erection, Testing & # Commissioning of TG sets, Control Panels along with Aux. | M/s Andritz Hydro Pvt. Ltd. | 108.01 Cr.+ Euro 0.5090 | 01.10.2010 09/2013 |
|  |  |  |  |  | M/s Andritz Hydro Pvt. Ltd., India | 11.12 | 01.10.2010 09/2013 |
|  |  |  | # Package- IV (Switch Yard & Transformer | # Supply of entire equipment of Switchyard & # Transformer | M/s Areva T&D India Limited | 20.92 | 26.09.2011 07/2013 |
|  |  |  |  | # Erection, Testing & # Commissioning of # Switchyard & # Transformer | M/s Areva T&D India Limited | 3.23 | 26.09.2011 07/2013 |
| 10 | Tuirial NEEPCO Revised CCEA 14.01.2011 2x30= 60 MW | Mizo ram NER | Civil works | # Dam & Spillway | M/s Patel Engg. Ltd. | 187.98 | 30.08.2002 14.01.2011 (Revised) 13.01.2014 |
|  |  |  |  | # Power House, # Switchyard and Power # Water Way |  | 32.75 | 31.12.2002 14.01.2011 (Revised) 13.01.2014 |
|  |  |  | H&M works | # Supply, # Manufacture, # Fabrication, Erection, # Testing & Commissioning etc | M/s Sew-PES- Tuirial Consortium | 36.43 | 22.09.2011 09/2013 |
|  |  |  | E&M works | # Lot-V : First Contract: # Manufacture, Supply of Power plant equipment, station and unit auxiliaries along with switchyard works. Second Contract: Erection, testing commissioning of Main plant and associated switchyard works. | # M/s BHEl, New Delhi. | 113.62 + 21.38 = 135.00 (Total) | 25.10.2003 01.08.2011 (Revised) 14.01.2014 |
| 11 | Ramam-III NTPC Ltd. 3x40= 120 MW | W.B. E.R. | Civil works & HM works | Approach road to right bank of barrage to access various project component, Barrage construction, Under ground de-silting chamber with SFT and 5.1 km HRT | M/s. Simplex-Apex-JV | 360.83 | 10.09.14 09/2019 |
|  |  |  |  | Access from bridge on Rammam river to various proj. components, 3.1 km HRT, Surface Power House, 740 m TRC and 132 KV Switchyard. | M/s. SEW Infrastructure Ltd. | 265.39 | 12.12.14 12/2019 |
|  |  |  | E&M works | Design, Engineering, Manufacturing, Supply, Insurance, Erection, Testing & Commissioning works for EM works EPC contract package. | M/s. BHEL | 224.67 | 19.02.2015 11/2018 |
|  | State Sector |  |  |  |  |  |  |
| 12 | ## Parnai JKSPDC 21.10.2013 3x12.5= 37.5 MW | # NR J&K | Civil works | # EPC contract | # M/s. Patel Engineering Ltd. & M/s. Alstom India. |  | # 25.10.2013 |
| 13 | ## Lower Kalnai JKSPDC 16.08.2013 2x24= 48 MW | # NR J&K | Civil works | # EPC contract | # M/s Coastal Projects Ltd. |  | # 12.09.2013 |
| 14 | ## Uhl-III, BVPC Ltd. 19.09.02 / -------- (TEC -2x50 MW) 3x33.3 =100 | H.P. NR | Civil works | Neri Intake works & power channel | M/s SSJVPP Ltd. 12th floor S.N.Tower 25/2 M.G.Road, Banglore Fresh Package awarded on 25.10.08 to: Continental Corp Project Ltd. | 8.68 | 18.04.05 15.8.07 Re-awarded on 25.10.08 |
|  |  |  |  | Head Race Tunnel (HRT) | M/s SSJVPP Ltd. 12th floor S.N.Tower 25/2 M.G.Road, Banglore 560001 Package re-awarded to: Continental Corp Project Ltd.. Re-awarded to M/s Abir Infrastructure Pvt. Ltd., Gurgaon. | 69.58 | 02.04.03 30.04.07 15.10.2010 |
|  |  |  |  | Rana Intake Works & Power channel | M/sTRG Industries Pvt Ltd E- 461 Greater Kailash –II New Delhi | 17.53 | 26.07.05 26.10.07 |
|  |  |  |  | Penstock fabrication, erection | M/s PES.Engineers Pvt. Ltd. Hyderabad-500016 | 57.26 | 27.05.05 27.11.07 |
|  |  |  |  | Power House | M/s Pilot Engg., Ludhiana | 9.87 | 19.6.2007 12/2009 |
|  |  |  | # E&M works | Generating Equipment & Associated Aux, Transformers | M/s BHEL | 117.36 | 15.02. 07 15.04.10 |
| 15 | Sawara Kuddu HP Power Corporation, 3x36.67=110 | # H.P. NR | Civil and H&M works | Package-I : Barrage, Power Intake, Desanding Arrangements and Gates & Hoisting Arrangements | M/s Patel Engineering Ltd. | # 283.49 | # 08.10.2009 07.06.2012 |
|  |  |  |  | Package-II : Construction of HRT | M/s Aban Coastal JV | # 115.92 | 17.07.2007 16.07.2011 |
|  |  |  |  | Contract Terminated on 09.01.2014. Re-awarded on 03.11.2014 to M/s. HCC. |  |  |  |
|  |  |  |  | Package-III : Power House Complex, Surge Shaft, Pressure shaft, Machine Hall, Erection Bay, Transformer Cavern, Pot Head Yard, Cable Tunnel, MAT & other Tunnels and TRT | M/s Patel Engineering Ltd. | # 153.37 | 04.03.2009 03.06.2012 |
|  |  |  | # E&M works | Package-IV: # Generating Units with associated Auxiliaries, Generator Transformers, 245 KV GIS, XLPE Cable and other power equipment | # M/s Andritz Hydro Pvt.Ltd. | # 180.54 | # 28.04.2009 27.04.2012 |
| 16 | ## Kashang-II & III H.P. Power Corpn. Ltd. 11.01 / 09.04.2009 1x65 + 1x65= 65 MW Unit#1 65 MW Commissioned. | # H.P. NR | Civil and H&M works | # River Diversion of Kerang Khand, Trench Weir, Connveyance Tunnel, De-sanding Basins, Connecting Tunnel, Kerang- Kashang Link Tunnel, Drop Structure, Underground Balancing Reservoir, HM works St.-II & St.-III | # M/s Patel Engg. Ltd. | # 252.39 | # 12.11.2010 11.11.2014 |
|  |  |  | # E&M works | # Included with Kashang Stage-I |  |  |  |
| 17 | ## Sainj H.P. Power Corpn. Ltd. 29.12.2010/ 02.08.2010 2x50=100 MW | # H.P. NR | # Civil and H&Mworks | EPC Contract Package for Civil & HM works | # M/s Hindustan Construction Co. Ltd. | # 431.00 | # 02.08.2010 02.08.2014 |
|  |  |  | # E&M works | Generating Units, Generator Transformers, 245 KV GIS, XLPE Cable and other Power Plant equipment for power house complex, Pothead Yard area, Barrage area and BFV house area | # M/s Voith Hydro, Pvt. Ltd. | # EURO 3304219 + USD $ 8319779 + 8,79,526,565 = 155.56 Cr. (Total Amt.) | # 17.08.2011 16.02.2015 |
| 18 | ## Shongtong Karcham H.P. Power Corpn. Ltd. Clearance: 16.08.2012/ 3x150= 450 MW | H.P. 2017-18 2017-18 | Civil And H&M works | EPC Contract Package for Civil & HM works | M/s Patel Engineering Ltd. | # 103.24 | # 04.08.2012 03.08.2017 |
| 19 | ## Shahpurkandi, Irrigation Deptt/PSPCL 04.05.2011 3x33+3x33+1x8= 206 MW | Punjab NR | Civil works & HM works | Main Dam alongwith Two head regulators | SOMA-BUREYA Joint Venture | 687.51 | 11.02.2013 Oct- 2016 |
|  |  |  |  | Hydel Channel | M/s Gurinder Singh Contractor | 90.11 | 26.02.2013 Oct- 2015 |
|  |  |  | E&M works | EPC Contract | BHEL |  | 28.02.14 |
| 20 | Koyna Left Bank PSS WRD, Govt. of Mah. 20.02.2004 2x40 = 80 MW | # Maha. WR | Civil and H&M works | # Barrage, Intake tunnel, Twin lake tap, Ventilation tunnel, Power house, Intake structure ,HRT, Pressure shaft, tail surge shaft, pen stoke, TRT, Bus duct tunnel, Lower intake structure | # M/s B.T. Patil-Malaxmi (JV), Pune # M/s Patel Engg. Ltd. Mumbai | # 131.91 Crs. # 118.86 Crs. | # 20.06.2007 30.06.2013 03.10.2007 30.06.2016 |
|  |  |  | # E&M works | Design, manufacture, testing & commissioning of TG unit and auxiliaries | # M/s IVRCL Ltd. Pune Turbine- Litostroj Slovania Generator- Koncar, Croatia | # Euro 4.03 Crs + # 177.99 Crs | # 16.12.2010 15.12.2014 |
| 21 | ## Nagarujana Sagar TR APGENCO ## 01 05 (TEC Transfer)/--- 2x25=50 MW | # A.P. SR | # Civil Works | # Excavation of foundation of dam and power house | # M/s Rama Krishna Reddy, Hyderabad | # 13.38 | # 19.05.2005 15.06.2006 |
|  |  |  |  | Spillway, power dam, intake, penstock ferrules | # M/s Maytas-Shankara Narayan JV, Bangalore | # 86.60 | # 15.4.2006 15.4.2008 |
|  |  |  |  | # Power House | M/s SEW const. Ltd., Hyderabad | # 22.77 | # 26.09.2006 25.03.2008 |
|  |  |  | # E&M works | # Design, manuf. testing & commissioning of TG unit and Auxl. | # M/s BHEL | # 61.26 | # 03.05.2006 02.09.2008 |
|  |  |  |  | # Erection of E&M equipment | # M/s Hypower Associates, Jabalpur |  | # 19.03.2008 |
|  |  |  | # HM Works |  | # M/s GTV-PES JV |  | # 11.05.2009 |
| 22 | Polavaram (PPA) 21.07.10/ 25.02.09 12x80 = 960MW | Andhra Pradesh S.R. | Civil works & HM works | Investigation and L.P schedules etc., (Balance) & | M/s. Trans stroy-JSCECUES (JV), Hyderabad | 4054.00 | 02.03.2013 01.03.2018 |
|  |  |  |  | 1) Construction of Earth Dam Gaps-I & II, Earth-cum-Rock fill Dam for Gap-I & II , Spill channel, Approach channel and Pilot channel. |  |  |  |
|  |  |  |  | 2) Construction of Spillway with concreting level+25.72m and its ancillary work and 3) Excavation of foundation of 960MW Hydro electric Power House, approach channel, Intake structure, Tail Race Pool , Tail Race Channel of ISPP on EPC Turnkey including O&M. |  |  |  |
|  |  |  | E&M works | Work yet to be awarded. |  |  |  |
| 23 | ## Pulichintala TSGENCO 4X30=120MW |  | Civil & H&M Works | Construction of Power House, Tail Race, , gates etc. | M/s SCL-CR18G JV | 56.59 | # 01.08.2007 01.02.2011 |
|  |  |  | E&M # works | # Design, manuf., testing & supply of TG unit and auxiliaries | # M/s BHEL | # 155 | # 25.05.2007 24.01.2010 |
|  |  |  |  | # Erection of E&M equipment | # M/s Hypower Associates, Jabalpur Re-awarded to M/s Yantra Epcom Solutions Pvt. Ltd., Hyderabad | # 3.63 Crores. | # 28.08.2009 27.05.2011 (Contract terminated in August 2013) re-awarded 17.02.2014 |
| 24 | Pallivasal KSEB/ Not Req./31.1.2007 2x30=60 | # Kerala SR | Civil, H&M works and E&M works | The work was awarded to M/s ESSAR – DEC – CPPL consortium as a single package and an agreement in this regard was executed on 31.01.2007. The contractual date of completion is 48 months i.e. 01.3.2011. E&M: Dongfang Electric Corporation, China (DEC) |  | 242.96 crs + US$57 million | 31.01.2007 # 01.03.2011 |
| 25 | Thottiyar KSEB 1x30 + 1x10= 40 MW | Kerala SR | Civil works | Dam, Water Conductor System, power House | M/s Coastal Projects Private Ltd- Chongqing Joint Venture, Hyderabad E&M: Chongqing, China | 44.23 | 22.12.2008 19.05.2012 |
|  |  |  | H&M works | Gates, erection, commissioning |  | 24.09 | 22.12.2008 19.05.2012 |
|  |  |  | E&M works | Planning, Engineering, Manufacture, Supply, Erection, testing & commissioning |  | 75.68 | 22.12.2008 19.05.2012 |
| 26 | New Umtru MePGCL 2x20=40MW | Meghalaya NER | Civil works |  | M/s ITD Cementation (India) Ltd. |  | # 20.12.2007 |
|  |  |  | E&M works | # Design, manuf., testing & commissioning of TG unit and auxiliaries | # M/s VATech Hydro India Ltd. |  | # 25.2.2009 |
| 27 | Vyasi UJVNL 2x60=120 MW | Uttra khand | Civil works | # Intake, Dam half portion of HRT 1.35 km. | # M/s. Gammon India Ltd. | # 317 Crs. |  |
|  |  |  |  | # Half posrtion of HRT 1.35 km, Surge Shaft, Penstock, Powerhouse, TRC | # M/s. NPCC Contract value | # 114.59 Crs. |  |
|  |  |  | E&M works |  | # M/s. BHEL | # 125 Crs. | # 26.03.2014 |
| 28 | Teesta Stage III Teesta Urja Ltd. 12.05.2006/ yet to be (FC) 6x200= 1200MW | Sikkim ER | Turn key execution award issued to the consortium of CKD-NEC-SEW-CGGC-ABIR-SABIR on 18.04.2007 with NEC (Navyug Engg. Co.) as lead partner. |  |  |  |  |
|  |  |  | # E&M works | # Generating units, and auxiliaries | M/s Andritz Hydro ,India | 1100.12 | # 18.10.2007 17.012012 |
|  | Private Sector |  |  |  |  |  |  |
| 29 | ## Ratle GVK Ratle HEP Pvt. Ltd. (GRHEPPL) ## 19-12-2012 4x205+1x30= 850 MW | # J&K NR | # Civil & HM # Works | # EPC contract for Civil & HM works including infrastructure works | GVK Projects & Technical Services Ltd. | # 2400 | # 20.07.2012 31.12.2017 |
|  |  |  | # E&M works | # EPC contract for E&M Works | # M/s Alstom, India | # 800 Cr. + # Euro 600000 + # USD 4200000 | # 31.12.2012 31.12.2017 |
|  |  |  | # Review of Design of EPC Contractors |  | # Lahmeyer International (India) Pvt. Ltd. | # 8.30 Cr. + Euro 580000 | # 23.03.2013 |
| 30 | Sorang Himachal Sorang Power Pvt. Ltd 2x50=100 MW | H.P. NR | Civil works | Power house, and other works | M/s NCC-Maytas- SSJV Consortium | 184 | 06/2007 |
|  |  |  | E&M works | Manufacturing., Supply, erection & commng. of TG units | M/s Voith Siemens, India | 146 | 06/2007 |
| 31 | Tidong-I M/s NSL Tidong Power Gen. Ltd. 2x50 = 100 MW | HP NR | Civil works | # Construction of River diversion, barrage, intake, Desilting basins, storage reservoir & HRT (RD 0 m -905 m) | M/s SCL Infratech Ltd. Hyderabad | 127.996 | 07.11.2008 06.11.2011 |
|  |  |  |  | Construction of HRT (RD 905 m-RD 5537 m) | M/s SCL Infratech Ltd. Hyderabad | 83.327 | 7.11.2008 09/2014 |
|  |  |  |  | Construction of HRT (RD 5537 m -RD 8537 m) | M/s Himalaya Construction (P) Ltd. | 31 | 07.07.2011 06.07.2015 |
|  |  |  |  | Construction of Surge Shaft, Pressure Shaft, Power House and Tail Race Channel | M/s Himalaya Construction (P) Ltd. | 40 | 07.07.2012 06.06.2015 |
|  |  |  | E&M works | # Supply, Installation, testing & commissioning of TG sets | M/s Alstom Projects, India | 84 | 28.02.2011 27.05.2013 |
| 32 | Tangnu Romai-I M/s Tangu Romai Power generation 2x22= 44 MW 30.11.2007 HPSEB | HP NR | Civil works | # Construction of Diversion Barrage, Intake, desilting, HRT, Surge Shaft, Penstok, Power House & Tail Race Channel | M/s Sai Urja Hydel Projects (P) Ltd., Shimla | 164.7 | 14.06.2010 06/2014 |
|  |  |  | E&M works | # Supply, installation, T&C of TG set, Switchyard equipment & associated auxiliaries | M/s Andritz Hydro, India | 56 | 17.04.2013 16.07.2015 |
| 33 | Bajoli Holi M/s GMR Bajoli Holi Hydro Power Pvt. Limited 31.12.2011 | HP NR | Civil works | # Lot-I & Lot-II All Major Civil Works | M/s Gammon India Ltd. | 369 +400 | 29.05.2013 30.11.2017 |
|  |  |  | E&M works | # E&M works | M/s. Alstom, India |  |  |
| 34 | ## Chanju-I M/s IA Energy 24.04.2010 3x12 = 36 MW | HP NR | Civil works | # Excavation of Barrage, River Diversion, Desilting arrangement, HRT (Package – I & II) & complete water conductor system | M/s Ashok Chauhan & Co., Shimla |  | 13.09.201 |
|  |  |  |  | # Excavation of Power House & Switchyard | M/s S.K.K. Mahajan Enterprise, Tissa, Distt. Chamba |  | 23.07.2011 |
|  |  |  |  | # Concreting/Lining works of River Diversion, Barrage & Power intake, desilting arrangement, HRT Package-I | M/s Him Hydro Joint Venture, Palampur, Distt. Kangra |  | 14.09.2011 |
|  |  |  |  | # Concrete lining of HRT Package-II | M/s Tuscon Engineers Pvt. Ltd., Kolkatta |  | 14.09.2011 |
|  |  |  |  | # Civil works of Power House, Switchyard & Valve House | M/s Him Hydro Joint Venture, Palampur, Distt. Kangra |  | 30.07.2011 |
|  |  |  | H&M works | # Design, Engineering, Manufacture, Farication & Erection of all hydro-mechamical gates & equipment | M/s ATB RIVA CALZONI India Pvt. Ltd., New Delhi |  | 06.08.2012 |
|  |  |  | E&M works | # Manufacturing., Supply, erection & commng. of TG units | B Fouress Pvt. Ltd., Banglore |  | 21.09.2011 |
| 35 | ## Phata Byung M/s Lanco 06.10.2008 2x38 MW = 76 MW | Uttarakhand NR | Civil works | # Dam, water conductor System, power House | Lanco Infratech Ltd. | 206 | 12.04.2008 07/2012 |
|  |  |  | H&M works | # Design, Engineering, Manufacture, Farication & Erectio,n of all hydro-mechamical equipment | M/s CIMMCO | 34 | 12.04.2008 08/2012 |
|  |  |  | E&M works | # Manufacturing., Supply, erection & commng. of TG units | M/s Alstom Project, India | 84 | 12.04.2008 08.2012 |
| 36 | ## Singoli Bhatwari M/s L&T 11.07.2008 3x33 MW = 99 MW |  | Civil works | # P-1 (Project Roads & Bridges) | M/s L&T DPBU | 34.2214 | 2.5.2008 --- |
|  |  |  |  | # P-2 (Dam/Barrage, Tunnels) |  | 381.7573 | 6.10.2008 --- |
|  |  |  |  | # P-39Power House, Tail Race Tunnel &Associated works) |  | 87.7931 | 20.6.2008 --- |
|  |  |  | H&M works | Supply, fabrication, Manufacturing, commissioning of Gates and Hoists | M/s General Mechanical Works Private Limited | 25.45 | 4.12.2011 12/2014 |
|  |  |  |  | Supply, fabrication, Manufacturing, commissioning of Steel Liners | NA |  |  |
|  |  |  | E&M works | # Generating units and auxiliaries | M/s Voith Hydro, India | EURO 1813069 + $ 3006954 + 963332930 + 122570000 | 15.06.2011 |
| 37 | Maheshwar, SMHPCL 12 96/ 29.9.2006 (FC) 10x40= 400MW | M. P. WR | Civil and HM works | # All civil works like dam, Power Dam, HRC, Penstock PH etc. | M/s SEW Construction –Prasad and Company Ltd. | 275.0 Crs. 22.02.97 | 22.02.1997 03/2005 |
|  |  |  | E&M works | # Manuf., Supply, erection & commng. of TG units | M/s BHEL | 470.5 Crs. + USD $ 11.74 M 18.05.2001 | 25.06.2007 10/ 2009 |
| 38 | Teesta-VI M/s Lanco Energy Pvt. Ltd. 27.12.2006/ 07/.2007(FC) 4x125= 500MW | Sikkim NER | Civil works | # Dam, Tunnel , Power House, Surge-Shaft, Intake | EPC contract To M/s Lanco Infratech Ltd. | 2260.00 | # 03/2007 10/2011 |
|  |  |  | H&M works | # Design Engineering Fabrication & Erection of Gates |  |  |  |
|  |  |  | # E&M works | # Main Plant # Generating units, and auxiliaries | M/s Alstom Projects, India | 568.00 | 04/2009 |
| 39 | Rangit-IV Jal Power Corp. Ltd. 06.07.2007/23.10.2007(FC) 3x40 MW= 120 | Sikkim NER | Civil works | # Dam, Intake, desilting chamber Package | # M/s Coastal Projects Pvt. Ltd | # 125.297 | # 01.02.2008 46 months |
|  |  |  |  | # HRT Package |  | 127.9 | # 22.11.2007 47 months |
|  |  |  |  | # Power House, Surge-Shaft, Pressure Shaft, Switchyad & Tail race Channel |  | # 77.789 | # 23.05.2008 48 months |
|  |  |  |  | # Road diversion Tunnel |  | # 7.938 | # 6.12.2007 4 months |
|  |  |  |  | Hill slopes Stabilization | # M/s Bumi Engineering | # 19.951 | # 16.01.2010 12 months |
|  |  |  | H&M works | Supply , Fabrication,Assembly, testing, painting, erection of various gates and their operating equipment including accessories, auxillaries etc. | # M/s Texmaco Rail & Engg. Ltd. | 36.7 |  |
|  |  |  | # E&M works | # Package-I # (Generating units and auxiliaries) | M/s Andritz Hydro, India | 111.11 | # 28.08.2009 # 12/2012 |
|  |  |  |  | # Package-II # (Balance of Plant) | M/s Siemens Ltd. | 53.9 | # 14.04.2011 04/2013 |
| 40 | Bhasmey Gati Infrastructure 2x25.5 = 51 MW | Sikkim NER | Civil works | # Dam, Tunnels , Power House, Surge Shaft, Pressure Shaft, Intake | # M/s Simplex Infrastructure Ltd. | # 160 | # 12.04.2010 11/2012 |
|  |  |  | H&M works | N.A. |  |  |  |
|  |  |  | E&M works | # Manufacturing., Supply, erection & commng. of TG units | # M/s Voith Hydro, India | # 93 | # 14.04.2010 10/2012 |
| 41 | Tashiding M/s Shiga Energy Private Ltd. 2x48.5 = 97 MW | Sikkim NER | # Civil # and # H&M works | # Dam, Tunnel , Power House, Surge Shaft, Pressure Shaft, Intake, # Design Engineering Farication & Erection of Gates etc. | M/s Bumi Geo Engineering Limited | 300 | # 28.03.2011 09/2013 |
|  |  |  | # E&M works | # Manufacturing., Supply, erection & commissioning of TG Units. | M/s Alstom Projects, India | 107.99 | # 21.05.2010 11/2012 |
| 42 | Dikchu Sneha KineticPower Projects Pvt. Ltd. 21.10.2011 2x48= 96 MW | Sikkim NER | # Civil works | # Dam, Tunnel , Power House, Surge Shaft, Pressure Shaft, Intake | M/s Haridwar Infrastructure Private Limited | 498 | # 22.03.2011 03/2014 07/2011 |
|  |  |  | # H&M works | # Design Engineering Fabrication & Erection of Gates |  |  |  |
|  |  |  | # E&M works | # Manufacturing, Supply, erection & commissioning of TG units | Alstom Projects, India |  |  |
| 43 | Rangit-II Sikkim Hydro Power Limited 2x33= 66 MW | Sikkim NER | # Civil &HM works | # EPC Contract | M/s Coastal Project Limited | 220.35 | # 13.12.2011 23.10.2013 |
|  |  |  | # E&M works |  | M/s. Gammon India Ltd. |  | # 24.03.2012 |
| 44 | Rongnichu Madhya Bharat Power Corporation Ltd. 2x48= 96 MW | Sikkim NER | # Civil works | # Barrage, Desilting Basin, Tunnel , Power House, Surge Shaft, Pressure Shaft, Intake etc. | M/s SEW Infrastructure Ltd. | 157.298 | # 07.04.2010 05.10.2013 |
|  |  |  | # E&M works | # Manufacturing., Supply, erection & commng. of TG units | M/s Voith Hydro, India | 101.100 | # 28.09.2011 |
| 45 | Panan Himagiri Hydro Energy Pvt. Ltd. 07.03.2011 4x75= 300 MW | Sikkim NER | # Civil works | # Coffer Dam, Diversion Tunnel, Dam, Desilting Basin, Power House, Surge Shaft, Pressure Shaft, Intake etc. | M/s Essar Projects (India) Ltd.. | 392.40 (Excl. cost of cement, Steel, explosives) | # 22.02.2014 21.02.2018 (48 months) |
|  |  |  | # E&M works | # Manufacturing., Supply, erection & commng. of TG units | Under Award |  |  |
| 46 | Gongri Dirang Energy Pvt. Ltd. 04.02.2013 2x72= 144 MW | Ar. Pradesh NER | # EPC # Ctrt. | # Planning, Engineering, Design and Construction of Civil, HM, E&M & Infrastructure works. | Patel Engineering Ltd, Mumbai | 989.589 | # 22.12.2011 # 19.11.2017 |
|  |  |  |  |  | # (42 months from date of start) State Pollution Control Board issued consent to establish in 19.05.2014 |  |  |
|  |  |  | # E&M works | # Manufacturing., Supply, erection & commng. of TG units | M/s Andritz Hydro Pvt. Ltd. |  | 13.12.2013 |