## Annex-III Plan progress
Chapter 2.2
Hydro Electric Projects for Benefits During 12th Plan- Plan Progress | [10 empty] | 31.12.2016
S. No. | Project Name | State | Developer | I. C. (No. x MW) | Year wise Cap. Addition |  |  |  |  | Slipping | Total | Likely Slippages
[5 empty] | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17
I. | As per 12th Plan Programme
A. | Commissioned
Central Sector
1 | Chamera-III | HP | NHPC | 3x77 | 231 | [5 empty] | 231
2 | Chutak | J&K | NHPC | 4x11 | 44 | [5 empty] | 44
3 | Teesta Low Dam- III | WB | NHPC | 4x33 | 99 | 33 |  |  |  |  | 132
4 | Uri-II | J&K | NHPC | 4x60 |  | 240 |  |  |  |  | 240
5 | Nimoo Bazgo | J&K | NHPC | 3x15 |  | 45 |  |  |  |  | 45
6 | Parabati- III | HP | NHPC | 4x130 |  | 390 | 130 |  |  |  | 520
7 | Rampur HEP | H.P. | SJVNL | 6x68.67 |  | 206 | 206 |  |  |  | 412
8 | Kol Dam HEP | H.P. | NTPC | 4x200 |  |  | 400 | 400 |  |  | 800
9 | Teesta Low Dam- IV | WB | NHPC | 4x40 |  |  |  | 80 | 80 |  | 160
| Sub Total: Central Sector |  |  |  | 374 | 914 | 736 | 480 | 80 |  | 2584
State Sector
10 | Bhawani Barrage-II | Tamil Nadu | TANGEDCO | 2x15 |  | 30 |  |  |  |  | 30
11 | Bhawani Barrage-III | Tamil Nadu | TANGEDCO | 2x15 | 15 | 15 |  |  |  |  | 30
12 | Myntdu-1 addl.Unit | Meghalaya | MePGCL | 1x42 | 42 | [5 empty] | 42
13 | Baglihar-II | J&K | JKPDC | 3x150 |  |  |  | 450 |  |  | 450
14 | Lower Jurala | Telengana | TSGENCO | 6x40 |  |  |  | 160 | 80 |  | 240
15a | Pulichintala | Telengana | TSGENCO | 4x30 |  |  |  |  | 30 |  | 30
16 | Kashang - I | H.P. | HPPCL | 1x65 |  |  |  |  | 65 |  | 65
17a | Kashang II & III | H.P. | HPPCL | 2x65 |  |  |  |  | 65 |  | 65
| Sub Total: State Sector |  |  |  | 57 | 45 |  | 610 | 240 |  | 952
Private Sector
18 | Budhil | HP | LANCO | 2x35 | 70 | [5 empty] | 70
19 | Chujachen | SIKKIM | GATI | 2x49.5 |  | 99 |  |  |  |  | 99
20 | Srinagar | Uttarakhand | AHPCo. Ltd. | 4x82.5 |  |  |  | 330 |  |  | 330
21 | Jorethang Loop | Sikkim | DANS Pvt. Ltd | 2x48 |  |  |  | 96 |  |  | 96
| Sub Total: Private Sector |  |  |  | 70 | 99 |  | 426 |  |  | 595
| Sub Total 'A': Commissioned |  |  |  | 501 | 1058 | 736 | 1516 | 320 |  | 4131
B. | Under Construction
Central Sector
22 | Pare HEP | Ar. P | NEEPCO | 2x55 | [5 empty] | 110 | 110
23 | Kameng HEP (300 MW-BE) | Ar. P | NEEPCO | 4x150 | [5 empty] | 600 | 600
24 | Subansiri Lower HEP | Ar. P | NHPC | 8x250 | [5 empty] | 1000 | 1000 | 1000
25 | Parbati-II HEP | H.P. | NHPC | 4x200 | [5 empty] | 800 | 800 | 800
26 | Kishan Ganga (BE) | J&K | NHPC | 3x110 | [5 empty] | 330 | 330
27 | Tuirial | Mizoram | NEEPCO | 2x30 | [5 empty] | 60 | 60
28 | Tapovan Vishnugad | Uttarakhand | NTPC | 4x130 | [5 empty] | 520 | 520 | 520
| Sub Total: Central Sector | [7 empty] | 0 | 3420 | 3420 | 2320
State Sector
15b | Pulichintala | Telengana | TSGENCO | 4x30 |  |  |  |  | 30 | 60 | 90
29 | Nagarjuna Sagar TR | AP | APGENCO | 2x25 |  |  |  |  | 50 |  | 50
30 | Uhl-III | H.P. | BVPC | 3x33.33 | [5 empty] | 100 | 100
31 | Sawra Kuddu | H.P. | HPPCL | 3x37 | [5 empty] | 111 | 111 | 111
17b | Kashang II & III | H.P. | HPPCL | 2x65 | [5 empty] | 65 | 65 | 130
32 | Sainj | H.P. | HPPCL | 2x50 |  |  |  |  | 100 |  | 100
33 | Thottiar | Kerala | KSEB | 1x30 + 1x10 | [5 empty] | 40 | 40 | 40
34 | Pallivasal | Kerala | KSEB | 2x30 | [5 empty] | 60 | 60 | 60
35 | New Umtru | Meghalaya | MePGCL | 2x20 |  |  |  |  | 20 | 20 | 40
36 | Teesta-III (600 MW- BE) | Sikkim | Teesta Urja | 6x200 |  |  |  |  | 1200 |  | 1200
| Sub Total: State Sector | [7 empty] | 1400 | 456 | 1856 | 341
Private Sector
37 | Tidong-I | H.P. | N S L Tidong Power Gen. Ltd | 2x50 | [5 empty] | 100 | 100
38 | Sorang | H.P. | Himachal Sorang Power Pvt. Ltd | 2x50 | [5 empty] | 100 | 100
39 | Tangnu Romai-I | H.P. | Tangnu Romai Power Gen. Ltd | 2x22 | [5 empty] | 44 | 44 | 44
40 | Maheshwar | MP | SMHPCL | 10x40 | [5 empty] | 400 | 400
41 | Bhasmey | Sikkim | GATI | 2x25.5 | [5 empty] | 51 | 51 | 51
42 | Rangit-IV | Sikkim | Jal Power | 3x40 | [5 empty] | 120 | 120 | 120
43 | Teesta-VI | Sikkim | LANCO | 4x125 | [5 empty] | 500 | 500 | 500
44 | Singoli Bhatwari | Uttarakhand | L & T | 3x33 | [5 empty] | 99 | 99 | 99
45 | Phata Byung | Uttarakhand | LANCO | 2x38 | [5 empty] | 76 | 76 | 76
| Sub Total: Private Sector | [7 empty] | 0 | 1490 | 1490 | 890
| Sub Total 'B': Under Construction | [7 empty] | 1400 | 5366 | 6766 | 3551
| Total- 12th Plan (A + B ) |  |  |  | 501 | 1058 | 736 | 1516 | 1720 | 5366 | 10897 | 3551
Likely in 12th Plan |  |  |  |  | 5531
II. | Outside from the 12th Plan Programme
A. | Commissioned
State Sector
1 | Jaldhaka | West Bengal | WBSEDCL | 4x9 | 9 | [5 empty] | 9
| Sub Total: State Sector |  |  |  | 9 | [5 empty] | 9 | 7102
| Total Commissioned (12th Plan) |  |  |  | 510 | 1058 | 736 | 1516 | 320 |  | 4140
B. | Under Construction
Private Sector
2 | Chanju | H.P. | IA Energy | 3x12 |  |  |  |  | 36 |  | 36
3 | Dikchu | Sikkim | Sneha Kinetic Power Projects Pvt. Ltd. | 2x48 |  |  |  |  | 96 |  | 96
4 | Tashiding | Sikkim | Shiga Energy Pvt. Ltd. | 2x48.5 |  |  |  |  | 97 |  | 97
| Sub Total: Private Sector | [7 empty] | 229 |  | 229 | 7102
| Total: Outside 12th Plan programme |  |  |  | 9 |  |  |  | 229 |  | 238
| Likely in 12th Plan |  |  |  | 510 | 1058 | 736 | 1516 | 1949
|  |  | Total: |  | 5769

## Annex-II Summary
Hydro Electric Projects for Benefits During 12th Plan- As Plan Progress
SUMMARY
As per 12th Plan Programme |  |  |  | As on 31-08-2016
|  | Central | State | Private | Total
A | Commissioned | 2584 | 952 | 595 | 4131
B | Under Construction | 3420 | 1856 | 1490 | 6766
| Total: (12th Plan A + B) | 6004 | 2808 | 2085 | 10897
| % age Ach: | 43.038 | 33.9031 | 28.5372 | 37.9095

## Project Details - Data Dump (hidden)
S. No. | Report | Project Name | Status | State | Developer | Sector | Fuel Type | Capacity (MW) | CIL till 2014-15 | beyond 2014-15 | BLOCK | IMP COAL | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17
1 | AS PER WORKING GROUP REPORT | Lower Jurala HEP | UC | A.P. | APGENCO | S | Hydro | 240 | [6 empty] | 120 | 120
2 | AS PER WORKING GROUP REPORT | Pulichintala HEP | UC | A.P. | APGENCO | S | Hydro | 120 | [7 empty] | 60 | 60
3 | AS PER WORKING GROUP REPORT | Sri Damodaram Sanjeevaiah TPP (Krishnapattnam TPP) U1,2 | UC | A.P. | APGENCO | S | Coal | 1600 | 560 | 560 |  | 480 |  |  |  | 800 | 800
4 | AS PER WORKING GROUP REPORT | Thamminapatnam TPP U3,4 | UC | A.P. | Meenakshi Energy Pvt. Ltd., | P | Coal | 700 | 490 |  |  | 210 |  | 350 | 350
5 | AS PER WORKING GROUP REPORT | Painampuram TPP U1,2 | UC | A.P. | Thermal Powertech Corporation Ltd. | P | Coal | 1320 | 462 | 462 |  | 396 |  |  |  | 660 | 660
6 | AS PER WORKING GROUP REPORT | Simhapuri TPP Ph-II U3,4 | UC | A.P. | Simhapuri Energy Pvt. Ltd.,Madhucan Projects | P | Coal | 300 |  |  |  | 300 |  | 150 | 150
1 | AS PER WORKING GROUP REPORT | Pare HEP | UC | Ar. P | NEEPCO | C | Hydro | 110 | [6 empty] | 110
2 | AS PER WORKING GROUP REPORT | Kameng HEP | UC | Ar. P | NEEPCO | C | Hydro | 600 | [8 empty] | 600
3 | AS PER WORKING GROUP REPORT | Subansiri Lower HEP | UC | Ar. P | NHPC | C | Hydro | 2000 | [8 empty] | 2000
1 | AS PER WORKING GROUP REPORT | NAMRUP CCGT | UC | Assam | APGCL | S | Gas | 100 | [6 empty] | 100
1 | AS PER WORKING GROUP REPORT | Muzaffarpur (Kanti) TPP U 3 | UC | Bihar | NTPC JV | C | Coal | 390 | 390 | [6 empty] | 195
2 | AS PER WORKING GROUP REPORT | Barh STPP-I U 1 | UC | Bihar | NTPC | C | Coal | 1980 | 660 | 1320 | [6 empty] | 660
3 | AS PER WORKING GROUP REPORT | Barh STPP-II U 1,2 | UC | Bihar | NTPC | C | Coal | 1320 |  |  | 1320 |  |  |  |  | 660 | 660
4 | AS PER WORKING GROUP REPORT | Nabinagar TPP U1-2 | UC | Bihar | NTPV JV | C | Coal | 1000 | 1000 | [6 empty] | 500
1 | AS PER WORKING GROUP REPORT | Sipat-I U 3 | UC | Chhattisgarh | NTPC | C | Coal | 660 | 660 |  |  |  | 660
2 | AS PER WORKING GROUP REPORT | Korba West St.III U5 | UC | Chhattisgarh | CSEB | S | Coal | 500 | 500 | [5 empty] | 500
3 | AS PER WORKING GROUP REPORT | Marwah TPP U1,2 | UC | Chhattisgarh | CSEB | S | Coal | 1000 |  |  | 1000 |  | 500 | 500
4 | AS PER WORKING GROUP REPORT | Avantha Bhandar TPP U1 | UC | Chhattisgarh | Korba West Power Company Ltd. | P | Coal | 600 | 600 |  |  |  |  | 600
5 | AS PER WORKING GROUP REPORT | Maurti Clean Coal & Power Ltd. U1 | UC | Chhattisgarh | Maurti Clean Coal & Power Ltd. | P | Coal | 300 |  | 300 |  |  |  | 300
6 | AS PER WORKING GROUP REPORT | Lanco Amarkantak U- 3,4 | UC | Chhattisgarh | LANCO Amarkantak Pvt Ltd | P | Coal | 1320 | 1320 | [6 empty] | 660 | 660
7 | AS PER WORKING GROUP REPORT | Uchpanda TPP U1-3 | UC | Chhattisgarh | R.K.M. POWERGEN PVT LTD, | P | Coal | 1080 | 720 | 180 | 180 |  |  | 360 | 360 | 360
8 | AS PER WORKING GROUP REPORT | Vandana Vidyut TPP U 2 | UC | Chattisgarh | Vandana Vidyut | P | Coal | 135 |  |  | 135 |  |  | 135
9 | AS PER WORKING GROUP REPORT | Darrampura TPP U1-3 | UC | Chhatisgarh | SKS Ispat and Power Ltd. | P | Coal | 900 |  | 900 |  |  |  |  | 600 | 300
10 | AS PER WORKING GROUP REPORT | Akaltara (Nariyara) TPP U 1-3 | UC | Chhattisgarh | KSK Mahanadi Power Company Limited | P | Coal | 2400 |  |  | 2400 |  |  |  | 600 | 600 | 600
1 | AS PER WORKING GROUP REPORT | KAPP U-3 & 4 | UC | Gujarat | NPC | C | Nuclear | 1400 | [8 empty] | 1400
2 | AS PER WORKING GROUP REPORT | Sikka TPP Extn. U3 | UC | Gujarat | GSECL | S | Coal | 500 |  |  |  | 500 |  |  |  | 250
3 | AS PER WORKING GROUP REPORT | Mundra UMPP, U 2-5 | UC | Gujarat | The Tata Power Company Ltd | P | Coal | 3200 |  |  |  | 3200 | 800 | 800 | 800 | 800
1 | AS PER WORKING GROUP REPORT | Parbati-II HEP | UC | H.P. | NHPC | C | Hydro | 800 | [8 empty] | 800
2 | AS PER WORKING GROUP REPORT | Rampur HEP | UC | H.P. | SJVNL | C | Hydro | 412 | [5 empty] | 412
3 | AS PER WORKING GROUP REPORT | Kol Dam HEP | UC | H.P. | NTPC | C | Hydro | 800 | [5 empty] | 800
4 | AS PER WORKING GROUP REPORT | Kashang - I HEP | UC | H.P. | Himachal Pradesh Power Corp Ltd. | S | Hydro | 65 | [6 empty] | 65
5 | AS PER WORKING GROUP REPORT | Uhl-III HEP | UC | H.P. | BVPC | S | Hydro | 100 | [6 empty] | 100
6 | AS PER WORKING GROUP REPORT | Sawara Kuddu HEP | UC | H.P. | HPPCL | S | Hydro | 111 | [6 empty] | 111
7 | AS PER WORKING GROUP REPORT | Kashang II & III HEP | UC | H.P. | HPPCL | S | Hydro | 130 | [7 empty] | 130
8 | AS PER WORKING GROUP REPORT | Sainj HEP | UC | H.P. | HPPCL | S | Hydro | 100 | [6 empty] | 100
9 | AS PER WORKING GROUP REPORT | Tidong-I HEP | UC | H.P. | N S L Tidong Power Generation Ltd | P | Hydro | 100 | [7 empty] | 100
10 | AS PER WORKING GROUP REPORT | Sorang HEP | UC | H.P. | Himachal Sorang Power Pvt. Ltd | P | Hydro | 100 | [5 empty] | 100
11 | AS PER WORKING GROUP REPORT | Tangnu Romai-I HEP | UC | H.P. | Tangnu Romai Power Generation Ltd | P | Hydro | 44 | [7 empty] | 44
1 | AS PER WORKING GROUP REPORT | Mahatmi Gandhi Jhajjar STPP U2 | COMND | Haryana | China Light Power | P | Coal | 660 | 660 |  |  |  | 660
1 | AS PER WORKING GROUP REPORT | Kishan Ganga HEP | UC | J & K | NHPC | C | Hydro | 330 | [8 empty] | 330
2 | AS PER WORKING GROUP REPORT | Baglihar-II HEP | UC | J & K | J&K State Power Development Corp. Ltd. | S | Hydro | 450 | [8 empty] | 450
1 | AS PER WORKING GROUP REPORT | Bokaro TPP A Exp U1 | UC | Jharkhand | DVC | C | Coal | 500 | 500 | [7 empty] | 500
2 | AS PER WORKING GROUP REPORT | MATA SHRI USHA TPP Ph-I U 1,2 | UC | Jharkhand | Corporate Power Ltd. | P | Coal | 540 | 540 |  |  |  | 270 | 270
3 | AS PER WORKING GROUP REPORT | Adhunik Power & Natural Resources Ltd TPP U1,2 | UC | Jharkhand | Adhunik Power & Natural Resources Ltd. | P | Coal | 540 | 270 |  | 270 |  | 270 | 270
1 | AS PER WORKING GROUP REPORT | Thottiar HEP | UC | Kerala | KSEB | S | Hydro | 40 | [7 empty] | 40
2 | AS PER WORKING GROUP REPORT | Pallivasal HEP | UC | Kerala | KSEB | S | Hydro | 60 | [6 empty] | 60
1 | AS PER WORKING GROUP REPORT | VINDHYACHAL STPP St-IV U-11,12 | UC | MP | NTPC | C | Coal | 1000 | 1000 |  |  |  | 500 | 500
2 | AS PER WORKING GROUP REPORT | SATPURA TPP EXT U-10,11 | UC | MP | MPGENCO | S | Coal | 500 | 500 |  |  |  | 250 | 250
3 | AS PER WORKING GROUP REPORT | Annupur TPP Ph-I U1,2 | UC | MP | MB Power ( Madhya Pradesh ) Ltd. | P | Coal | 1200 | 600 | 600 | [5 empty] | 600 | 600
4 | AS PER WORKING GROUP REPORT | Bina TPP U 2 | UC | MP | Bina Power Supply Comp. Ltd, Jaypee Group | P | Coal | 250 | 250 |  |  |  |  | 250
5 | AS PER WORKING GROUP REPORT | Sasan UMPP,U 1-2 | UC | MP | Reliance Power Ltd. | P | Coal | 2640 |  |  | 2640 |  |  |  | 660 | 660
6 | AS PER WORKING GROUP REPORT | NIGRIE TPP U1 | UC | MP | Jaypee Group | P | Coal | 660 |  |  | 660 |  |  |  |  | 660
7 | AS PER WORKING GROUP REPORT | Mahan TPP U1 | UC | MP | Essar Power | P | Coal | 1200 | No Coal | [6 empty] | 600
1 | AS PER WORKING GROUP REPORT | MAUDA TPP U1 | COMND | Maharashtra | NTPC | C | Coal | 500 | 500 |  |  |  | 500
2 | AS PER WORKING GROUP REPORT | MAUDA TPP U2 | UC | Maharashtra | NTPC | C | Coal | 500 | 500 |  |  |  |  | 500
3 | AS PER WORKING GROUP REPORT | Chandrapur Ext. U8 | UC | Maharashtra | MAHGENCO | S | Coal | 1000 |  |  | 1000 |  |  |  |  | 500
4 | AS PER WORKING GROUP REPORT | Koradi TPP Ext U8 | UC | Maharashtra | MAHGENCO | S | Coal | 1980 |  |  | 1980 |  |  |  |  | 660
5 | AS PER WORKING GROUP REPORT | Parli Unit-8 | UC | Maharashtra | MAHGENCO | S | Coal | 250 |  |  | 250 |  |  |  | 250
6 | AS PER WORKING GROUP REPORT | India Bulls- Amravati TPP Ph-I,U1-4 | UC | Maharashtra | India Bulls Realtech Limited | P | Coal | 1350 | 1350 |  |  |  |  | 540 | 270 | 270
7 | AS PER WORKING GROUP REPORT | India Bulls - Nasik TPP Ph-I,U1-4 | UC | Maharashtra | India Bulls Realtech Limited | P | Coal | 1350 | 1350 |  |  |  |  | 540 | 270 | 270
8 | AS PER WORKING GROUP REPORT | DHARIWAL INFRASTRUCTURE (P) Ltd TPP U1,2 | UC | Maharashtra | DHARIWAL INFRASTRUCTURE (P) LTD | P | Coal | 600 | 600 |  |  |  |  | 600
9 | AS PER WORKING GROUP REPORT | EMCO WARORA Ph-I | UC | Maharashtra | GMR | P | Coal | 300 | 300 |  |  |  | 300
10 | AS PER WORKING GROUP REPORT | EMCO WARORA- Ph-II | UC | Maharashtra | GMR | P | Coal | 300 | 300 |  |  |  |  | 300
11 | AS PER WORKING GROUP REPORT | Butibori TPP Ph -II U-1 | UC | Maharashtra | Vidarbha Industries Power Ltd | P | Coal | 300 | 300 |  |  |  | 300
12 | AS PER WORKING GROUP REPORT | Lanco Mahanadi, Vidarbha TPP U1 | UC | Maharashtra | Lanco Mahanadi | P | Coal | 1320 | 1320 | [7 empty] | 660
13 | AS PER WORKING GROUP REPORT | TIRODA TPP PH-I U2 | UC | Maharashtra | ADANI POWER | P | Coal | 660 | 660 |  |  |  | 660
14 | AS PER WORKING GROUP REPORT | Tiroda TPP Ph-II, U1 | UC | Maharashtra | Adani Power | P | Coal | 660 | No Coal |  |  |  | 660
1 | AS PER WORKING GROUP REPORT | New Umtru HEP |  | Meghalaya | MeECL | S | Hydro | 40 | [6 empty] | 40
1 | AS PER WORKING GROUP REPORT | Tuirial HEP | UC | Mizoram | NEEPCO | C | Hydro | 60 | [8 empty] | 60
1 | AS PER WORKING GROUP REPORT | DERANG TPP U1,2 | UC | Orissa | Jindal India Thermal Power Ltd | P | Coal | 1200 | 600 | 600 |  |  |  | 600 | 600
2 | AS PER WORKING GROUP REPORT | Ind Barath Energy Pvt. Ltd. TPP U1,2 | UC | Orissa | Ind. Barath power (Utkal) Ltd. | P | Coal | 700 | 700 |  |  |  |  | 350 | 350
3 | AS PER WORKING GROUP REPORT | Lanco Babandh - Dhenkanal U-1 | UC | Orissa | Lanco Babandh | P | Coal | 660 | 660 | [5 empty] | 660
4 | AS PER WORKING GROUP REPORT | K.V.K. Nilachal TPP U 1-3 | UC | Orissa | K.V.K. Nilachal Power Pvt. Ltd. | P | Coal | 1050 | 1050 |  |  |  |  | 350 | 350 | 350
5 | AS PER WORKING GROUP REPORT | Kamalanga TPP U1-3 | UC | Orissa | GMR Energy | P | Coal | 1050 | 500 |  | 550 |  |  | 700 | 350
1 | AS PER WORKING GROUP REPORT | TALWANDI SABO TPP U1,2 | UC | Punjab | Vedanta | P | Coal | 1320 | 1320 |  |  |  |  | 660 | 660
2 | AS PER WORKING GROUP REPORT | Goindwal Sahib TPP U1 | UC | Punjab | GVK Industries | P | Coal | 270 |  |  | 270 |  |  | 270
1 | AS PER WORKING GROUP REPORT | RAPP U 7 & 8 | UC | Rajasthan | NPC | C | Nuclear | 1400 | [8 empty] | 1400
2 | AS PER WORKING GROUP REPORT | Kalisindh TPS U1 | UC | Rajasthan | RRVUNL | S | Coal | 1200 |  |  | 1200 |  |  |  |  | 600
3 | AS PER WORKING GROUP REPORT | Chhabra TPS Extn U3,4 | UC | Rajasthan | RRVUNL | S | Coal | 500 |  |  | 500 |  |  |  | 250 | 250
4 | AS PER WORKING GROUP REPORT | RAMGARH | UC | Rajasthan | RRVUNL | S | Gas | 160 |  |  |  |  | 160
1 | AS PER WORKING GROUP REPORT | Bhasmey HEP | UC | Sikkim | Gati Infrastructure Ltd. | P | Hydro | 51 | [6 empty] | 51
2 | AS PER WORKING GROUP REPORT | Jorethang Loop HEP | UC | Sikkim | M/s. DANS Pvt. Ltd | P | Hydro | 96 | [6 empty] | 96
3 | AS PER WORKING GROUP REPORT | Rangit-IV HEP | UC | Sikkim | Jal Power Corp. Ltd. | P | Hydro | 120 | [6 empty] | 120
4 | AS PER WORKING GROUP REPORT | Teesta-VI HEP | UC | Sikkim | M/s. Lanco Energy Pvt. Ltd. | P | Hydro | 500 | [7 empty] | 500
5 | AS PER WORKING GROUP REPORT | Teesta-III HEP | UC | Sikkim | Teesta Urja | P | Hydro | 600 | [6 empty] | 600
1 | AS PER WORKING GROUP REPORT | Vallur TPP U 3 | UC | TN | NTPC/TNEB JV | C | Coal | 500 | 500 | [5 empty] | 500
2 | AS PER WORKING GROUP REPORT | Tuticorin TPP JV U1,2 | UC | TN | NPTL (NLC JV) | C | Coal | 1000 |  | 1000 |  |  |  |  | 500 | 500
3 | AS PER WORKING GROUP REPORT | Mutiara TPP, Tuticorin, Melamaruthur U1,2 | UC | TN | COASTAL ENERGEN PVT LTD | P | Coal | 1200 |  | 360 |  | 840 |  | 1200
1 | AS PER WORKING GROUP REPORT | TRIPURA GAS | UC | Tripura | ONGC | C | Gas | 726.6 |  |  |  |  | 363.3 | 363.3
2 | AS PER WORKING GROUP REPORT | MONARCHAK Gas | UC | Tripura | NEEPCO | C | Gas | 100 | [7 empty] | 100
1 | AS PER WORKING GROUP REPORT | RIHAND STPP-III, U5,6 | UC | UP | NTPC | C | Coal | 1000 | 1000 |  |  |  | 500 | 500
2 | AS PER WORKING GROUP REPORT | ANPARA-D TPP U 1 | UC | UP | UPRVUNL | S | Coal | 1000 | 1000 | [6 empty] | 500
3 | AS PER WORKING GROUP REPORT | BARA TPP U1 | UC | UP | Jaypee Group | P | Coal | 1320 |  | 1320 | [5 empty] | 660
1 | AS PER WORKING GROUP REPORT | Tapovan Vishnugad HEP | UC | Uttarakhand | NTPC | C | Hydro | 520 | [7 empty] | 520
2 | AS PER WORKING GROUP REPORT | Singoli Bhatwari HEP | UC | Uttarakhand | L & T | P | Hydro | 99 | [7 empty] | 99
3 | AS PER WORKING GROUP REPORT | Phata Byung HEP | UC | Uttarakhand | Lanco Energy Pvt. Ltd. | P | Hydro | 76 | [5 empty] | 76
4 | AS PER WORKING GROUP REPORT | Srinagar HEP | UC | Uttara-khand | AHPCo. Ltd. | P | Hydro | 330 | [5 empty] | 330
1 | AS PER WORKING GROUP REPORT | DPL TPP U 8 | UC | WB | DPL | S | Coal | 250 | 250 | [5 empty] | 250
1 | ADDITIONAL PROJECTS | NAGARJUNA SAGAR TR | UC | AP | APGENCO | S | HYDRO | 50 | [6 empty] | 50
2 | ADDITIONAL PROJECTS | BHAVANAPADDU TPP U-1,2 | UC | AP | East Coast Energy | P | Coal | 1320 | 924 |  |  | 396 |  |  | 660 | 660
3 | ADDITIONAL PROJECTS | HINDUJA VIZAG U-1 | UC | AP | HINDUJA | P | Coal | 1050 |  | 1040 | [5 empty] | 525
4 | ADDITIONAL PROJECTS | Thamminapatnam TPP I U 1,2 | UC | AP | Meenakshi Energy Pvt. Ltd., | P | Coal | 300 |  |  |  | 300 | 300
5 | ADDITIONAL PROJECTS | Simhapuri TPP Ph-I, U 2 | UC | AP | Simhapuri Energy Pvt. Ltd., | P | Coal | 150 |  |  |  | 150 | 150
1 | ADDITIONAL PROJECTS | BONGAIGAON TPP U 1,2 | UC | ASSAM | NTPC | C | COAL | 500 | 500 | [6 empty] | 500
1 | ADDITIONAL PROJECTS | Kasaipalli TPP U 2 | UC | Chhattisgarh | ACB India | P | Coal | 135 | Washery reject |  |  |  | 135
2 | ADDITIONAL PROJECTS | Swastik Korba U 1 | UC | Chhattisgarh | ACB India | P | Coal | 25 | Washery reject |  |  |  | 25
3 | ADDITIONAL PROJECTS | Vandana Vidyut TPP U 1 | UC | Chhattisgarh | Vandana Vidyut | P | Coal | 135 | 135 |  |  |  | 135
4 | ADDITIONAL PROJECTS | Balco U-1,2 | UC | Chhattisgarh |  | P | COAL | 600 | 600 |  |  |  |  | 600
5 | ADDITIONAL PROJECTS | ATHENA SINGHTARAI U-1,2 | UC | Chhattisgarh |  | P | COAL | 1200 | 600 |  | 600 |  |  |  | 600 | 600
6 | ADDITIONAL PROJECTS | D B POWER U-1,2 | UC | Chhattisgarh | D B GROUP | P | COAL | 1200 |  | 600 | 600 |  |  |  | 600 | 600
7 | ADDITIONAL PROJECTS | RAIGARH JINDAL U-1,2 | UC | Chhattisgarh | JINDAL POWER | P | COAL | 1200 |  | 1200 | [5 empty] | 600 | 600
8 | ADDITIONAL PROJECTS | TRN ENERGY U-1,2 | UC | Chhattisgarh |  | P | COAL | 600 |  | 600 |  |  |  |  | 600
9 | ADDITIONAL PROJECTS | Uchpanda TPP U 4 | UC | Chhattisgarh | R.K.M. POWERGEN PVT LTD, | P | Coal | 360 |  |  | 360 |  |  |  |  | 360
10 | ADDITIONAL PROJECTS | RAIKHEDA TPP U-1 | UC | Chhattisgarh |  | P | Coal | 1370 | No Coal | [6 empty] | 685
11 | ADDITIONAL PROJECTS | Darrampura TPP U 4 | UC | Chhatisgarh | SKS Ispat and Power Ltd. | P | Coal | 300 |  |  | 300 |  |  |  |  | 300
13 | ADDITIONAL PROJECTS | RATIJA TPP | UC | Chhattisgarh |  | P | Coal | 50 | Washery reject |  |  |  |  | 50
1 | ADDITIONAL PROJECTS | PRAGATI-III (BAWANA) | UC | DELHI | PPCL | S | Gas | 750 |  |  |  |  | 250 | 500
1 | ADDITIONAL PROJECTS | UKAI EXT U6 | UC | GUJ | GSECL | S | COAL | 500 |  |  | 500 |  | 490
2 | ADDITIONAL PROJECTS | PIPAVAV JV CCGT Block-1,2 | UC | GUJ | GSECL | S | Gas | 702 |  |  |  |  | 351 | 351
3 | ADDITIONAL PROJECTS | Bhavnagar Lignite U-1,2 | UC | GUJ | Bhavnagar Energy | S | Lignite | 500 | [6 empty] | 250 | 250
4 | ADDITIONAL PROJECTS | Salaya TPP U 2 | UC | GUJ | Essar Power | P | Coal | 600 |  |  |  | 600 | 600
1 | ADDITIONAL PROJECTS | INDIRA GANDHI TPP (JHAJJAR) JV U-3 | UC | HAR | NTPC | C | COAL | 500 | 500 |  |  |  | 500
1 | ADDITIONAL PROJECTS | CHAMERA-III | UC | HP | NHPC | C | HYDRO | 231 |  |  |  |  | 231
2 | ADDITIONAL PROJECTS | PARBATI - III | UC | HP | NHPC | C | HYDRO | 520 |  |  |  |  | 130 | 390
3 | ADDITIONAL PROJECTS | BUDHIL | UC | HP | LANCO | P | HYDRO | 70 |  |  |  |  | 70
1 | ADDITIONAL PROJECTS | URI-II | UC | J&K | NHPC | C | HYDRO | 240 |  |  |  |  | 240
2 | ADDITIONAL PROJECTS | NIMOO BAZGO | UC | J&K | NHPC | C | HYDRO | 45 | [5 empty] | 45
3 | ADDITIONAL PROJECTS | CHUTAK | UC | J&K | NHPC | C | HYDRO | 44 |  |  |  |  | 44
1 | ADDITIONAL PROJECTS | KODERMA U2 | UC | JHAR | DVC | C | COAL | 500 | 500 |  |  |  | 500
1 | ADDITIONAL PROJECTS | TIRODA TPP PH-I U 1 | UC | MAH | ADANI POWER | P | COAL | 660 | 660 |  |  |  | 660
2 | ADDITIONAL PROJECTS | Bela TPP U 1 | UC | MAH | IEPL | P | Coal | 270 | 270 |  |  |  | 270
3 | ADDITIONAL PROJECTS | TIRODA TPP PH-II U 2,3 | UC | MAH | ADANI POWER | P | COAL | 1320 | NO COAL |  |  |  |  | 1320
1 | ADDITIONAL PROJECTS | MYNTDU St-I ADDL UNIT | UC | MEGH | MeSEB | S | HYDRO | 42 |  |  |  |  | 42
1 | ADDITIONAL PROJECTS | MAHESHWAR 1-10 | UC | MP | SMHPCL | P | HYDRO | 400 | [5 empty] | 240 | 160
2 | ADDITIONAL PROJECTS | Bina TPP U 1 | UC | MP | Bina Power Supply Company Ltd., Jaypee Group | P | Coal | 250 | 250 |  |  |  | 250
3 | ADDITIONAL PROJECTS | JHABUA U-1 | UC | MP | JHABUA POWER | P | Coal | 600 | 600 | [5 empty] | 600
6 | ADDITIONAL PROJECTS | D B POWER SIDHI | UC | MP | DB GROUP | P | Coal | 660 |  | 660 | [5 empty] | 660
1 | ADDITIONAL PROJECTS | Sterlite TPP U 4 | COMND | Orissa | Sterlite Energy | P | Coal | 600 |  |  | 600 |  | 600
2 | ADDITIONAL PROJECTS | Lanco Babandh - Dhenkanal U-2 | UC | Orissa | Lanco Babandh | P | Coal | 660 |  |  | 660 | [5 empty] | 660
3 | ADDITIONAL PROJECTS | MONNET MALIBRAHMINI | UC | Orissa | MONNET GROUP | P | Coal | 1050 |  | 525 | 525 |  |  |  | 525 | 525
1 | ADDITIONAL PROJECTS | NABHA | UC | PUNJAB |  | P | COAL | 1400 | 700 | 700 | [5 empty] | 700
2 | ADDITIONAL PROJECTS | Goindwal Sahib TPP U 2 | UC | Punjab | GVK Industries | P | Coal | 270 |  |  | 270 |  |  |  | 270
1 | ADDITIONAL PROJECTS | JALLIPA LIGNITE U 5-8 | UC | RAJ | RAJ WEST POWER | P | LIGNITE | 540 |  |  |  |  | 135 | 135 | 270
1 | ADDITIONAL PROJECTS | TEESTA III | UC | SIKKIM | TEESTA URJA | P | HYDRO | 600 | [6 empty] | 600
2 | ADDITIONAL PROJECTS | CHUJACHEN | UC | SIKKIM | GATI | P | HYDRO | 99 | [5 empty] | 99
1 | ADDITIONAL PROJECTS | BHAWANI BARRAGE II & III | UC | TN | TNEB | S | HYDRO | 60 |  |  |  |  | 45 | 15
2 | ADDITIONAL PROJECTS | VALLUR (ENNORE) JV U 2 | UC | TN | NTPC | C | COAL | 500 | 500 |  |  |  | 500
3 | ADDITIONAL PROJECTS | NEYVELI - II LIG U2 | UC | TN | NLC | C | LIGNITE | 250 | [5 empty] | 250
4 | ADDITIONAL PROJECTS | METTUR EXT U1 | UC | TN | TNEB | S | COAL | 600 | 600 |  |  |  | 600
5 | ADDITIONAL PROJECTS | NORTH CHENNAI EXT U1,2 | UC | TN | TNEB | S | COAL | 1200 | 1200 |  |  |  | 600 | 600
6 | ADDITIONAL PROJECTS | KUDANKULAM U 1,2 | UC | TN | NPC | C | NUCLEAR | 2000 |  |  |  |  | 2000
7 | ADDITIONAL PROJECTS | PFBR(Kalapakkam) | UC | TN | NPC | C | NUCLEAR | 500 | [6 empty] | 500
1 | ADDITIONAL PROJECTS | PARICHHA EXT U-5,6 | UC | UP | UPRVUNL | S | COAL | 500 | 500 |  |  |  | 500
2 | ADDITIONAL PROJECTS | HARDUAGANJ EXT U-9 | UC | UP | UPRVUNL | S | COAL | 250 | 250 |  |  |  | 250
1 | ADDITIONAL PROJECTS | TEESTA LOW DAM-III | UC | WB | NHPC | C | HYDRO | 132 | [5 empty] | 132
2 | ADDITIONAL PROJECTS | TEESTA LOW DAM-IV | UC | WB | NHPC | C | HYDRO | 160 | [6 empty] | 160
3 | ADDITIONAL PROJECTS | RAGHUNATHPUR PH-I U1,2 | UC | WB | DVC | C | COAL | 1200 |  |  | 1200 |  |  | 1200
4 | ADDITIONAL PROJECTS | HALDIA | UC | WB | CESC | P | COAL | 600 | 300 | 300 | [5 empty] | 300