## Ch 5
CHAPTER- 5
Sanctioned Hydro Projects for 12th Plan & Beyond
(Excluding projects under Ministry of New & Renewable Energy)
Sl. | Name of Scheme | State | I.C. | Benefits | Date of | Likely
No. |  |  | (No. x MW) | (MW) | Approval | Commng.
A. | Hydro Capacity as per Programme of 12th Plan
i) | Commissioned during 12th Plan
Commissioned during 2012-13
Central Sector
1 | Chamera-III (NHPC) | H.P. | 3x77 | 231 | 01.09.05
2 | Chutak (NHPC) | J&K | 4x11 | 44 | 24.08.06
3a | Teesta Low Dam-III (NHPC) | W.B. | 4x33 | 99 | 30.10.03
| Sub- total (Central Sector) : |  |  | 374
State Sector
4a | Bhawani Barrage III (TANGEDCO) | T.N. | 2x15 | 15 | 27.03.02
5 | Myntdu (MeECL) | Meghalaya | 2x42+ 1x42 | 42 | 09.06.03
| Sub- total (State Sector) : |  |  | 57
# | Jaldhaka (WBSEDCL) | W.B. | 4x9 | 9 | 08.10.12 | Outside 12th plan programme
Private Sector
6 | Budhil (LANCO Green Power) | H.P. | 2x35 | 70 | 02.06.05
| Sub- total (Private Sector) : |  |  | 70
| Total Commissioned 2012-13 |  |  | 501
Commissioned during 2013-14
Central Sector
3b | Teesta Low Dam-III (NHPC) | W.B. | 4x33 | 33 | 30.10.03
7 | Uri-II (NHPC) | J&K | 4x60 | 240 | 01.09.05
8 | Nimoo Bazgo (NHPC) | J&K | 3x15 | 45 | 24.08.06
9a | Parabati-III (NHPC) | H.P. | 4x130 | 390 | 09.11.05
10a | Rampur (SJVNL) | H.P. | 6x68.67 | 206 | 25.01.07
| Sub- total (Central Sector) : |  |  | 914
State Sector
11 | Bhawani Barrage II (TANGEDCO) | T.N. | 2x15 | 30 | 11.06.99
4b | Bhawani Barrage III (TANGEDCO) | T.N. | 2x15 | 15 | 27.03.02
| Sub- total (State Sector) : |  |  | 45
Private Sector
12 | Chujachen (Gati Infrastructure) | Sikkim | 2x49.5 | 99 | 30.11.04
| Sub- total (Private Sector) : |  |  | 99
| Total Commissioned 2013-14 |  |  | 1058
Commissioned during 2014-15
Central Sector
9b | Parabati-III (NHPC) | H.P. | 4x130 | 130 | 09.11.05
10b | Rampur (SJVNL) | H.P. | 6x68.67 | 206 | 25.01.07
13a | Kol Dam (NTPC) | H.P. | 4x200 | 400 | 28.10.02
| Sub- total (Central Sector) : |  |  | 736
| Total Commissioned 2014-15 |  |  | 736
Commissioned during 2015-16
Central Sector
13b | Kol Dam (NTPC) | H.P. | 4x200 | 400 | 28.10.02
14a | Teesta Low Dam-IV (NHPC) | W.B. | 4x40 | 80 | 30.09.05
| Sub- total (Central Sector) : |  |  | 480
State Sector
15 | Baglihar- II (JKPDC | J&K | 3x150 | 450 | 19.03.12
16a | Lower Jurala (TSGENCO) | Telangana | 6x40 | 160 | July, 2007
| Sub- total (State Sector) : |  |  | 610
Private Sector
17 | Shrinagar (AHPC) | Uttarakhand | 4x82.5 | 330 | 14.06.2000
18 | Jorethang Loop (DANS Energy) | Sikkim | 2x48 | 96 | 26.08.06
| Sub- total (Private Sector) : |  |  | 426
| Total Commissioned 2015-16 |  |  | 1516
Commissioned during 2016-17 (Upto 31.12.2016)
Central Sector
14b | Teesta Low Dam-IV (NHPC) | W.B. | 4x40 | 80 | 30.09.05
| Sub- total (Central Sector) : |  |  | 80
State Sector
19 | Kashang -I (HPPCL) | H.P. | 1x65 | 65 | Nov, 01
16b | Lower Jurala (TSGENCO) | Telangana | 6x40 | 80 | July, 2007
20*P | Kashang -II & III (HPPCL) | H.P. | 2x65 | 65 | -
21*P | Pulichintala (TSGENCO) | Telangana | 4x30 | 30 | 25.04.07
| Sub- total (State Sector) : |  |  | 240
| Total Commissioned 2016-17 |  |  | 320
| Total (i) 12th Plan-Commissioned (up to 31.12.2016) |  |  | 4131
ii) | Under Execution
Central Sector
1 | Kishanganga (NHPC) | J&K | 3x110 | 330 | 20.07.07 | 2017-18
2 | Parbati St. II (NHPC) | H.P. | 4x200 | 800 | 11.09.02 | 2018-19
3 | Tapovan Vishnugad (NTPC) | Uttarakhand | 4x130 | 520 | 11/2006 | 2019-20
4a | Subansiri Lower (NHPC) | Ar. Pr./Assam | 8x250 | 1000 | 09.09.03 | 2020-21 *R
5 | Kameng (NEEPCO) | Ar. Pr. | 4x150 | 600 | 02.12.04 | 2017-18 *S
6 | Pare (NEEPCO) | Ar. Pr. | 2x55 | 110 | 04.12.08 | 2017-18 *S
7 | Tuirial (NEEPCO) | Mizoram | 2x30 | 60 | 14.01.11 | 2017-18
| Sub- total (Central Sector) : |  |  | 3420
- 17 -
State Sector
8 | Uhl-III (BVPCL) | H.P. | 3x33.33 | 100 | 19.09.02 | 2017-18
9*P | Kashang -II & III (HPPCL) | H.P. | 2x65 | 65 | - | 2019-20 *R
10 | Sainj (HPPCL) | H.P. | 2x50 | 100 | 29.12.10 | 2016-17
11 | Swara Kuddu (HPPCL) | H.P. | 3x37 | 111 | 10.11.04 | 2018-19
12 | Nagarujana Sagar TR (APGENCO) | A.P. | 2x25 | 50 | 17.01.05 | 2016-17
13*P | Pulichintala (TSGENCO) | Telangana | 4x30 | 90 | 25.04.07 | 2016-18
14 | Pallivasal (KSEB) | Kerala | 2x30 | 60 | Jan., 07 | 2019-20 *R
15 | Thottiyar (KSEB) | Kerala | 1x30+1x10 | 40 | 05.06.08 | 2019-20 *R
16 | New Umtru (MePGCL) | Meghalaya | 2x20 | 40 | Dec., 07 | 2016-18 *S
17 | Teesta St. III (Teesta Urja) | Sikkim | 6x200 | 1200 | 12.05.06 | 2016-17
| Sub- total (State Sector) : |  |  | 1856
Private Sector
18 | Sorang (Himachal Sorang Power) | H.P. | 2x50 | 100 | 09.06.06 | 2017-18 *R
19 | Tidong-I (NSL Power) | H.P. | 2x50 | 100 | 28.07.06 | 2017-18
20 | Tangnu Romai- I (NSL Power) | H.P. | 2x22 | 44 | 30.11.07 | 2018-19 *R
21 | Phata Byung (LANCO) | Uttarakhand | 2x38 | 76 | 06.10.08 | 2019-20 *A
22 | Singoli Bhatwari (L&T) | Uttarakhand | 3x33 | 99 | 11.07.08 | 2020-21 *A
23 | Maheshwar (SMHPCL) | M.P. | 10x40 | 400 | 30.12.96 | 2017-19 *R
24 | Teesta St. VI (LANCO) | Sikkim | 4x125 | 500 | 27.12.06 | 2021-22 *R
25 | Rangit-IV (JAL Power) | Sikkim | 3x40 | 120 | 06.07.07 | 2019-20 *R
26 | Bhasmey (GATI Infrstructure) | Sikkim | 2x25.5 | 51 | Dec-08 | 2019-20
| Sub- total (Private Sector) : |  |  | 1490
| Total ii: 12th Plan-Under execution |  |  | 6766
| Total 'A': 12th Plan (Comm. + Under Execution # ) |  |  | 10897
SUMMARY- 12th Plan
|  | Central | State | Private | Total
| Commissioned | 2584 | 952 | 595 | 4131
| Under Construction | 3420 | 1856 | 1490 | 6766
| Total: (12th Plan) # | 6004 | 2808 | 2085 | 10897
| Out of Programme Commissioning # | 0 | 9 | 0 | 9
# includes out of Programme Jaldakha HEP U#1-9MW, State Sector commissioned in 2012-13.
B. | Hydro Capacity for benefits beyond 12th Plan- Under Execution
Central Sector
27 | Tehri PSS (THDC) | Uttarakhand | 4x250 | 1000 | 18.07.06 | 2019-20
28 | Lata Tapovan (NTPC) | Uttarakhand | 3x57 | 171 | 17.07.12 | 2021-22 *R
29 | Vishnugad Pipalkoti (THDC) | Uttarakhand | 4x111 | 444 | 21.08.08 | 2019-20
4b | Subansiri Lower (NHPC) | Ar. Pr./Assam | 8x250 | 1000 | 09.09.03 | 2020-21 *R
30 | Ramam-III (NTPC) | West Bengal | 3x40 | 120 | 10.09.14 | 2020-21
| Sub- total (Central Sector) : |  |  | 2735
State Sector
31 | Parnai (JKSPDC) | J&K | 3x12.5 | 37.5 | 21.10.13 | 2020-21
32 | Lower Kalnai (JKSPDC) | J&K | 2x24 | 48 | 16.08.13 | 2020-21
33 | Shongtom Karcham (HPPCL) | H.P. | 3x150 | 450 | 16.08.12 | 2019-20
34 | Shahpurkandi (PSPCL) | Punjab | 3x33+3x33+1x8 | 206 | 04.05.11 | 2019-20 *R
35 | Vyasi (UJVNL) | Uttarakhand | 2x60 | 120 | 25.10.11 | 2018-19
36 | Koyna Left Bank (WRDMah) | Maharashtra | 2x40 | 80 | 20.02.04 | 2019-20 *A
37 | Indrasagar Polavaram (PPA) | Andhra Pradesh | 12x80 | 960 | 25.02.09 | 2021-22 *AE
| Sub- total (State Sector) : |  |  | 1901.5
Private Sector
38 | Ratle (Ratle Hydro) | J&K | 4x205+1x30 | 850 | 19.12.12 | 2021-22 *R
39 | Bajoli Holi (GMR) | H.P. | 3x60 | 180 | 30.12.11 | 2019-20
40 | Chanju-I (IA Energy) | H.P. | 3x12 | 36 | 24.04.10 | 2016-17
41 | Tashiding (Shiga) | Sikkim | 2x48.5 | 97 | 06.04.09 | 2016-17
42 | Dikchu (Dikchu) | Sikkim | 2x48 | 96 | 21.10.11 | 2016-17
43 | Rangit-II (Sikkim Hydro Power) | Sikkim | 2x33 | 66 | 10.02.10 | 2019-20 *R
44 | Rongnichu (Madhya Bharat Power) | Sikkim | 2x48 | 96 | 01.10.08 | 2019-20
45 | Panan (Himagiri Hydro Energy) | Sikkim | 4x75 | 300 | 07.03.11 | 2020-21 *AE
46 | Gongri (Dirang Energy) | Ar. Pradesh | 2x72 | 144 | 04.02.13 | 2019-20 *A
| Sub- total (Private Sector) : |  |  | 1865
| Total 'B': Beyond 12th Plan-Under execution |  |  | 6501.5
| Total: Under Execution |  |  | 13267.5
| Under Construction (12th plan & Beyond) | Central | State | Private | Total
|  | 6155 | 3757.5 | 3355 | 13267.5
Legends: *C-Critical; *P-Partialy Commissioned ; *R-Subject to Re-Start of Works; *A-Subject to Active Start of works ; *AE-Subject to Active Start & Award of E&M Works; # :-Outside from the 12th Plan Programme, *S-Programme of 2016-17, however Slipping to 2017-18.
- 18 -

## Ch7
| CHAPTER 7 | [15 empty] | to be deleted
| Financial Status of H.E. Projects 12th Plan and Beyond | [13 empty] | Figures in Crores
Sl. | Name of project | Capacity | Benefits | Sancd. | Latest/ | Total | Total | Total | Total | Total | Total | Total | Total | Total | Expend. | Expend. | Expend.
No. | (State) | (MW) | (MW) | Cost | Ant. | Expend. | Expend. | Expend. | Expend. | Expend. | Expend. | Expend. | Expend. | Expend. | During | Cumm. | During
|  |  |  | (PL) | Cost | upto | upto | upto | upto | upto | upto | upto | upto | upto | 2016-17 | since | 2015-16
[5 empty] | (PL) | Mar,08 | Mar,09 | Mar,10 | Mar,11 | Mar,12 | Mar,13 | Mar,14 | Mar,15 | Mar,16 | (Upto) | Inception
i) Commissioned during 11th Plan
Central Sector
1 | Sewa -II (NHPC) | 3x40 | 120 | 66546 | 106312 | 63126 | 79014 | 94696 | 99947 | 106488 | 106823
| J&K |  |  | (9/02) | [6 empty] | (Jun-12)
2 | Koteshwar (THDC) | 4x100 | 400 | 130156 | 2386.41 | 75836 | 121944 | 177149 | 230802 | 262071 | 271684 | 273502 | 667
| (Uttarakhand) |  |  | (10/99) | (03/12) | [7 empty] | (Dec-14)
3 | Omkareshwar (NHDC) | 8x65 | 520 | 222473 | - | 219052 | 222879
| M.P. |  |  | (11/2002) |  |  | (11/2008)
4 | Teesta V (NHPC) | 3x170 | 510 | 219804 | 252622 | 245989
| (Sikkim) |  |  | (04/99) | (04/08)
Sub-total:Central Sector |  |  | 1550
State Sector
5 | Baglihar-I (J&K) | 3x150 | 450 | 349500 | 520000 | 402215 | 457172 | 474786 |  |  |  |  | -
|  |  |  | (1997) | (2008) |  |  | (May-09)
6 | Maneri Bhali-II | 4x76 | 304 | 111139 | 171441 | 184611 | [6 empty] | NA
| (Uttarakhand) |  |  | (02/99) | (2005)
7 | Ghatghar PSS | 2x125 | 250 | 62078 | 156401 | 139308 | [6 empty] | -
| Maharashtra |  |  |  | (Under Rev.)
8 | Varahi Extn. | 2x115 | 230 | 28055 | 29100 | 12301 | 28300
| Ktk. |  |  | (2002) | (2004)
9 | Priyadarshni Jurala, | 6x39 | 234 | 54700 | 70000 | 35755 | 47498 | 62500 | 65701 | 68913 | 68950
| A.P. |  |  | (2002) | [6 empty] | (Sep-12)
10 | Kuttiyadi Addl. Extn. | 2x50 | 100 | 22050 * | 16828** | 10573 | 13389 | 14158
| Kerala |  |  | (1998) | (2003) |  |  | (Sep-09)
11 | Balimela Extn. | 2x75 | 150 | 20009 | 21240 | 19413 | 20577 | 20640 |  |  |  |  | -
| Orissa |  |  | (10/98) | (04/2000) |  |  | (May-09)
12 | Purulia PSS | 4x225 | 900 | 145656 | 295260 | 210073
| W.B. |  |  | (09/91) | (1994)
13 | Myntdu, Meghalaya | 2x42 | 84 | 36308 | 117313 | 42374 | 65937 | 82827 | 96485 | 96879
|  |  |  | (1999) | (2010) |  |  |  |  | (Jul-11)
Sub-total: State Sector |  |  | 2702
Private Sector
14 | Allain Duhangan | 2x96 | 192 | 92235 | - | 87100 | 129600 | 150600 |  |  |  |  | -
| H.P. | [6 empty] | (Jun-09)
15 | Karcham Wangtoo | 4x250 | 1000 | 590959 | - | 129971 | 265813 | 421767 | 618785
H.P.
16 | Malana-II | 2x50 | 100 | 59800 | 63347 | 28001 | 51100 | 63939 | 78646
H.P.
Sub-total: Private Sector |  |  | 1292
Total (Commnd- 11th Plan): |  |  | 5544
Commissioned during12th Plan
Central Sector
1 | Uri-II (NHPC) | 4x60 | 240 | 1724.79 | 2305.65 | 331.25 | 722.57 | 1082.33 | 1399.23 | 1693.59 | 1928.07 | 2096.81
| J&K |  |  | (02/2005) | [7 empty] | (Dec-13)
2 | Chamera-III (NHPC) | 3x77 | 231 | 1405.63 | 2084.01 | 408.7 | 746.55 | 1144.62 | 1552.7 | 1795.93 | 1842.24
| H.P. |  |  | (02/2005) | [6 empty] | (Jun-12)
3 | Chutak | 4x11 | 44 | 621.26 | 913.25 | 139.91 | 238.37 | 413.98 | 621.95 | 731.93 | 775.32 | [6 empty] | Rs. Lakhs
| J&K |  |  | (12/05) | [6 empty] | (Jan-13)
4 | Teesta Low Dam - III | 4x33 | 132 | 768.92 | 1628 | 637.17 | 879.29 | 1095.42 | 1258.07 | 1467.53 | 1686.98 | 1706.39
| (NHPC) W.B. |  |  | (12/02) | [7 empty] | (Apr-13)
5 | Nimoo Bazgo | 3x15 | 45 | 611.01 | 936.1 | 143.19 | 264.48 | 444.69 | 622.09 | 724.94 | 840.91 | 883.85
| J&K |  |  | (12/05) | (03/2011) | [6 empty] | (Oct-13)
6 | Parbati -III(NHPC) | 4x130 | 520 | 2304.56 | 2716 | 407.1 | 698.05 | 988.78 | 1406.31 | 1760.29 | 2077.96 | 2349.46
| H.P. |  |  | (05/2005)
7 | Ram Pur (SJVNL) | 6x68.67 | 412 | 2047.03 | 3288.28 | 252.77 | 534.96 | 787.3 | 1127.52 | 1659.73 | 2380.13 | 3123.29 | 3337.91 | 3337.91
| H.P. | [11 empty] | (Dec-14)
8 | Kol Dam (NTPC) | 4x200 | 800 | 4527.15 | 7220 | 2159.27 | 2691.62 | 3174 | 3640 | 4270 | 4937 | 5878 | 6544 | 6544
| H.P. |  |  | (12/2001)
9 | Teesta Low Dam-IV(NHPC) | 4x40 | 160 | 1061.38 | 2198.08 | 23115 | 46109 | 69559 | 927.44 | 1105 | 1314.17 | 1480.5 | 1724.7 | 2013.84 | 34.56 | 2039.6
| W.B. |  |  | (3/05) | [10 empty] | (Aug-16) | (Jul-16)
| Sub-total:Central Sector |  | 2584
State Sector
10 | Bhawani Kattlai Barrage - II | 2x15 | 30 | 99.15 | 497.46 | 62.72 | 111.69 | 253.93 | 453.7 | 465.83 | 477.06 | 493.4
| T.N. (TANGEDCO) |  |  | (1995) | [7 empty] | (Sep-13)
11 | Bhawani Kattlai Barrage - III | 2x15 | 30 | 99.75 | 493.2 | 57.05 | 96.6 | 151.86 | 353.79 | 368.52 | 379.87 | 413.64
| T.N. (TANGEDCO) |  |  | (1999) | [7 empty] | (Sep-13)
12 | Myntdu, (MeECL) | 2x42+1x42 | 42 | 363.08 | 1173.13 | 423.74 | 659.37 | 828.27 | 964.85 | 968
| Meghalaya |  |  | (1999) | (2010) |  |  |  |  | (Jun-11)
13 | Baglihar-II (JKPDC) | 3x150 | 450 | 3113.19 | 3113.19 |  |  |  |  | 191.72
J&K
14 | Lower Jurala (TSGENCO) | 6x40 | 240 | 908.34 | 1969.14 | 213 | 14565 | 31608 | 61672 | 886 | 1109.52 | 1332.89 | 1572.83 | 1728.89
| Telangana |  |  | (05/07) | [9 empty] | (Mar-16)
15 | Kashang-I (HPPCL) | 1x65 | 65 | 47802 | 47802 | 143.32 | 175.23 | 177.18 | 315.46 | @ | [6 empty] | 111.77
| H.P. |  |  | (03/08) | (03/08)
16*P | Kashang -II & III (HPPCL) | 2x65 | 65 | 601.78 | 1079.81 | 14332 | 17523 | 17718 | 315.46 | [7 empty] | 111.77
| H.P. | [15 empty] | (Mar-16)
17*P | Pulichintala | 4x30 | 30 | 380 | 563.49 | 222 | 1585 | 9701 | 158.82 | [7 empty] | 43.18
| Telangana |  |  | (2006-07)
| Sub-total:State Sector |  | 952
Outside 12th Plan programme
# | Jaldhaka (WBSEDCL) | 4x9 | 9
West Bengal
Private Sector
18 | Budhil (Lanco Green Power) | 2x35 | 70 | 418.8 | - | 160.62 | 24510 | 30839 | 364
| H.P. | [7 empty] | (04/2010)
19 | Chujachen (Gati Infrastruc.) | 2x49.5 | 99 | 448.76 | 1044.5 | 254.31 | 425.34 | 653.1 | 800.8 | 966.2 | 1191.26
| Sikkim | [9 empty] | (Feb/2013)
20 | Shrinagar (AHPC) | 4x82.5 | 330 | 1699.12 | 2069 | 271 | 75927 | 149060 | 2273.98 | 3328.01 |  |  | 5088 | 5088
| Uttarakhand |  |  | (08/07) |  | (12/07) | [6 empty] | (Jan-15)
21 | Jorethang Loop(DANS Ener) | 2x48 | 96 | 543.15 | 543.15
Sikkim
21 |  |  | 595
4131
| Sub-total:Private Sector |  | 595
iii) Under Execution for benefits during 12th Plan and beyond
Central Sector
1 | Kishanganga (NHPC) | 3x110 | 330 | 3642.04 | 5783.17 | 49.22 | 175.77 | 28932 | 692.14 | 1403.13 | 2184.17 | 3279.46 | 3912.95 | 4476.2 | 302.34 | 4778.54 | 577.44
| J&K |  |  | (09/07) | (09/2015) | [9 empty] | (Dec-16) | (Dec-16) | (Mar-16)
2 | Parbati -II(NHPC) | 4x200 | 800 | 3919.59 | 8398.76 | 201325 | 234394 | 270070 | 3083.03 | 3363.07 | 3854.2 | 4383.57 | 4950.04 | 5557.21 | 503.39 | 6060.6 | 598.21
| H.P. |  |  | (12/2001) | (03/2015) | [9 empty] | (Dec-16) | (Dec-16) | (Mar-16)
3 | Tehri PSP (THDC), | 4x250 | 1000 | 1657.6 | 2978.86 | 21016 | 23744 | 24435 | 252.15 | 320.76 | 466.42 | 692.34 | 1180.43 | 1706.72 | 334.28 | 2041
| Uttarakhand |  |  | (12/05) | (04/10) | [9 empty] | (Dec-16) | (Dec-16)
4 | Tapovan Vishnugad (NTPC) | 4x130 | 520 | 2978.48 | 3846.3 | 24053 | 55400 | 84600 | 1078 | 1457 | 1813 | 2078 | 2417 | 2788 | 214 | 3002
| Uttarakhand |  |  | (03/2004) | (01/2014) | [9 empty] | (Nov-16) | (Nov-16)
5 | Lata Tapovan(NTPC) | 3x57 | 171 | 1527 | 1801.07 | - | - | - |  | 36 | 97 | 138 | 139 | 143 | 3 | 146
| Uttarakhand |  |  | (07/2012) | (07/2012) | [9 empty] | (Oct-16) | (Nov-16)
6 | Vishnugad Pipalkoti (THDC) | 4x111 | 444 | 2491.58 | 2491.58 | 3001 | 5893 | 10250 | 146.5 | 298.92 | 342.98 | 479.31 | 592.44 | 824.04 | 156.8 | 980.84
| Uttarakhand |  |  | (3/08) | (03/08) | [9 empty] | (Dec-16) | (Dec-16) | (Mar-16)
7 | Ramam-III (NTPC) | 3x40 | 120 | 1381.84 | 1592.34 | [7 empty] | 108 | 174 | 47 | 221
| West Bengal | [13 empty] | (Nov-16) | (Nov-16) | (Feb-16)
8 | Subansiri Lower (NHPC) | 8x250 | 2000 | 6285.33 | 18063.89 | 197522 | 298696 | 395827 | 4851.06 | 5605.94 | 6203.48 | 6782.58 | 7578.63 | 8367.94 | 398.69 | 8766.63
| Ar. Pradesh/Assam |  |  | (12/2002) | (04/15) | [9 empty] | (Dec-16) | (Dec-16) | (Mar-16)
9 | Kameng (NEEPCO) | 4x150 | 600 | 2496.9 | 6085.84 | 70239 | 87006 | 110586 | 1410.13 | 1800.28 | 2215.94 | 2846.68 | 3762.55 | 4574.8 | 585.13 | 5159.93
| Ar. Pradesh |  |  | (03/04) | (03/2015) | [9 empty] | (Dec-16) | (Dec-16) | (Mar-16)
10 | Pare (NEEPCO) | 2x55 | 110 | 573.99 | 1339.57 |  | 4560 | 9750 | 182.47 | 310.59 | 517.54 | 811.78 | 994.4 | 1160.87 | 149.89 | 1310.76
| Ar. Pr. |  |  | (06/07) | (01/16) | [9 empty] | (Dec-16) | (Dec-16) | (Mar-16)
11 | Tuirial (NEEPCO) | 2x30 | 60 | 368.72 | 1381.71 |  |  | 21409 | 226.09 | 301.15 | 401.34 | 573.22 | 800.74 | 1005.51 | 120.74 | 1126.25
| Mizoram |  |  | (06/97) | (12/14) | [9 empty] | (Dec-16) | (Dec-16) | (Mar-16)
| Sub Total: Central Sector |  | 6155
-41-
State Sector
12 | Parnai | 3x12.5 | 37.5 | [12 empty] | 64.64
| J&K | [14 empty] | (Nov-16)
13 | Lower Kalnai | 2x24 | 48 | [12 empty] | 71.98
| J&K | [14 empty] | (Nov-16)
14 | Uhl-III | 3x33.33 | 100 | 431.56 | 940.84 | 25916 | 34812 | 49962 | 624.65 | 754.74 | 881.49 | 1004.7 | 1128.3 | 1259.29 | 60.63 | 1319.92 | 667.04
| H.P. |  |  | (09/02) | (03/08) | [9 empty] | (Nov-16) | (Nov-16) | (Feb-16)
15 | Kashang -II & III @ | 2x65 | 65 | 601.78 | 601.78 | 14332 | 17523 | 17718 | 315.46 | 459.64 | 608.74 | 736.55 | 843.44 | 963.45 | 48.39 | 1011.84 | 111.77
| H.P. | [13 empty] | (Dec-16) | (Dec-16) | (Mar-16)
16 | Sainj | 2x50 | 100 | 784.56 | 784.56 |  |  |  | 139.9 | 272.79 | 450.48 | 656.19 | 839.46 | 974.89 | 19.73 | 994.62 | 127.47
| H.P. | [13 empty] | (Dec-16) | (Dec-16) | (Feb-16)
17 | Sawara Kuddu | 3x37 | 111 | 558.53 | 1181.9 | 9292 | 12100 | 33125 | 431.26 | 660.18 | 813.55 | 959.09 | 1022.55 | 1028.62 | 98.21 | 1126.83 | 72.7
| H.P. |  |  | (03/03) | [10 empty] | (Dec-16) | (Dec-16) | (Feb-16)
18 | Shontong Karcham | 3x150 | 450 | 2807.83 | 3316.35 | [5 empty] | 178.89 | 229.04 | 270.93 | 451.19 | 73.92 | 525.11 | 175.54
| H.P. | [13 empty] | (Dec-16) | (Dec-16) | (Feb-16)
19 | Vyasi | 2x60 | 120 | 936.23 | 936.23 | - | [6 empty] | 114.53 | 183.93 | 105.18 | 289.11 | 60.22
| Uttarakhand |  |  | (2010-02) | [10 empty] | (Dec-16) | (Dec-16) | (Feb-16)
20 | Shahpurkandi | 3x33+3x33+1x8 | 206 | 2285.81 | 2285.81 | [5 empty] | 299.34 | 327.73 | 513.5 |  |  | 517.17 | 44.44
| Punjab |  |  |  | (04/2008) | [6 empty] | (Aug-13) | (Apr-15) | (Jan-16) | (Jul-16) | (May-16) | (Jan-16)
21 | Koyna Left bank PSS | 2x40 | 80 | 245.02 | 1494.94 |  |  |  |  | 84.8 | 116.67 | 128.93 | 131.6 |  |  | 334.59 | 202.99
| Maharashtra | [14 empty] | (Nov-16) | (Sep-15)
22 | New Umtru | 2x20 | 40 | 226.4 | 599 | - | 5928 |  |  | 112.87 | 167.23 | 196.67 | 255.91 | 323.11 | 37.39 | 360.5
| Meghalaya+B87 | [5 empty] | (08/2008) | [6 empty] | (Mar-16) | (Nov-16) | (Nov-16) | (Dec-15)
23 | Nagarjuna Sagar T Pool | 2x25 | 50 | 464.63 | 958.67 | 7275 | 13220 | 23568 | 388.08 | 463.62 | 534.62 | 589.95 | 872.6 |  |  | 912.1 | 39.5
| Andhra Pradesh |  |  | (2002) | [11 empty] | (Aug-15) | (Aug-15)
24 | Polavaram (PPA) | 12x80 | 960 | 16010.45 | 16010.45 | [6 empty] | 5067.38 | 5506.86 |  |  | 7364.06 | 1857.2
| Andhra Pradesh |  |  | (02/09) | (02/09) | [10 empty] | (Aug-15) | (Aug-15)
25 | Pallivasal | 2x30 | 60 | 222.00 | 284.69 | 3580 | 4592 | 5884 | 116.97 | 146.41 | 158.54 | 173.68 | 178.77 | 178.77 | 4.93 | 183.7 | 5.7
| Kerala |  |  | (2004) | (2007) | [9 empty] | (Dec-16) | (Dec-16) | (Mar-16)
26 | Thottiyar | 1x30 + 1x10 | 40 | 136.79 | 150.02 | - | - | 91 | 1.18 | 2.91 | 16.24 | 32.05 | 46.18 | 52.8662 | 0.009825 | 52.88 | 6.68
| Kerala |  |  | (2007) | [10 empty] | (Jun-16) | (Jun-16) | (Mar-16)
27*P | Pulichintala | 4x30 | 90 | 380 | 563.49 | 222 | 1585 | 9701 | 158.82 | 174.46 | 217.91 | 240.94 | 424.63 | 446.2 | 25.58 | 471.78 | 43.18
| Telangana |  |  | (2006-07) | [10 empty] | (Dec-16) | (Dec-16) | (Feb-16)
28 | Teesta St. III | 6x200 | 1200 | 5705.55 | 13965.00 | 94800 | 167300 | 308340 | 4425.04 | 5475.43 | 6854.78 | 8219.68 | 9161.7 | 10888.44 | 801.66 | 11690.1 | 1230.15
| Sikkim | [9 empty] | (01/2013) |  |  | (Mar-16) | (Oct-16) | (Oct-16) | (Jan-16)
| Sub-total: State Sector |  | 3757.5
Private Sector
29 | Ratle | 4x205 + 1x30 | 850 | 5517.02 | 6257.00 |  |  |  |  | 124.12 | 373.8 |  |  | 1451
| J&K |  |  |  | (09/2013)
30 | Sorang | 2x50 | 100 | 586 | 586 | 9959 | 17105 | 21305
| H.P. |  |  | (2006) | (2006)
31 | Tidong-I | 2x50 | 100 | 543.15 | 543.15 | - | 2340 | 3460 | 118 | 226 | 250.89 | 279.89 | 398.14 |  |  | 398.14
| H.P. |  |  | (08/05) | (08/05) | [6 empty] | (May-13) | (Oct-15) |  |  | (Oct-15)
32 | Tangnu Romai- I | 2x22 | 44 | 255 | 255 |  |  |  | 35.26 | 41.37 | 179 |  |  |  |  | 179
| H.P. |  |  | (2006) | (2006) | [10 empty] | (Mar-13)
33 | Bajoli Holi | 3x60 | 180 | 1696.93 | 2205.00 | [5 empty] | 112 |  | 323.28 | 897 | 256 | 1153
| H.P. | [11 empty] | (Dec-14) |  | (Dec-16) | (Dec-16)
34 | Chanju-I | 3x12 | 36 | 295.09 | 295.09 |  |  |  | 8.05 | 45.94 | 152.39 | 194.66 | 363.71 | 509.46 | 509.46 | 509.46 | 106.61
| H.P. | [13 empty] | (Mar-16) | (Mar-16) | (Mar-16)
35 | Phata Byung | 2x38 | 76 | 520 | 1225.53 | - | - | 19112 | 276.98 | 364.98 | 486.96 | 518.24 |  | 818.49 |  | 854.33
| Uttarakhand |  |  | (2007) |  |  |  | (03/2010) |  |  |  | (Jun-13) |  | (Jul-16) |  | (Dec-16)
36 | Singoli Bhatwari | 3x33 | 99 | 666.47 | 1577 | - | - | 14507 | 203.62 | 351 | 485.78 | 635.13 | 737.42 | 848.53 | 70.83 | 919.36 | 111.11
| Uttarakhand |  |  | (2008) | [10 empty] | (Dec-16) | (Dec-16) | (Mar-16)
37 | Maheshwar | 10x40 | 400 | 1569.27 | 6793 | 1255.13 | 1705.57 | 2382 | 2911.85 | 2917.7 |  |  | 3135 |  |  |  | -
| M.P. |  |  | (96-97)
38 | Teesta St. VI | 4x125 | 500 | 3283.08 | 7542 | 53419 | 72467 | 76673 | 1503.96 | 2086.25 | 2399.5 |  | 3052.22 | 3396 |  | 225 | 91.78
| Sikkim | [6 empty] | (09/2009) | [5 empty] | (Mar-16) |  | (Dec-16) | (Jun-15)
39 | Rangit-IV | 3x40 | 120 | 775.3 | 1692.6 | 561 | 9809 | 13829 | 247.17 | 376.36 | 416.53 | 563.2 | 804.37 | 816.76 |  | 816.76 | -
| Sikkim |  |  |  | (06/2016) | [6 empty] | (Sep-13) | (Aug-15) | (Jun-16) |  | (Jun-16)
40 | Bhasmey | 2x25.5 | 51 | 408.5 | 690.3 |  |  |  |  | 160.9 | 162.4 |  | 237.1 | 276.7 |  | 276.7 | 39.6
| Sikkim | [9 empty] | (Apr-12) |  | (Mar-15) | (Oct-15) |  | (Oct-15) | (Oct-15)
41 | Tashiding | 2x48.5 | 97 | 465.95 | 465.95 |  |  |  | 29.75 | 103.92 |  |  |  | 815
| Sikkim | [8 empty] | (Feb-12) |  |  |  | (Apr-16)
42 | Dikchu | 2x48 | 96 | 639.57 | 1140 | 175 | 1123 | 2961 | 52.43 | 99.38 |  |  |  | 1074 | 66 | 1140
| Sikkim | [8 empty] | (Nov-11) | [5 empty] | ('Dec-16)
43 | Rangit- II | 2x33 | 66 | 496.44 | 496.44
Sikkim
44 | Rongnichu | 2x48 | 96 | 491.32 | 491.32 | [10 empty] | 94.24 | -
| Sikkim | [14 empty] | (Nov-11)
45 | Panan | 4x75 | 300 | 1833.05 | 2021.9 | 1578 | 2808 | 5367 | 91.67 | 104.62 | 117.31 | 127.4 | 141.35 | 152.3 | 4.2 | 156.5 | 153
| Sikkim | [12 empty] | (Mar-16) | (Oct-16) | (Oct-16) | (Jun-15)
46 | Gongri | 2x72 | 144 | 1436.27 | 1436.27 | [5 empty] | 290.21 | 426.87 | 468.86 | 521.21 |  |  | 54
Ar. Pradesh
| Sub-total: Private Sector |  | 3355
| Total (iii): (Under Execution): |  | 13267.5
Legends: *C-Critical; *P-Partialy Commissioned ; *R-Subject to Re-Start of Works; *A-Subject to Active Start of works ; *AE-Subject to Active Start & Award of E&M Works; # :-Outside the 12th Plan Programme, *S-Programme of 2016-17, however Slipping to 2017-18. @ Financial Figures are shared by Kashang-I & Kashang-II & III HEPs.
-42-

## Ch8
CHAPTER 8
Status of Environmental and Forest Clearance of H.E. Projects for
benefits in 12th Plan & beyond
Sl. | Name of | State | I.C. | Benefits | Date of | Date of | Date of | Date of
No. | Project |  | (No.xMW) | (MW) | Clearance | Env. | Forest | Approval
[6 empty] | Clearance | Clearance
A. | Commissioned during 12th Plan
Central Sector
1 | Uri-II (NHPC) | J&K | 4x60 | 240 | 11.02.04 | 13.08.04 | Not Reqd. | 01.09.05
2 | Chutak (NHPC) | J&K | 4x11 | 44 | 23.04.04 | 17.11.05 | Not Reqd. | 24.08.06
3 | Nimoo Bazgo (NHPC) | J&K | 3x15 | 45 | 16.03.04 | 30.05.05 | Not Reqd. | 24.08.06
4 | Chamera-III (NHPC) | H.P. | 3x77 | 231 | 10.10.03 | 10.03.05 | 08.06.04 | 01.09.05
5 | Parabati-III (NHPC) | H.P. | 4x130 | 520 | 12.11.03 | 16.04.05 | 13.06.05 | 09.11.05
6 | Ram Pur (SJVNL) | H.P. | 6x68.67 | 412 | 16.12.05 | 31.03.06 | 07.04.06 | 25.01.07
7 | Kol Dam (NTPC) | H.P. | 4x200 | 800 | 30.06.02 | 10.05.2000 | 23.11.2000 | 28.10.02
8 | Teesta Low Dam-III (NHPC) | W.B. | 4x33 | 132 | 25.06.02 | 16.07.03 | 07.04.04 | 30.10.03
9 | Teesta Low Dam-IV (NHPC) | W.B. | 4x40 | 160 | 23.12.03 | 31.03.05 | 12.01.05 | 30.09.05
|  | Central Sector Totals: |  | 2584
State Sector
10 | Baglihar-II | J&K | 3x150 | 450 | 29.12.10 | - | Not Reqd. | 29.12.10
11 | Bhawani Kattlai Barrage-II | T.N. | 2x15 | 30 | - | 02.01.86 | 02.01.86 | 11.06.99
12 | Bhawani Kattlai Barrage- III | T.N. | 2x15 | 30 | - | 02.01.86 | 02.01.86 | 27.03.02
13 | Myntdu (MeECL) | Meghalaya | 2x42 | 42 | 20.09.99 | 26.09.01 | 19.06.01 | 09.06.03
14 | Lower Jurala (TSGENCO) | Telangana | 6x40 | 240 | 24.07.07 | 04.05.07 | Not Reqd. | 24.07.07
15 | Kashang-I (HPPCL) | H.P. | 2x32.5 | 65 | - | 15.11.02 | 23.06.04 | 31.07.08
16*P | Kashang -II & III (HPPCL) | H.P. | 2x65 | 65 | - | 16.04.10 | 14.01.13 | 2009
17*P | Pulichintala | Telangana | 4x30 | 30 | - | 09.06.2005 | 20.10.2006 | 25.04.07
|  | State Sector Totals: |  | 952
Outside 12th Plan Programme
# | Jaldhaka (WBSEDCL) | W.B. | 4x9 | 9
Private Sector
18 | Budhil | H.P. | 2x35 | 70 | - | 28.02.06 | 19.04.06 | 02.06.05
19 | Srinagar | Utt. | 4x82.5 | 330 | - | 27.07.99 | 17.04.06 | 20.07.05
20 | Chujachen | Sikkim | 2x49.5 | 99 | - | 09.09.05 | 09.01.06 | 30.11.04
21 | Jorethang Loop | Sikkim | 2x48 | 96 | - | 26.07.07 | 12.05.08 | 26.08.06
|  | Private Sector Totals: |  | 595
| Total : Commissioned 12th Plan (up to Dec'16) |  |  | 4131
B. | Under Execution
Central Sector
1 | Kishanganga (NHPC) | J&K | 3x110 | 330 | 31.08.05 | 09.03.06 | 27.05.08 | 14.01.09
2 | Parbati-II (NHPC) | H.P. | 2x400 | 800 | 03.01.01 | 04.06.01 | 04.09.2001 | 11.09.02
3 | Tehri PSS (THDC) | Utt. | 4x250 | 1000 | 10.10.88 | 19.07.90 | 04.06.87 | 18.07.06
4 | Tapovan Vishnugad (NTPC) | Utt. | 4x130 | 520 | 11.08.04 | 08.02.05 | 22.04.06 | 11/2006
5 | Lata Tapovan (NTPC) | Utt. | 3x57 | 171 | 08.02.06 | 21.02.07 | 30.04.07 | 2012-08-01
6 | Vishnugad Pipalkoti (THDC) | Utt. | 4x111 | 444 | 09/2006 | 22.08.07 | 28.05.13 | 21.08.08
7 | Ramam-III (NTPC) | W.B. | 3x40 | 120 | 12.09.06 | 17.08.07 | 18.10.08 | 10.09.14
8 | Subansiri Lower (NHPC) | Ar. Pr./Asm. | 8x250 | 2000 | 13.01.03 | 16.07.03 | 24.06.2004 | 09.09.03
9 | Kameng (NEEPCO) | Ar. Pr. | 4x150 | 600 | 30.04.91 | 29.03.01 | 03.08.2000 | 02.12.04
10 | Pare (NEEPCO) | Ar. Pr. | 2x55 | 110 | 24.09.07 | 13.09.06 | 13.07.2009 | 04.12.08
11 | Tuirial (NEEPCO) | Mizoram | 2x30 | 60 | 30.01.09 | 16.10.96 | 16.03.2000 | 07.07.1998
| Sub-total (Central Sector): |  |  | 6155
State Sector
12 | Parnai (JKSPDC) | J&K | 3x12.5 | 37.5 | 11.12.1992 | 24.12.2010 | 17.05.2013 | 25.10.2013
13 | Lower Kalnai (JKSPDC) | J&K | 2x24 | 48 | 16.08.2013 | 22.08.2014 |  | 16.08.2013
14 | Uhl-III | H.P. | 3x33.33 | 100 | 19.09.02 | 15.11.02 | 20.12.02 | 26.09.03
15 | Kashang -II & III | H.P. | 2x65 | 65 | - | 16.04.10 | 14.01.13 | 2009
16 | Sainj | H.P. | 2x50 | 100 | - | 04.05.09 | 26.10.09 | 29.12.10
17 | Sawara Kuddu | H.P. | 3x37 | 111 | June, 07 | May, 07 | June, 06 | June, 07
18 | Shongtong Karcham | H.P. | 3x150 | 450 | 16.8.12 | 19.05.11 | 22.03.11 | -
19 | Vyasi | Uttarakhand | 2x60 | 120 | 25.10.2011 | 22.04.10 | 14.10.13 | 25.10.2011
20 | Shahpurkandi | Punjab | 3x33+3x33+1x8 | 206 | 08/2009 | 18.11.81 | Not Reqd. | 04.05.11
21 | Koyna Left Bank PSS | Mah. | 2x40 | 80 | - | 16.05.07 | Not Reqd. | 20.02.04
22 | New Umtru | Meghalaya | 2x20 | 40 | - | 13.03.06 | 27.09.05 | 2006-12-01
23 | Nagarjuna Sagar T Pool | Andhra Pr. | 2x25 | 50 | 30.11.07 | 14.06.01 | 11.04.01 | 17.01.05
24 | Polavaram (PPA) | Andhra Pr. | 12x80 | 960 | 21.07.2010 | 28.07.10 | 21.07.10 | 25.02.09
25 | Pallivasal Extn. | Kerala | 2x30 | 60 | 31.01.07 | Not Reqd. | 11.07.07 | 31.01.07
26 | Thottiyar | Kerala | 1x30 + 1x10 | 40 | 05.06.08 | Not Reqd. | 11.07.07 | 05.06.08
27*P | Pulichintala | Telangana | 4x30 | 90 | - | 09.06.2005 | 20.10.2006 | 25.04.07
28 | Teesta St. III | Sikkim | 6x200 | 1200 | - | 04.08.06 | 02.11.07 | 12.05.06
| Sub-total (State Sector): |  |  | 3757.5
Private Sector
29 | Ratle | J&K | 4x205=1x30 | 850 | - | 12.12.12 | 27.04.12 | 19.12.12
30 | Sorang | H.P. | 2x50 | 100 | - | 07.09.06 | Nov, 06 | June, 06
31 | Tidong-I | H.P. | 100 | 100 | - | 18.06.08 | 18.06.08 | 23.07.07
32 | Tangnu Romai- I | H.P. | 2x22 | 44 | - | 01.05.09 | 19.01.10 | 30.11.07
33 | Bajoli Holi | H.P. | 3x60 | 180 | - | 24.01.11 | 08.07.11 | 30.12.11
34 | Chanju | H.P. | 3x12 | 36 | - | 20.04.11 | 17.02.11 | 24.04.10
35 | Phata Byung | Uttarakhand | 2x38 | 76 | - | 01.05.09 | - | 30.11.07
36 | Singoli Bhatwari | Uttarakhand | 3x33 | 99 | - | 24.08.07 | 16.01.09 | 11.07.08
37 | Maheshwar | M.P. | 10x40 | 400 | - | 07.01.94 | Not Reqd. | 29.09.06
38 | Teesta St. VI | Sikkim | 4x125 | 500 | - | 21.09.06 | 25.04.08 | 27.12.06
39 | Rangit-IV | Sikkim | 3x40 | 120 | - | 16.05.07 | 26.12.07 | 06.07.07
40 | Bhasmey | Sikkim | 2x25.5 | 51 | - | 15.05.07 | 13.09.10 | -
41 | Tashiding | Sikkim | 2x48.5 | 97 | - | 29.07.10 | 06.04.10 | 06.04.09
42 | Dikchu | Sikkim | 2x48 | 96 | - | 01.04.08 | 22.01.10 | 21.10.11
43 | Rangit- II | Sikkim | 2x33 | 66 | - | 16.04.10 | 22.10.10 | 10.2.10
44 | Rongnichu | Sikkim | 2x48 | 96 | - | 04.04.07 | 18.05.09 | 01.10.08
45 | Panan | Sikkim | 4x75 | 300 | - | 02.01.07 | 21.09.10 | 07.03.11
46 | Gongri | Ar. Pradesh | 2x72 | 144 | - | 07.09.12 | 19.03.13 | 04.02.13
| Sub-total (Private Sector): |  |  | 3355
| Total : Under Execution |  |  | 13267.5
Legends: *C-Critical; *P-Partialy Commissioned ; *R-Subject to Re-Start of Works; *A-Subject to Active Start of works ; *AE-Subject to Active Start & Award of E&M Works; # :-Outside from the 12th Plan Programme, *S-Programme of 2016-17, however Slipping to 2017-18.
-43-

## Ch9
CHAPTER 9
Status of Civil Package Award (First Package) of H.E. Projects
for 12th Plan & beyond
Sl. | Name of Project | State | Capacity | Benefits | Date of CCEA/ | Date of letter
No. |  |  | (MW) |  | Investment | of award
|  |  |  | (MW) | Decision | (First Package)
A. | Commissioned during 12th Plan
Central Sector
1 | Uri-II (NHPC) | J&K | 4x60 | 240 | 01.09.05 | 21.09.05
2 | Chutak (NHPC) | J&K | 4x11 | 44 | 24.08.06 | 23.09.06
3 | Nimoo Bazgo (NHPC) | J&K | 3x15 | 45 | 24.08.06 | 23.09.06
4 | Chamera-III (NHPC) | H.P. | 3x77 | 231 | 01.09.05 | 21.09.05
5 | Parbati-III (NHPC) | H.P. | 4x130 | 520 | 09.11.05 | 15.12.05
6 | Ram Pur (SJVNL) | H.P. | 412 | 412 | 25.01.07 | 01.02.07
7 | Kol Dam (NTPC) | H.P. | 4x200 | 800 | 28.10.02 | 12/2003
8 | Teesta Low Dam-III(NHPC) | W.B. | 4x33 | 132 | 30.10.03 | 28.10.03
9*P | Teesta Low Dam-IV(NHPC) | W.B. | 4x40 | 160 | 30.09.05 | 10.05.06
| State Sector | Central Sector Totals: |  | 2584
10 | Bhawani Kattlai Barrage-II | T.N. | 2x15 | 30 | 11.06.99 | 03.02.06
11 | Bhawani Kattlai Barrage-III | T.N. | 2x15 | 30 | 27.03.02 | 03.02.06
12 | Myntdu | Meghalaya | 2x42 | 42 | 09.06.03 | 03/04
13 | Baglihar-II | J&K | 3x150 | 450 | 29.12.10 | 31.03.12
14 | Lower Jurala | Telangana | 6x40 | 240 | 07/07 | 10.02.08
15 | Kashang-I | H.P. | 1X65 | 65 | 11/01 | 09.04.09
16*P | Kashang -II & III (HPPCL) | H.P. | 2x65 | 65 | 11/2001 | 11.11.10
17*P | Pulichintala | Telangana | 4x30 | 30 | 25.04.07 | 01.08.07
|  | State Sector Totals: |  | 952
Outside 12th Plan Programme
# | Jaldhaka (WBSEDCL) | W.B. | 4x9 | 9
Private Sector
18 | Budhil | H.P. | 2x35 | 70 | 02.06.05 | 26.12.05
19 | Srinagar | Uttaranchal | 4x82.5 | 330 | 20.07.05 | 06/2007
20 | Chujachen | Sikkim | 2x49.5 | 99 | 30.11.04 | 12.08.06
21 | Jorethang Loop | Sikkim | 2x48 | 96 | 26.08.06 | 09.03.09
|  | Private Sector Totals: |  | 595
| Total : Commissioned (up to Dec'16) |  |  | 4131
B. | Under Execution
Central Sector
1 | Kishanganga (NHPC) | J&K | 3x110 | 330 | 20.07.07 | 22.01.09
2 | Parbati-II (NHPC) | H.P. | 4x200 | 800 | 11.09.02 | 09/02
3 | Tehri PSP | Uttarakhand | 4x250 | 1000 | 18.07.06 | 23.06.11
4 | Tapovan Vishnugad (NTPC) | Uttarakhand | 4x130 | 520 | 11/06 | 11/06
5 | Lata Tapovan (NTPC) | Uttarakhand | 3x57 | 171 | 08/2012 | 17.08.12
6 | Vishnugad Pipalkoti (THDC) | Uttarakhand | 4x111 | 444 | 21.08.08 | 17.01.14
7 | Ramam-III | W.B. | 3x40 | 120 |  | 10.09.14
8 | Subansiri Lower (NHPC) | Ar.Pr./ Assam | 8x250 | 2000 | 09.09.03 | 19.12.03
9 | Kameng (NEEPCO) | Ar. Pr. | 4x150 | 600 | 02.12.04 | 08.12.04
10 | Pare (NEEPCO) | Ar. Pr. | 2x55 | 110 | 04.12.08 | 31.08.09
11 | Tuirial (NEEPCO) | Mizoram | 2x30 | 60 | 07.07.98 14.01.11(RCE) | 30.08.02
| Sub-total (Central Sector): |  |  | 6155
State Sector
12 | Parnai (JKSPDC) | J&K | 3x12.5 | 37.5 | 21.10.2013 | 25.10.2013
13 | Lower Kalnai (JKSPDC) | J&K | 2x24 | 48 | 16.08.2013 | 12.09.2013
14 | Uhl-III | H.P. | 3x33.33 | 100 | 19.09.02 | 02.04.03
15 | Kashang -II & III | H.P. | 2x65 | 65 | 11/2001 | 11.11.10
16 | Sainj | H.P. | 2x50 | 100 | 29.12.10 | 02.08.10
17 | Sawara Kuddu | H.P. | 3x37 | 111 | 06/07 | 17.07.07
18 | Shongton Karcham | H.P. | 3x150 | 450 | 16.08.12 | 04.08.12
19 | Vyasi | Uttarakhand | 2x60 | 120 | 25.10.11 | 10.12.13
20 | Shahpurkandi | Punjab | 3x33+3x33+1x8 | 206 | 04.05.11 | 11.02.13
21 | Koyna Left Bank PSS | Mah. | 2x40 | 80 | 20.02.04 | 20.06.07
22 | New Umtru | Meghalaya | 2x20 | 40 | Dec-07 | 20.12.07
23 | Nagarjuna Sagar T Pool | Andhra Pr. | 2x25 | 50 | 17.01.05 | 19.05.05
24 | Polavaram (PPA) | Andhra Pr. | 12x80 | 960
25 | Pallivasal | Kerala | 2x30 | 60 | 31.01.07 | 31.01.07
26 | Thottiyar | Kerala | 1x30 + 1x10 | 40 | 05.06.08 | 22.12.08
27*P | Pulichintala | Telangana | 4x30 | 90 | 25.04.07 | 01.08.07
28 | Teesta St. III | Sikkim | 6x200 | 1200 | 12.05.06 | 18.04.07
| Sub-total (State Sector): |  |  | 3757.5
Private Sector
29 | Ratle | J&K | 4x205+1x30 | 850 | 19.12.12 | 04.07.13
30 | Sorang | H.P. | 2x50 | 100 | 06/06 | 06/2007
31 | Tidong-I | H.P. | 100 | 100 | 23.07.07 | 07.11.08
32 | Tangnu Romai- I | H.P. | 2x22 | 44 | 2014-15 | 14.06.10
33 | Bajoli Holi | H.P. | 3x60 | 180 | 30.12.11 | 29.05.13
34 | Chanju-I | H.P. | 3x12 | 36 | 2017-18 | 23.07.11
35 | Phata Byung | Uttarakhand | 2x38 | 76 | 06.10.08 | 12.04.08
36 | Singoli Bhatwari | Uttarakhand | 3x33 | 99 | 11.07.08 | 20.06.08
37 | Maheshwar | M.P. | 10x40 | 400 | 30.12.96 | 22.02.97
38 | Teesta St. VI | Sikkim | 4x125 | 500 | 27.12.06 | 03/2007
39 | Rangit-IV | Sikkim | 3x40 | 120 | 06.07.07 | 22.11.07
40 | Bhasmey | Sikkim | 2x25.5 | 51 | Dec-08 | 12.04.10
41 | Tashiding | Sikkim | 2x48.5 | 97 | 06.04.09 | 28.03.11
42 | Dikchu | Sikkim | 2x48 | 96 | 21.10.11 | 22.03.11
43 | Rangit-II | Sikkim | 2x33 | 66 | 10.02.10 | 24.10.11
44 | Rongnichu | Sikkim | 2x48 | 96 | 01.10.08 | 07.04.10
45 | Panan | Sikkim | 4x75 | 300 | 07.03.11 | 22.02.14
46 | Gongri | Ar. Pradesh | 2x72 | 144 | 04.02.13 | 22.12.11
| Sub-total (Private Sector): |  |  | 3355
| Total - Under Execution: |  |  | 13267.5
Additional
1 | Demwe Lower | Ar. Pradesh | 5x342+1x40 | 1750 | 20.11.09 | 12/2010
Works on the project yet to start for want of Financial Closure.
Legends: *C-Critical; *P-Partialy Commissioned ; *R-Subject to Re-Start of Works; *A-Subject to Active Start of works ; *AE-Subject to Active Start & Award of E&M Works; # :-Outside from the 12th Plan Programme, *S-Programme of 2016-17, however Slipping to 2017-18.
- 44-

## Ch9.1
CHAPTER 9.1
Ordering Status of TG sets for H. E. Projects for 12th Plan & Beyond
Summary- Units Ordered
Sector | BHEL | China | Others | Total
Central Sector
Commissioned | 1981 | 0 | 603 | 2584
Under Execution | 3045 | 0 | 3110 | 6155
Sub-total (Central) | 5026 | 0 | 3713 | 8739
State Sector
Commissioned | 30 | 0 | 922 | 952
Under Execution | 566 | 100 | 2046 | 2712
Sub-total (State) | 596 | 100 | 2968 | 3664
Comm. Outside 12th Plan | 0 | 0 | 9 | 9
Private Sector
Commissioned | 330 | 70 | 195 | 595
Under Execution | 400 | 0 | 2655 | 3055
Sub-total (Private) | 730 | 70 | 2850 | 3650
Commissioned-12th Plan | 2341 | 70 | 1720 | 4131
Comm. Outside 12th Plan | 0 | 0 | 9 | 9
Total: Commissioned | 2341 | 70 | 1729 | 4140
Total: Under Execution | 4011 | 100 | 7811 | 11922
Total- Units Ordered | 6352 | 170 | 9531 | 16062
Summary- Under Execution- 12th Plan & Beyond
Sector | Benefits | Capacity Ordered |  |  | Not yet ordered
| (MW) | BHEL | Others | Total
Central Sector | 6155 | 3045 | 3110 | 6155 | 0
State Sector | 3757.5 | 566 | 2146 | 2712 | 1045.5
Private Sector | 3355 | 400 | 2655 | 3055 | 300
Total: Under Execution | 13267.5 | 4011 | 7911 | 11922 | 1345.5
- 45 -

## Ch9.2
CHAPTER 9.2
Ordering Status of TG sets of H.E. Projects
for 12th Plan & beyond
Sl. | Name of the | Capacity | Benefits | Make/Supplier | Date of
No. | Project/State | (No.x MW) | (MW) | of TG set | Order
A. | Commissioned during 12th Plan
Central Sector
BHEL Units
1 | Chutak (NHPC) J&K | 4x11 | 44 | BHEL | 16.08.07
2 | Nimoo Bazgo (NHPC) J&K | 3x15 | 45 | BHEL | 12.06.07
3 | Parabati-III (NHPC) HP | 4x130 | 520 | BHEL | 29.12.06
4 | Ram Pur (SJVNL), H.P. | 6x68.67 | 412 | BHEL | 16.09.08
5 | Kol Dam (NTPC), H.P. | 4x200 | 800 | BHEL, Toshiba & Marubeni | 07/2004
6 | Teesta Low Dam-IV (NHPC), W.B. | 4x40 | 160 | BHEL | 10.05.07
| Sub-total CS BHEL |  | 1981
Other Units
7 | Uri-II (NHPC), J&K | 4x60 | 240 | Alstom, India & France | 29.12.06
8 | Chamera-III (NHPC) HP | 3x77 | 231 | M/s Alstom, India & France | 23.01.07
9 | Teesta Low Dam-III (NHPC), W.B. | 4x33 | 132 | VA Tech, India | 30.07.04
| Sub-total CS Other units |  | 603
| Sub-total (Central Sector): |  | 2584
State Sector
BHEL Units
10*P | Pulichintala, Telangana | 4x30 | 30 | BHEL | 25.05.07
| Sub-total SS BHEL |  | 30
Other Units
11 | Bhawani Barrage II ,T.N. | 2x15 | 30 | Litostroj Slovania Koncar, Croatia | 27.12.06
12 | Bhawani Barrage III, T.N. | 2x15 | 30 | Litostroj Slovania | 15.11.06
Koncar, Croatia
13 | Myntdu, (Meghalaya) | 2x42 | 42 | V.A. Tech, India | 30.11.05
14 | Baglihar-II, J&K | 3x150 | 450 | Voith-Andritz consortium, Germany & India | 31.03.12
15 | Lower Jurala, Telangana | 6x40 | 240 | Alstom, India | 09.06.08
16 | Kashang-I (H.P.) | 1x65 | 65 | Andritz Hydro, India | 01.12.10
17*P | Kashang -II & III (H.P.) | 2x65 | 65 | Andritz Hydro, India | 01.12.10
| Sub-total SS Other units |  | 922
| Sub-total (State Sector): |  | 952
Outside 12th Plan programme
# | Jaldhaka , West Bengal | 4x9 | 9
Private Sector
BHEL Units
18 | Srinagar (Uttarakhand) | 4x82.5 | 330 | BHEL | 04/2007
| Sub-total- BHEL |  | 330
Chineese
19 | Budhil (H.P.) | 2x35 | 70 | Dongfang Elec.Corporation, China | 12.07.06
| Sub-total- Chineese |  | 70
Other Units
20 | Chujachen (Sikkim) | 2x49.5 | 99 | Alstom, India | 20.12.06
21 | Jorethang Loop, Sikkim | 2x48 | 96 | Alstom, India | 1.12.09
| Sub-total- Other units |  | 195
| Sub-total (Private Sector): |  | 595
Total : Commnd. 12th Plan (upto Dec '16) |  |  | 4131
B. | Under Execution for benefits during 12th Plan & beyond
Units ordered
Central Sector
BHEL Units
1 | Kishanganga (NHPC), J&K | 3x110 | 330 | BHEL | 22.01.09
2 | Parbati-II (NHPC),(H.P. | 4x200 | 800 | BHEL | 24.12.02
3 | Tapovan Vishnugad (NTPC), Utt. | 4x130 | 520 | BHEL | 01/2008
4 | Lata Tapovan, Uttarakhand | 3x57 | 171 | BHEL | 12/2012
5 | Vishnugad Pipalkoti (THDC) | 4x111 | 444 | BHEL | 18.11.14
6 | Kameng (NEEPCO), Ar. Pr. | 4x150 | 600 | BHEL | 03.12.04
7 | Tuirial (NEEPCO), Mizoram | 2x30 | 60 | BHEL | 25.10.03 & 01.08.11(Rev)
8 | Ramam-III (NTPC) | 3x40 | 120 | BHEL | 10.09.14
| Sub-total- BHEL |  | 3045
Other Units
9 | Tehri PSP (THDC) | 4x250 | 1000 | Alstom, France | 23.06.11
10 | Subansiri Lower (NHPC), Ar. Pradesh | 8x250 | 2000 | Alstom, France & India | 11.02.05
11 | Pare (NEEPCO), Ar. Pr. | 2x55 | 110 | Andritz Hydro, India | 01.10.10
| Sub-total- Others |  | 3110
| Sub-total (Central Sector): |  | 6155
- 46 -
State Sector
BHEL Units
12 | Uhl-III (H.P.) | 3x33.33 | 100 | BHEL | 15.02.07
13 | Nagarjuna Sagar Tail, AP | 2x25 | 50 | BHEL | 03.05.06
14 | Pulichintala, Telangana | 4x30 | 90 | BHEL | 25.05.07
15 | Shahpurkandi, Punjab | 3x33+3x33+1x8 | 206 | BHEL | 28.02.14
16 | Vyasi , Uttarakhand | 2x60 | 120 | BHEL | 26.03.14
| Sub-total- BHEL |  | 566
Chineese
17 | Pallivasal, Kerala | 2x30 | 60 | Dongfang Elec.Corp., China | 31.01.07
18 | Thottiyar, Kerala | 1x30 + 1x10 | 40 | Chongqing, China | 22.12.08
| Sub-total- Chineese |  | 100
OTHER UNITS
19 | Kashang -II & III , H.P. | 2x65 | 65 | Andritz Hydro, India | 01.12.10
20 | Sawara Kuddu, H.P. | 3x37 | 111 | Andritz Hydro, India | 05.02.09
21 | Sainj, H.P. |  | 100 | Voith Hydro, India | 17.08.11
22 | Koyna Left Bank PSS, Maharashtra | 2x40 | 80 | Litostroj Slovania Koncar, Croatia | 16.12.10
23 | New Umtru, Meghalaya | 2x20 | 40 | V.A. Tech, India | 25.02.09
24 | Shontong Karcham, H.P. | 3x150 | 450 | Andritz Hydro, India | 04.03.15
25 | Teesta St. III, (Sikkim) (*) | 6x200 | 1200 | Andritz Hydro, India | 18.10.07
| Sub-total- Others |  | 2046
| Sub-total (State Sector): |  | 2712
Private Sector
BHEL Units
26 | Maheshwar (M.P.) | 4x100 | 400 | BHEL | 25.06.07
| Sub-total- BHEL |  | 400
OTHER UNITS
27 | Ratle (J&K) | 4x205+1x30 | 850 | Alstom, India | 31.12.12
28 | Sorang (H.P.) | 2x50 | 100 | Voith Siemens, India | 06/2007
29 | Tidong-I, (H.P.) | 100 | 100 | Alstom, India | 28.02.11
30 | Tangnu Romai- I, (H.P.) | 2x22 | 44 | Andritz Hydro, India | 17.04.13
31 | Chanju-I, (H.P.) | 3x12 | 36 | B Fouress, India | 21.09.11
32 | Phata Byung, (Uttarakhand) | 76 | 76 | Alstom, India | 12.04.08
33 | Singoli Bhatwari, Uttarakhand | 3x33 | 99 | Voith Hydro, India | 15.06.11
34 | Rangit-IV, (Sikkim) | 3x40 | 120 | Andritz Hydro, India | 28.08.09
35 | Bhasmey, (Sikkim) | 2x25.5 | 51 | Voith Hydro, India | 14.04.10
36 | Teesta St. VI, (Sikkim) | 4x125 | 500 | Alstom, India | 04/2009
37 | Tashiding, (Sikkim) | 2x48.5 | 97 | Alstom, India | 21.05.10
38 | Rongnichu, (Sikkim) | 2x48 | 96 | Voith Hydro, India | 28.09.11
39 | Dikchu, (Sikkim) | 2x48 | 96 | Alstom, India | 07/2011
40 | Gongri, (Ar. Pradesh) | 2x72 | 144 | Andritz Hydro, India | 13.12.13
41 | Rangit-II, (Sikkim) | 2x33 | 66 | Gammon India Ltd. | 24.03.12
42 | Bajoli Holi, (H.P.) | 3x60 | 180 | Alstom, India | 20.02.15
| Sub-total- Others |  | 2655
| Sub-total (Private Sector): |  | 3055
| Under Execution Total (Units Ordered): |  | 11922
Units not yet ordered |  |  | 0
Central Sector
| Sub-total (Central Sector): |  | 0
State Sector
43 | Polavaram (PPA) Andhra Pr. | 12x80 | 960
44 | Parnai (JKSPDC) J&K | 3x12.5 | 37.5
45 | Lower Kalnai (JKSPDC) J&K | 2x24 | 48
| Sub-total (State Sector): |  | 1045.5
Private Sector
46 | Panan, Sikkim | 4x75 | 300
| Sub-total (Private Sector): |  | 300
Total: (Units not yet ordered) |  |  | 1345.5
| Total: Under execution |  | 13267.5
Legends: *C-Critical; *P-Partialy Commissioned ; *R-Subject to Re-Start of Works; *A-Subject to Active Start of works ; *AE-Subject to Active Start & Award of E&M Works; # :-Outside from the 12th Plan Programme, *S-Programme of 2016-17, however Slipping to 2017-18.
- 47-

## summ ch 5
SUMMARY- 12th Plan
|  | Central | State | Private | Total
| Commissioned | 2584 | 952 | 595 | 4131
| 12th plan Under Construction | 3420 | 1856 | 1490 | 6766
| U/Cons. Beyond 12th Plan | 2735 | 1901.5 | 1865 | 6501.5
| Total: (12th Plan) | 6004 | 2808 | 2085 | 10897
| Total: (12th Plan & Beyond) | 6155 | 3757.5 | 3355 | 13267.5